## Worksheet
Created | Requestor | Market | Store # | Item | Year Built | Timeline | Month Deployed | Estimated Cost | Updated Est. Cost | Commitment | Actual Cost | Variance | Carryover | Capex Type | Category | Equipment | Type | Status | Order Date | PO Number | Year | Priority | Quote Confirmed | Blendco Order | Notes History | Last Updated
2025-03-31 08:55:42 | David Carreon | 800 | 800 | 111 |  | Q1 | N/A | 3500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | IT | Technology | Prevent further damage | Deferred |  |  | 2025 | Low | No |  |  | 2026-02-02 15:31:24
2025-03-31 08:55:42 | David Carreon | 800 | 800 | Network Battery UPS replace |  | Q2 | April | 8000 |  | Uncommitted | 0 | 0 |  | Planned maintenance | IT | Technology | Customer Experience | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - testy: setting priority making it a 9 | 2026-01-12 11:59:20
2025-11-07 10:26:29 | Austin Webb | 100 | 100 | Market Spare 40 Vac Producer |  |  | N/A | 17000 |  |  | 0 | 0 | No | Prevent further damage | Equipment | Vacuum |  | 2026 Request |  |  | 2026 | High | No |  | 01/12/2026 - Joshua McCown: Spare based on historic needs Feb? 02/02/2026 - Eric Dunn: Spare based on historic needs Feb? | 2026-02-02 15:32:26
2025-11-07 10:26:29 | Austin Webb | 100 | 100 | Market Chain/Roller Conveyor Rebuild |  |  |  | 13500 |  |  | 0 | 0 | No | Prevent further damage | Equipment |  |  | 2026 Request |  |  | 2026 | High | No |  | 01/12/2026 - unknown: Spare based on historic needs | 2026-01-12 12:00:08
2025-11-07 10:26:29 | Austin Webb | 100 | 100 | Market Blower Assembly |  |  |  | 7000 |  |  | 0 | 0 | No | Prevent further damage | Equipment | Blowers |  | 2026 Request |  |  | 2026 | High | No |  | 01/12/2026 - unknown: Spare based on historic needs | 2026-01-12 12:00:08
2025-11-07 10:26:29 | Austin Webb | 100 | 100 | Mitter Basket Rebuild |  |  |  | 5500 |  |  | 0 | 0 | No | Prevent further damage | Equipment |  |  | 2026 Request |  |  | 2026 | High | No |  | 01/12/2026 - unknown: | 2026-01-12 12:00:08
2025-11-07 10:26:29 | Austin Webb | 100 | 100 | Mitter Basket Rebuild |  |  |  | 5500 |  |  | 0 | 0 | No | Prevent further damage | Equipment |  |  | 2026 Request |  |  | 2026 | High | No |  | 01/12/2026 - unknown: | 2026-02-16 19:57:42
2025-11-07 10:26:29 | Austin Webb | 100 | 100 | Wrap Brush Rebuild |  |  |  | 5000 |  |  | 0 | 0 | No | Prevent further damage | Equipment |  |  | 2026 Request |  |  | 2026 | High | No |  | 01/12/2026 - unknown: Spare based on historic needs | 2026-01-12 12:00:08
2025-11-07 10:26:29 | Austin Webb | 100 | 100 | Tire Brush Rebuild |  |  |  | 4500 |  |  | 0 | 0 | No | Prevent further damage | Equipment |  |  | 2026 Request |  |  | 2026 | High | No |  | 01/12/2026 - unknown: Spare based on historic needs | 2026-01-12 12:00:08
2025-11-07 10:26:29 | Austin Webb | 100 | 100 | Tire Brush Rebuild |  |  |  | 4500 |  |  | 0 | 0 | No | Prevent further damage | Equipment |  |  | 2026 Request |  |  | 2026 | High | No |  | 01/12/2026 - unknown: Spare based on historic needs | 2026-01-12 12:00:08
2025-11-07 10:26:29 | Austin Webb | 100 | 100 | Tire Brush Rebuild |  |  |  | 4500 |  |  | 0 | 0 | No | Prevent further damage | Equipment |  |  | 2026 Request |  |  | 2026 | High | No |  | 01/12/2026 - unknown: Spare based on historic needs | 2026-01-12 12:00:08
2025-11-07 10:26:29 | Austin Webb | 100 | 100 | Power Pack Rebuild |  |  |  | 4000 |  |  | 0 | 0 | No | Prevent further damage | Equipment |  |  | 2026 Request |  |  | 2026 | High | No |  | 01/12/2026 - unknown: Based on historic needs | 2026-01-12 12:00:08
2025-11-07 10:26:29 | Austin Webb | 100 | 100 | Power Pack Rebuild |  |  |  | 4000 |  |  | 0 | 0 | No | Prevent further damage | Equipment |  |  | 2026 Request |  |  | 2026 | High | No |  | 01/12/2026 - unknown: Based on historic needs | 2026-01-12 12:00:08
2025-11-07 10:26:29 | Austin Webb | 100 | 100 | Pump (2) Market Spare Hydraflex F&W Pump |  |  |  | 4000 |  |  | 0 | 0 | No | Prevent further damage | Equipment |  |  | 2026 Request |  |  | 2026 | High | No |  | 01/12/2026 - unknown: Spare based on historic needs | 2026-01-12 12:00:08
2025-11-07 10:26:29 | Ryan Payne | 200 | 200 | Market Spare Hydraflex Grundfos Pump |  |  |  | 8000 |  |  | 0 | 0 | No | Prevent further damage | Equipment |  |  | 2026 Request |  |  | 2026 | High | No |  | 01/12/2026 - unknown: Spare based on historic needs | 2026-01-12 12:00:08
2025-11-07 10:26:29 | Ryan Payne | 200 | 200 | Market Spare Hydraflex Grundfos Pump |  |  |  | 8000 |  |  | 0 | 0 | No | Prevent further damage | Equipment |  |  | 2026 Request |  |  | 2026 | High | No |  | 01/12/2026 - unknown: Spare based on historic needs | 2026-01-12 12:00:08
2025-11-07 10:26:29 | Ryan Payne | 200 | 200 | HVAC |  |  |  | 8000 |  |  | 0 | 0 | No | Prevent further damage | Equipment |  |  | 2026 Request |  |  | 2026 | High | No |  | 01/12/2026 - unknown: Acclocation based on historic needs, 10/14/25 - Need more detail - GM | 2026-01-12 12:00:08
2025-11-07 10:26:29 | Ryan Payne | 200 | 200 | HVAC |  |  |  | 8000 |  |  | 0 | 0 | No | Prevent further damage | Equipment |  |  | 2026 Request |  |  | 2026 | High | No |  | 01/12/2026 - unknown: Acclocation based on historic needs 10/14/25 - Need more detail - GM | 2026-01-12 12:00:08
2025-11-07 10:26:29 | Ryan Payne | 200 | 200 | Market Blower Assembly |  |  |  | 7000 |  |  | 0 | 0 | No | Prevent further damage | Equipment | Blowers |  | 2026 Request |  |  | 2026 | High | No |  | 01/12/2026 - unknown: Spare based on historic needs | 2026-01-12 12:00:08
2025-11-07 10:26:29 | Ryan Payne | 200 | 200 | Market Blower Assembly |  |  |  | 7000 |  |  | 0 | 0 | No | Prevent further damage | Equipment | Blowers |  | 2026 Request |  |  | 2026 | High | No |  | 01/12/2026 - unknown: Spare based on historic needs 03/31/2026 - Eric Dunn: Spare based on historic needs... | 2026-03-31 12:26:31
2025-11-07 10:26:29 | Ryan Payne | 200 | 200 | Market Blower Assembly |  |  |  | 7000 |  |  | 0 | 0 | No | Prevent further damage | Equipment | Blowers |  | 2026 Request |  |  | 2026 | High | No |  | 01/12/2026 - unknown: Spare based on historic needs | 2026-01-12 12:00:08
2025-11-07 10:26:29 | Ryan Payne | 200 | 200 | Market Spare Compressor |  |  |  | 5500 |  |  | 0 | 0 | No | Prevent further damage | Equipment | Compressors Replacement |  | 2026 Request |  |  | 2026 | High | No |  | 01/12/2026 - unknown: Spare based on historic needs | 2026-01-12 12:00:08
2025-11-07 10:26:29 | Ryan Payne | 200 | 200 | Market Spare Compressor |  |  |  | 5500 |  |  | 0 | 0 | No | Prevent further damage | Equipment | Compressors Replacement |  | 2026 Request |  |  | 2026 | High | No |  | 01/12/2026 - unknown: Spare based on historic needs 03/31/2026 - Eric Dunn: Spare based on historic needs... | 2026-03-31 22:25:16
2025-11-07 10:26:29 | Ryan Payne | 200 | 200 | Pump (2) Market Spare Hydraflex F&W Pump |  |  |  | 4000 |  |  | 0 | 0 | No | Prevent further damage | Equipment |  |  | 2026 Request |  |  | 2026 | High | No |  | 01/12/2026 - unknown: Spare based on historic needs | 2026-01-12 12:00:08
2025-11-07 10:26:29 | Ryan Payne | 200 | 200 | Pump (2) Market Spare Hydraflex F&W Pump |  |  |  | 4000 |  |  | 0 | 0 | No | Prevent further damage | Equipment |  |  | 2026 Request |  |  | 2026 | High | No |  | 01/12/2026 - unknown: Spare based on historic needs | 2026-01-12 12:00:08
2025-11-07 10:26:29 | Ryan Payne | 200 | 200 | Pump (2) Market Spare Hydraflex F&W Pump |  |  |  | 4000 |  |  | 0 | 0 | No | Prevent further damage | Equipment |  |  | 2026 Request |  |  | 2026 | High | No |  | 01/12/2026 - unknown: Spare based on historic needs | 2026-01-12 12:00:08
2025-11-07 10:26:29 | Ryan Payne | 200 | 200 | Pump (2) Market Spare Hydraflex F&W Pump |  |  |  | 4000 |  |  | 0 | 0 | No | Prevent further damage | Equipment |  |  | 2026 Request |  |  | 2026 | High | No |  | 01/12/2026 - unknown: Spare based on historic needs | 2026-01-12 12:00:08
2025-11-07 10:26:29 | Ryan Payne | 200 | 200 | Power Pack Rebuild |  |  |  | 4000 |  |  | 0 | 0 | No | Prevent further damage | Equipment |  |  | 2026 Request |  |  | 2026 | High | No |  | 01/12/2026 - unknown: Based on historic needs | 2026-01-12 12:00:08
2025-11-07 10:26:29 | Ryan Payne | 200 | 200 | Power Pack Rebuild |  |  |  | 4000 |  |  | 0 | 0 | No | Prevent further damage | Equipment |  |  | 2026 Request |  |  | 2026 | High | No |  | 01/12/2026 - unknown: Based on historic needs | 2026-01-12 12:00:08
2025-11-07 10:26:29 | Ryan Payne | 400 | 400 | planned cappex PM budget belt sites |  |  |  | 25000 |  |  | 0 | 0 | No | Prevent further damage | Equipment | Conveyor Belt |  | 2026 Request |  |  | 2026 | High | No |  | 01/12/2026 - unknown: | 2026-01-12 12:00:08
2025-11-07 10:26:29 | Ryan Payne | 400 | 400 | Thinner grand entry arches for belt sites- 407, 408, 409, 410 |  |  |  | 40000 |  |  | 0 | 0 | No | Customer Experience | Equipment | Building Facilities |  | 2026 Request |  |  | 2026 | Medium | No |  | 01/12/2026 - unknown: | 2026-01-12 12:01:41
2025-11-07 10:26:29 | Ryan Payne | 400 | 400 | Wrap Brush Rebuild |  |  |  | 5000 |  |  | 0 | 0 | No | Prevent further damage | Equipment |  |  | 2026 Request |  |  | 2026 | High | No |  | 01/12/2026 - unknown: Spare based on historic needs | 2026-01-12 12:00:08
2025-11-07 10:26:29 | Ryan Payne | 400 | 400 | Tire Brush Rebuild |  |  |  | 4500 |  |  | 0 | 0 | No | Prevent further damage | Equipment |  |  | 2026 Request |  |  | 2026 | High | No |  | 01/12/2026 - unknown: Spare based on historic needs | 2026-01-12 12:00:08
2025-11-07 10:26:29 | Ryan Payne | 400 | 400 | Power Pack Rebuild |  |  |  | 4000 |  |  | 0 | 0 | No | Prevent further damage | Equipment |  |  | 2026 Request |  |  | 2026 | High | No |  | 01/12/2026 - unknown: Based on historic needs 02/19/2026 - Philip Loper: 02/19 - Sent Rusty and team an email to request additional information on this project. This is placed as 401 on Ruty's sheet he sent | 2026-01-12 12:00:08
2025-11-07 10:26:29 | Austin Webb |  |  | Camera system (vast upgrade) |  |  |  | 3000 |  |  | 0 | 0 | No | Customer Experience | Equipment | Camera |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: | 2026-01-12 12:02:24
2025-11-07 10:36:13 | Lauren Fine | 300 | 300 | Pump (2) Market Spare Hydraflex F&W Pump |  |  |  | 4000 |  |  | 0 | 0 | No | Prevent further damage | Equipment |  |  | 2026 Request |  |  | 2026 | High | No |  | 01/12/2026 - unknown: Anticipated based on historic needs | 2026-01-12 12:00:08
2025-11-07 10:36:13 | Lauren Fine | 300 | 300 | Blower Assembly |  |  |  | 7000 |  |  | 0 | 0 | No | Prevent further damage | Equipment |  |  | 2026 Request |  |  | 2026 | High | No |  | 01/12/2026 - unknown: Anticipated based on historic needs 03/31/2026 - Eric Dunn: Anticipated based on historic needs.. | 2026-03-31 22:25:36
2025-11-07 10:36:13 | Lauren Fine | 300 | 300 | Tire Brush Rebuild |  |  |  | 4500 |  |  | 0 | 0 | No | Prevent further damage | Equipment |  |  | 2026 Request |  |  | 2026 | High | No |  | 01/12/2026 - unknown: Anticipated based on historic needs | 2026-01-12 12:00:08
2025-11-07 10:36:13 | Lauren Fine | 300 | 300 | Wrap Brush Rebuild |  |  |  | 5000 |  |  | 0 | 0 | No | Prevent further damage | Equipment |  |  | 2026 Request |  |  | 2026 | High | No |  | 01/12/2026 - unknown: Anticipated based on historic needs | 2026-01-12 12:00:08
2025-11-07 10:36:13 | Lauren Fine | 300 | 300 | Market Spare 40 Vac Producer |  |  |  | 17000 |  |  | 0 | 0 | No | Prevent further damage | Equipment |  |  | 2026 Request |  |  | 2026 | High | No |  | 01/12/2026 - unknown: Anticipated based on historic needs | 2026-01-12 12:00:08
2025-11-07 10:36:13 | Lauren Fine | 500 | 500 | Power Pack Rebuild |  |  |  | 4000 |  |  | 0 | 0 | No | Prevent further damage | Equipment |  |  | 2026 Request |  |  | 2026 | High | No |  | 01/12/2026 - unknown: Based on historic needs | 2026-01-12 12:00:08
2025-11-07 10:36:13 | Lauren Fine | 500 | 500 | Power Pack Rebuild |  |  |  | 4000 |  |  | 0 | 0 | No | Prevent further damage | Equipment |  |  | 2026 Request |  |  | 2026 | High | No |  | 01/12/2026 - unknown: Based on historic needs | 2026-01-12 12:00:08
2025-11-07 10:36:13 | Lauren Fine | 500 | 500 | Market Grundfos Replacement |  |  |  | 8000 |  |  | 0 | 0 | No | Prevent further damage | Equipment |  |  | 2026 Request |  |  | 2026 | High | No |  | 01/12/2026 - unknown: Anticipated based on historic needs | 2026-01-12 12:00:08
2025-11-07 10:36:13 | Lauren Fine | 500 | 500 | Blower Assembly |  |  |  | 7000 |  |  | 0 | 0 | No | Prevent further damage | Equipment |  |  | 2026 Request |  |  | 2026 | High | No |  | 01/12/2026 - unknown: Anticipated based on historic needs | 2026-01-12 12:00:08
2025-11-07 10:36:13 | Lauren Fine | 500 | 500 | Pump (2) Market Spare Hydraflex F&W Pump |  |  |  | 4000 |  |  | 0 | 0 | No | Prevent further damage | Equipment |  |  | 2026 Request |  |  | 2026 | High | No |  | 01/12/2026 - unknown: Anticipated based on historic needs | 2026-01-12 12:00:08
2025-11-07 10:36:13 | Lauren Fine | 500 | 500 | Tire Brush Rebuild |  |  |  | 4500 |  |  | 0 | 0 | No | Prevent further damage | Equipment |  |  | 2026 Request |  |  | 2026 | High | No |  | 01/12/2026 - unknown: Anticipated based on historic needs | 2026-01-12 12:00:08
2025-11-07 10:36:13 | Lauren Fine | 500 | 500 | Tire Brush Rebuild |  |  |  | 4500 |  |  | 0 | 0 | No | Prevent further damage | Equipment |  |  | 2026 Request |  |  | 2026 | High | No |  | 01/12/2026 - unknown: Anticipated based on historic needs | 2026-01-12 12:00:08
2025-11-07 10:36:13 | Lauren Fine | 500 | 500 | Wrap Brush Rebuild |  |  |  | 5000 |  |  | 0 | 0 | No | Prevent further damage | Equipment |  |  | 2026 Request |  |  | 2026 | High | No |  | 01/12/2026 - unknown: Anticipated based on historic needs | 2026-01-12 12:00:08
2025-11-07 10:36:13 | Benjamin Herr | 700 | 700 | Chain and Roller Conveyor Rebuild |  |  |  | 13500 |  |  | 0 | 0 | No | Prevent further damage | Equipment | Conveyor Chain |  | 2026 Request |  |  | 2026 | Medium | No |  | 01/12/2026 - unknown: | 2026-01-12 12:01:41
2025-11-07 10:36:13 | Benjamin Herr | 700 | 700 | Chain and Roller Conveyor Rebuild |  |  |  | 13500 |  |  | 0 | 0 | No | Prevent further damage | Equipment | Conveyor Chain |  | 2026 Request |  |  | 2026 | Medium | No |  | 01/12/2026 - unknown: | 2026-01-12 12:01:41
2025-11-07 10:36:13 | Benjamin Herr | 700 | 700 | Blower Assembly |  |  |  | 7000 |  |  | 0 | 0 | No | Prevent further damage | Equipment |  |  | 2026 Request |  |  | 2026 | High | No |  | 01/12/2026 - unknown: Anticipated based on historic needs | 2026-01-12 12:00:08
2025-11-07 10:36:13 | Benjamin Herr | 700 | 700 | Pump (2) Market Spare Hydraflex F&W Pump |  |  |  | 4000 |  |  | 0 | 0 | No | Prevent further damage | Equipment |  |  | 2026 Request |  |  | 2026 | High | No |  | 01/12/2026 - unknown: Anticipated based on historic needs | 2026-01-12 12:00:08
2025-11-07 10:36:13 | Benjamin Herr | 700 | 700 | Tire Brush Rebuild |  |  |  | 4500 |  |  | 0 | 0 | No | Prevent further damage | Equipment |  |  | 2026 Request |  |  | 2026 | High | No |  | 01/12/2026 - unknown: Anticipated based on historic needs | 2026-01-12 12:00:08
2025-11-07 10:36:13 | Benjamin Herr | 700 | 700 | Wrap Brush Rebuild |  |  |  | 5000 |  |  | 0 | 0 | No | Prevent further damage | Equipment |  |  | 2026 Request |  |  | 2026 | High | No |  | 01/12/2026 - unknown: Anticipated based on historic needs | 2026-01-12 12:00:08
2025-11-07 10:36:13 | Josh McCown | 800 | 800 | EMV Hotspot Upgrade |  |  |  | 15000 |  |  | 0 | 0 | No | Prevent further damage | IT | Technology |  | 2026 Request |  |  | 2026 | Medium | No |  | 01/12/2026 - unknown: Upgrade 14 sites to inseego hotspot for EMV ISP backup 03/31/2026 - Eric Dunn: Upgrade 14 sites to Inseego hotspot for EMV ISP backup.. | 2026-03-31 12:29:01
2025-11-07 10:36:13 | Caleb Harris | 800 | 800 | Spare Grundfos Replacement |  |  |  | 8500 |  |  | 0 | 0 | No | Prevent further damage | Equipment |  |  | 2026 Request |  |  | 2026 | Medium | No |  | 01/12/2026 - unknown: WX800 Market 09/24/25 - Sent and email to Terry @ Sonnys and requested a proposal for a 40 GPM and 20 GPM pump for spare - PL 09/25/25 - I recieved a quote for a 20 GPM and a 40 GPM and placed them in the folder. - PL | 2026-01-12 12:01:41
2025-11-07 10:36:13 | Caleb Harris | 800 | 800 | Pump (2) Market Spare Hydraflex F&W Pump |  |  |  | 4000 |  |  | 0 | 0 | No | Prevent further damage | Equipment |  |  | 2026 Request |  |  | 2026 | High | No |  | 01/12/2026 - unknown: Anticipated based on historic needs | 2026-01-12 12:00:08
2025-11-07 10:36:13 | Caleb Harris | 800 | 800 | Tire Brush Rebuild |  |  |  | 4500 |  |  | 0 | 0 | No | Prevent further damage | Equipment |  |  | 2026 Request |  |  | 2026 | High | No |  | 01/12/2026 - unknown: Anticipated based on historic needs | 2026-01-12 12:00:08
2025-11-07 10:36:13 | Caleb Harris | 800 | 800 | Spare Market 40 HP Vac Producer (Spencer) |  |  |  | 17000 |  |  | 0 | 0 | No | Prevent further damage | Equipment |  |  | 2026 Request |  |  | 2026 | Medium | No |  | 01/12/2026 - unknown: | 2026-01-12 12:01:41
2025-11-07 10:26:29 | Josh McCown |  | 99 | DRB Query Server upgrade Windows 11 |  |  |  | 3000 |  |  | 0 | 0 | No | Prevent further damage | IT | Technology |  | 2026 Request |  |  | 2026 | Medium | No |  | 01/12/2026 - unknown: 03/31/2026 - Eric Dunn: test | 2026-01-12 12:01:41
2025-03-31 08:55:40 | Abel Smith | 100 | 101 | Air Compressor | 2015 | -------- | N/A | 7000 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Compressors Replacement | Wash Quality | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - unknown: Completed in 2024 JS - test | 2026-01-12 12:31:32
2025-03-31 08:55:40 | Mason Faltysek | 100 | 101 | Tunnel Liner Wall Panels | 2015 | Q2 | N/A | 14000 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Building Facilities | Customer Experience | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-11-07 10:26:29 | Austin Webb | 100 | 101 | TCS1 Upgrade |  |  | N/A | 45000 |  |  | 0 | 0 | No | Prevent further damage | IT | Technology |  | 2026 Request |  |  | 2026 | Low | No |  |  | 2026-01-12 12:02:24
2025-11-07 10:26:29 | Austin Webb | 100 | 101 | Chem room door replacement |  |  |  | 7000 |  |  | 0 | 0 | No | Prevent further damage | Building/Site | Facilities Site Work |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: | 2026-05-19 11:55:45
2025-11-07 10:26:29 | Austin Webb | 100 | 101 | Upgrade XPTs to XPT5+ from XPT 2012 - Replace with SAL use XPT for parts |  |  |  | 3500 |  |  | 0 | 0 | No | Prevent further damage | IT | XPT |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: 02/23/2026 - Rusty Modesty: Updated estimated cost from $6,000 to $3,500. | 2026-02-23 17:15:57
2025-11-07 10:26:29 | Austin Webb | 100 | 101 | Oval building sign |  |  | N/A | 8500 |  | Uncommitted | 0 | 0 | No | Prevent further damage | Building/Site | Facilities Site Work |  | Deferred |  |  | 2026 | High | No |  | 01/12/2026 - gregg: 11-20 - GM - Pricing has been requested. Expecting pricing week of 11/24 02/24/2026 - Rusty Modesty: Committed July | 2026-07-18 19:27:14
2026-05-13 16:26:23 | David Carreon | 100 | 101 | Tunnel OTT | 2016 |  | April | 3500 |  | Committed | 0 | 0 | No | Planned maintenance |  | Technology |  | Completed |  | EQ-0101-2026-1771 |  | High | No |  |  | 2026-05-13 16:26:23
2025-03-31 08:55:40 | Abel Smith | 100 | 102 | Chain | 2016 | Q4 | N/A | 13000 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Equipment | chain/roller | Wash Quality | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - rusty: New Chain, Rollers, Entrance rebuild, Exit Sprocket | 2026-01-12 11:59:20
2025-11-07 10:26:29 | Austin Webb | 100 | 102 | TCS1 Upgrade |  |  |  | 45000 |  |  | 0 | 0 | No | Prevent further damage | IT | Technology |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: | 2026-01-12 12:02:24
2025-11-07 10:26:29 | Austin Webb | 100 | 102 | Chem room door replacement |  |  |  | 7000 |  |  | 0 | 0 | No | Prevent further damage | Building/Site | Facilities Site Work |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - mason: Bid received from renascent pricing updated to reflect bid 11/26 MF | 2026-01-12 12:02:24
2025-11-07 10:26:29 | Austin Webb | 100 | 102 | Upgrade XPTs to XPT5+ from XPT 2012 - Replace with SAL use XPT for parts |  |  |  | 3500 |  |  | 0 | 0 | No | Prevent further damage | IT | XPT |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: 02/23/2026 - Rusty Modesty: Updated estimated cost from $6,000 to $3,500. | 2026-02-23 17:16:18
2025-11-07 10:26:29 | Austin Webb | 100 | 102 | Conveyor Chain/Rollers |  |  | January | 14649 |  | Committed | 12304.14 | 2344.86 | No | Prevent further damage | Equipment | Conveyor Chain | Prevent further damage | Completed | 2026-01-08 | EQ-0102-2026-1628 | 2026 | Low | Yes |  |  | 2026-02-23 10:54:12
2025-03-31 08:55:40 | Abel Smith | 100 | 103 | Grandfos - 2 20 GPM Grundfos Pumps - 460V | 2017 | Q4 | N/A | 16000 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Equipment | Hydroflex | Wash Quality | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - rusty: Deferred per AW and JS | 2026-01-12 12:31:32
2025-03-31 08:55:40 | Abel Smith | 100 | 103 | Tire brush - Poodle brush | 2017 | Q1 | N/A | 4500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Equipment | Hydroflex | Wash Quality | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:40 | Mason Faltysek | 100 | 103 | Parking lot restripe | 2017 | Q3 | N/A | 6500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Facilities Site Work | Customer Experience | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-11-07 10:26:29 | Austin Webb | 100 | 103 | Reclaim (one from LA?) |  |  | N/A | 6000 |  | Uncommitted | 0 | 0 | No | Wash Quality | Equipment |  |  | Deferred |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: Unsure of Project Viability. Will need verification - understood - AW 02/24/2026 - Rusty Modesty: Marked as Committed Oct. | 2026-09-15 15:44:29
2025-11-07 10:26:29 | Austin Webb | 100 | 103 | TCS1 Upgrade |  |  |  | 45000 |  |  | 0 | 0 | No | Prevent further damage | IT | Technology |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: | 2026-01-12 12:02:24
2025-11-07 10:26:29 | Austin Webb | 100 | 103 | Upgrade XPTs to XPT5+ from XPT 2012 |  |  |  | 40000 |  |  | 0 | 0 | No | Prevent further damage | IT | XPT |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: | 2026-01-12 12:02:24
2025-11-07 10:26:29 | Austin Webb | 100 | 103 | Chem room door replacement |  |  |  | 7000 |  |  | 0 | 0 | No | Prevent further damage | Building/Site | Facilities Site Work |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - mason: Bid received from renascent pricing updated to reflect bid 11/26 MF | 2026-01-12 12:02:24
2025-11-07 10:26:29 | Austin Webb | 100 | 103 | Vacuum turbine |  |  |  | 18514 |  | Uncommitted | 0 | 0 | No | Prevent further damage | Equipment | Vacuum |  | Deferred |  |  | 2026 | High | Yes |  | 01/12/2026 - unknown: 10/01/25 - This value is for the turbine with includes freight. This does not include any additional parts, labor, or additional materials. - PL 02/17/2026 - Philip Loper: 02/16 - Sent an email to Chris @ NCS for a proposal. 02/23/2026 - Philip Loper: 02/23 - Sent an update request to Chris @ NCS 02/24/2026 - Philip Loper: 02/24 - Received the proposal from NCS. It has been placed in the CAPEX Folder. The cost w/ tax and freight is $16,804.61 02/24/2026 - Rusty Modesty: Marked as Committed | 2026-04-21 12:59:54
2026-07-28 13:02:57 | Andrew Folse | 100 | 103 | 20gpm Grundfoss Pump |  |  | August | 9000 |  | Committed | 0 | 0 | No | Planned maintenance | Equipment | Hydroflex | Prevent further damage | Completed | 2026-08-01 | EQ-0103-2026-1932 |  | High | No | No |  | 2026-09-16 15:17:51
2025-03-31 08:55:40 | Abel Smith | 100 | 104 | Mitter Carriage | 2017 | Q2 | August | 5300 |  | Committed | 5189.54 | 110.46 |  | Planned maintenance | Equipment | Mitter | Wash Quality | Completed |  | EQ-0104-2025-1418 | 2025 | Low | Yes |  |  | 2026-02-23 10:54:26
2025-03-31 08:55:40 | Abel Smith | 100 | 104 | Airlines and plumbing - Overflow vac area | 2017 | Q2 | Completed | 8000 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Facilities Site Work | Customer Experience | Completed |  |  | 2025 | Low | No |  | 01/12/2026 - unknown: JS-Completed 11/26/2024 by Short Coompany. Not sure how this got into 2025's CapEx requests. 04/21/2026 - Jonathan Blair: JS-Completed 11/26/2024 by Short Coompany. Not sure how this got into 2025's CapEx requests. | 2026-04-21 12:45:34
2025-03-31 08:55:40 | Mason Faltysek | 100 | 104 | Concrete -Tunnel drainage | 2017 | Q3 | N/A | 5000 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Building Facilities | Prevent further damage | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:40 | Abel Smith | 100 | 104 | Chain - New Rollers | 2017 | Q4 | April | 12000 |  | Committed | 15483.72 | -3483.72 |  | Planned maintenance | Equipment | chain/roller | Wash Quality | Completed |  | EQ-0104-2025-1267 | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-11-07 10:26:29 | Austin Webb | 100 | 104 | Door laundry room. |  |  |  | 5000 |  |  | 0 | 0 | No | Customer Experience | Building/Site | Facilities Site Work |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - mason: Bid received from renascent pricing updated to reflect bid 11/26 MF | 2026-01-12 12:02:24
2025-11-07 10:26:29 | Austin Webb | 100 | 104 | Chem room door replacement |  |  |  | 7000 |  |  | 0 | 0 | No | Prevent further damage | Building/Site | Facilities Site Work |  | 2026 Request |  |  | 2026 | Low | No |  |  | 2026-01-12 12:02:24
2025-11-07 10:26:29 | Austin Webb | 100 | 104 | TCS1 Upgrade |  |  |  | 45000 |  |  | 0 | 0 | No | Prevent further damage | IT | Technology |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: | 2026-01-12 12:02:24
2025-11-07 10:26:29 | Austin Webb | 100 | 104 | Upgrade XPTs to XPT5+ from XPT 2012 - Replace with SAL use XPT for parts |  |  |  | 3500 |  |  | 0 | 0 | No | Prevent further damage | IT | XPT |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: 02/23/2026 - Rusty Modesty: Updated estimated cost from $6,000 to $3,500. | 2026-02-23 17:17:32
2025-11-07 10:26:29 | Austin Webb | 100 | 104 | Tunnel Drainage |  |  | N/A | 0 |  | Uncommitted | 0 | 0 | No | Safety | Building/Site | Facilities Site Work |  | Deferred |  |  | 2026 | Medium | No |  | 01/12/2026 - Henry Shine: 5000 will not cover amount to correct the issue Bid comes in around 26k 02/24/2026 - Rusty Modesty: Updated Committed and price from $5000 to $26k 05/18/2026 - Andrew Folse: Discussion week of 5/11: Need to ensure site staff is properly cleaning mud out of cuts and holes in concrete and doing their part to ensure drainage before spending this much to address the issue. Need to follow up with RD & AD on 5/29. Meeting already scheduled. Pushed deployment month to July 05/29/2026 - Andrew Folse: After discussion with RD we have decided not to action this request. | 2026-05-29 18:56:39
2025-11-07 10:26:29 | Austin Webb | 100 | 105 | Chem room door replacement |  |  |  | 7000 |  |  | 0 | 0 | No | Prevent further damage | Building/Site | Facilities Site Work |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: | 2026-01-12 12:02:24
2025-11-07 10:26:29 | Austin Webb | 100 | 105 | 105 - CapEx Vac Producer |  |  | March | 18514 |  | Committed | 17660.58 | 853.42 | No | Prevent further damage | Equipment | Vacuum |  | Completed |  | EQ-0105-2026-1679 | 2026 | High | Yes |  |  | 2026-09-15 15:54:26
2025-11-07 10:26:29 | Austin Webb | 100 | 105 | Air compressor |  |  | April | 5700 |  | Committed | 4432.71 | 1267.29 | No | Prevent further damage | Equipment | Compressors Replacement | Wash Quality | Completed | 2026-04-01 | EQ-0105-2026-1730 | 2026 | High | Yes |  | 01/12/2026 - Austin Webb: WX105 02/16/2026 - Jonathan Blair: Went from 5,500 to 5,700 02/17/2026 - Philip Loper: Compressor with tax and freight is $4,104.84 02/17/2026 - Philip Loper: 02/16 - Sent an email to Green Vall Compressor for a proposal opn a 460v system. Recieved the quote 02/17/2026 - Philip Loper: Cost for Compressor and freight is $4,104.84 04/01/2026 - Andrew Folse: Quote approved, order placed with Green Valley Compressor 04/21/2026 - Andrew Folse: Compressor onsite | 2026-05-04 15:27:29
2025-11-07 10:26:29 | Austin Webb | 100 | 106 | Vacuum turbine |  |  | March | 18514 |  | Committed | 17068.61 | 1445.39 | No | Prevent further damage | Equipment | Vacuum |  | Completed | 2026-03-04 | EQ-0106-2026-1700 | 2026 | High | Yes |  | 01/12/2026 - unknown: 10/01/25 - This value is for the turbine with includes freight. This does not include any additional parts, labor, or additional materials. - PL 02/17/2026 - Philip Loper: 02/16 - Sent an email to Chris @ NCS and requested a proposal. 02/24/2026 - Philip Loper: 02/24 - Sent a follow up email to Chris requesting a status update 02/24/2026 - Rusty Modesty: Marked as Committed 02/25/2026 - Philip Loper: 02/25 - VCS returned the quote, and it has been placed in the capex folder. Cost is $16,804.61 before install 03/02/2026 - Philip Loper: 03/02 - Submitted ofr CAPEX PO Number 03/04/2026 - Philip Loper: Capex was approved on 03/03/26 @ 10:22pm 03/04/2026 - Philip Loper: This was ordered on 03/04/26. Order invoice from NCS is saved in the CAPEX folder. | 2026-04-22 16:22:52
2025-11-07 10:26:29 | Austin Webb | 100 | 106 | Air Compressor |  |  | April | 5700 |  | Committed | 4498.75 | 1201.25 | No | Wash Quality | Equipment | Compressors Replacement | Wash Quality | Completed | 2026-04-01 | EQ-0106-2026-1731 | 2026 | High | Yes |  | 01/12/2026 - unknown: 02/16/2026 - Jonathan Blair: Went from 5,500 to 5,700. 02/17/2026 - Philip Loper: Price of compressor with tax and freight $4,104.84 02/27/2026 - Philip Loper: Joe Shanklin has conformed the store voltage for this Compressor needs to be *****240V***** 04/01/2026 - Andrew Folse: Quote confirmed, order placed with Green Valley Compressor 04/21/2026 - Andrew Folse: Compressor onsite | 2026-05-04 15:27:45
2025-03-31 08:55:41 | Mason Faltysek | 100 | 107 | Roof - Gutter down spout | 2020 | Q1 | N/A | 11500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Building Facilities | Prevent further damage | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:41 | Mason Faltysek | 100 | 107 | Signage - New WW Entrance Arch | 2020 | Q2 | N/A | 12000 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Equipment | marketing/signage | Customer Experience | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - rusty: Changing from replacement to face change only | 2026-01-12 12:31:32
2025-03-31 08:55:41 | Abel Smith | 100 | 107 | Tire Brush - Replace Ninja Brushes/Rebuild completely | 2020 | Q3 | May | 4500 |  | Committed | 8866.25 | -4366.25 |  | Planned maintenance | Equipment | Tire Shine | Wash Quality | Completed |  | EQ-0107-2025-1260 | 2025 | Low | No |  | 01/12/2026 - rusty: Project is partially complete 9/8 Parts were reutilized for an emergency project, delaying completion. | 2026-01-12 12:31:32
2025-11-07 10:26:29 | Austin Webb | 100 | 107 | Market Chain/Roller Conveyor Rebuild |  |  | April | 15500 |  | Committed | 12326.55 | 3173.45 | No | Prevent further damage | Equipment |  |  | Completed | 2026-03-26 | EQ-0107-2026-1722 | 2026 | High | Yes |  | 01/12/2026 - unknown: Spare based on historic needs 02/16/2026 - Jonathan Blair: Spare based on historic needs 02/16/2026 - Jonathan Blair: Assigned to 107 02/16/2026 - Jonathan Blair: Went from 13,500 to 15,500. 02/17/2026 - Philip Loper: Recieved quote from Vaughn. Cost is $9,832.13. This is for Chain and Rollers only. 03/25/2026 - Philip Loper: Capex has been submitted for approval. 03/26/2026 - Philip Loper: Placed order for chain and rollers from Vaughn. Also ordered sprocket and drum kit from Sonnys. CC'd awebb@whitewatercw.com afolse@whitewatercw.com jshanklin@whitewatercw.com 04/21/2026 - Andrew Folse: Complete on 4/16 | 2026-04-21 12:24:11
2025-11-07 10:26:29 | Austin Webb | 100 | 107 | adding gutter down spouts and french drain to tunnel gutters | [6 empty] | 0 | 0 | No | Safety | Building/Site | Facilities Site Work |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: | 2026-01-12 12:02:24
2025-11-07 10:26:29 | Austin Webb | 100 | 108 | Grand Entry Arch (Just Facings) |  |  |  | 1900 |  |  | 0 | 0 | No | Customer Experience | Equipment | Building Facilities |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: WX108- Just facing needing replaced 09/18/25 - Sent an email to Terry @ Sonnys requesting a quote for faces only no cabinets - PL 09/22/25 - Terry has returned the proposal and I have placed it in the folder. - PL (Likely not capex threshold-RM) | 2026-01-12 12:02:24
2025-03-31 08:55:41 | Rusty Modesty | 100 | 109 | Water Softner - Water softeners (units on-site are small, requesting bigger units like rest of the market- TA) | 2021 | Q2 | N/A | 13000 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Equipment | Water Softener | Wash Quality | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - rusty: Sonnys has become non-responsive on estimates. Moving forward with sobrite. Gaining price from Short Co on removal and install. | 2026-01-12 12:31:32
2025-08-19 13:54:00 | Abel Smith | 100 | 109 | Second Poodle Brush |  | Q4 | N/A | 0 |  | Uncommitted | 0 | 0 | No | Planned maintenance | Equipment | Wheel Brush | Customer Experience | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - rusty: Duplicate Project | 2026-01-12 12:31:32
2025-08-19 14:11:39 | Abel Smith | 100 | 109 | Wheel Brush (2) Rebuild |  | Q4 | N/A | 8000 |  | Uncommitted | 0 | 0 | No | Planned maintenance | Equipment | Wheel Brush | Customer Experience | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - rusty: Rebuild of Second Wheel Brush (Did not meet capex threshold. Will be R&M. -RM/JS | 2026-01-12 12:31:32
2025-11-07 10:26:29 | Austin Webb | 100 | 109 | Gate Exit |  |  | N/A | 10000 |  | Uncommitted | 0 | 0 | No | Customer Experience | Building/Site | Facilities Site Work |  | Deferred |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: Follow up 10/21/25 - Reduce free vaccum customers pulling into the lot, We can move this to a lower priority if need be. It would be more a nice to have in conjuction with the ops team communicating - AW 02/24/2026 - Rusty Modesty: Committed Aug 06/29/2026 - Andrew Folse: A Webb said this was not needed | 2026-06-29 17:12:55
2025-03-31 08:55:41 | Abel Smith | 100 | 110 | Blower gators | 2018 | Q2 | September | 12500 |  | Committed | 0 | 0 |  | Planned maintenance | Equipment | Blowers | Wash Quality | Completed |  | EQ-0110-2025-1471 | 2025 | Low | No |  | 01/12/2026 - Rusty Modesty: Only needed 8 gators - reduced budget | 2026-01-12 12:31:32
2025-03-31 08:55:41 | Andrew Folse | 100 | 110 | Conveyor Deck Repair | 2018 | Q3 | April | 4500 | 7135.18 | Committed | 0 | 0 |  | Planned maintenance | Equipment | Conveyor Chain | Safety | Completed |  | EQ-0110-2026-1768 | 2025 | High | No |  | 01/12/2026 - rusty: Scope of work was inaccurate. Project will exceed budget 04/16/2026 - Andrew Folse: Weld new flat bar on top deck. Work done in house. 04/22/2026 - Rusty Modesty: Compiling invoices and quotes for complete capex pricing. 04/23/2026 - Andrew Folse: Completed on 4/22 | 2026-05-19 23:44:18
2025-03-31 08:55:41 | Abel Smith | 100 | 110 | Convert from Hydra-Flex pumps to Grundfos pumps | 2018 | Q3 | N/A | 17000 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Equipment | Hydroflex | Wash Quality | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-08-28 10:35:28 | David Carreon | 100 | 110 | LED sig controller | 2018 |  | N/A | 5700 |  | Uncommitted | 0 | 0 | No | Unplanned | Building/Site | marketing/signage | Customer Experience | Deferred | 2025-08-28 |  | 2025 | Low | No |  | 01/12/2026 - rusty: LED sign controller board has failed, needs replacement, Vendor will install 04/21/2026 - Jonathan Blair: LED sign controller board has failed, needs replacement, Vendor will install | 2026-04-21 13:14:13
2025-11-07 10:26:29 | Austin Webb | 100 | 110 | Pump Grundfos (2 20 gpm) |  |  |  | 15000 |  | Uncommitted | 0 | 0 | No | Prevent further damage | Equipment |  |  | Deferred |  |  | 2026 | High | Yes |  | 01/12/2026 - unknown: WX110 09/18/25 - Sent email to Terry at Sonnys asking for a quote.-PL 09/21/25 - Received the quote from Terry @ Sonys. It has been placed in the folder - PL 02/17/2026 - Philip Loper: 02/17 - Sent an email to the store asking for additional information. Asking for photos and voltages. 02/18/2026 - Philip Loper: 02/18 - Sent an email to Terry @ Sonnys and requested a proposal. 02/24/2026 - Rusty Modesty: Marked as Committed 03/02/2026 - Philip Loper: ProposaL RETURNED AND PLACED IN THE capex folder. The cost before freight is $15,406.09 | 2026-04-21 13:00:30
2025-11-07 10:26:29 | Austin Webb | 100 | 110 | Upgrade XPTs to XPT5+ from XPT 2012 |  |  |  | 40000 |  |  | 0 | 0 | No | Prevent further damage | IT | XPT |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: | 2026-01-12 12:02:24
2025-11-07 10:26:29 | Austin Webb | 100 | 110 | Sign LED |  |  | September | 12000 |  | Committed | 0 | 0 | No | Customer Experience | IT | Building Facilities |  | Ordered |  | SI-0110-2026-1979 | 2026 | Medium | No |  | 01/12/2026 - Austin Webb: https://app.getmaintainx.com/workorders/50310035 02/24/2026 - Rusty Modesty: Marked as Committed. Sept 09/10/2026 - Mason Faltysek: Signs in manufacturing expected to install last week of september | 2026-09-10 08:29:24
2025-11-07 10:26:29 | Austin Webb | 100 | 110 | Replace ceramic and carnauba light bars |  |  | N/A | 2500 |  | Uncommitted | 0 | 0 | No | Customer Experience | Equipment | Building Facilities |  | Deferred |  |  | 2026 | Medium | Yes |  | 01/12/2026 - unknown: 02/16/2026 - Jonathan Blair: Went from 3,000 to 2,500. 02/17/2026 - Philip Loper: This is not CAPEX about. Replacement lights are $1,750, including tax and freight. I have placed this in the 2026 Folder. | 2026-04-21 13:14:54
2025-11-07 10:26:29 | Austin Webb | 100 | 110 | Grand Entry Arch (full replacement) |  |  | October | 8600 |  | Committed | 0 | 0 | No | Customer Experience | Equipment | Building Facilities |  | Ordered |  | SI-0110-2026-2015 | 2026 | High | No |  | 01/12/2026 - unknown: WX110 09/18/25 - Austin changed this to only center cabinet and face. - PL 09/18/25 - Sent an email to Terry @Sonnys for a proposal. -PL 09/22/25- Terry sent back the proposal and I have placed it in the folder. -PL 10/07/25 - A Full replacemebnt will cost $8,600 plus freight. - PL 02/17/2026 - Philip Loper: 02/17 Proposal returned from Sonnys. Entry arch with tax is $6,598.52. This does not include freight of about $1,200.00. This proposal was placed in the CAPEX Folder. 02/25/2026 - Rusty Modesty: WX110 09/18/25 - Austin changed this to only center cabinet and face. - PL 09/18/25 - Sent an email to Terry @Sonnys for a proposal. -PL 09/22/25- Terry sent back the proposal and I have placed it in the folder. -PL 10/07/25 - A Full replacemebnt will cost $8,600 plus freight. - PL | 2026-08-27 21:48:04
2025-11-07 10:26:29 | Austin Webb | 100 | 111 | Equipment Wrap Rebuild Full Quad |  |  |  | 8000 |  | Uncommitted | 0 | 0 | No | Prevent further damage | Equipment |  |  | Deferred |  |  | 2026 | High | No |  | 01/12/2026 - unknown: 02/17/2026 - Philip Loper: 02/17 - Sent an email to Rusty and Joe and asked for addisional information. I am not familiar with this project. 02/24/2026 - Rusty Modesty: Marked as Committed. 02/26/2026 - Philip Loper: 02/26 - Sent another email to Rusty and Joe for information (Follow-up) 03/02/2026 - Philip Loper: 03/02 - Joe and Bo are not aware of this project. I emailed them a screenshot of this record. I told them I would pause on this until we are all on the same page. | 2026-04-21 13:00:56
2025-03-31 08:55:41 | Abel Smith | 100 | 112 | Hydra-Pulse | 2022 | Q1 | N/A | 3200 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Equipment | Conveyor Chain | Wash Quality | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - unknown: Material purchased on 2024 so no budget needed | 2026-01-12 12:31:32
2025-03-31 08:55:41 | Abel Smith | 100 | 112 | Tire Brush - Replace Ninja Brushes/Rebuild completely | 2022 | Q3 | N/A | 4500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Equipment | Tire Shine | Wash Quality | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-11-07 10:26:29 | Austin Webb | 100 | 114 | Exterior lights (2 building lights & 2 XPT Canopy lights) |  |  | N/A | 6000 |  | Uncommitted | 0 | 0 | No | Customer Experience | Building/Site | Facilities Site Work |  | Deferred |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: 10/20/25 - This is R&M based on scope of work description - GM 02/16/2026 - Jonathan Blair: 10/20/25 - This is R&M based on scope of work description - GM | 2026-04-21 13:15:26
2025-03-31 08:55:40 |  | 0 | 115 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 2025 | Medium | No |  |  | 2026-01-12 12:01:22
2025-11-07 10:26:29 | Austin Webb | 100 | 115 | Replace 2 tunnel accent lights |  |  |  | 3000 |  |  | 0 | 0 | No | Customer Experience | Equipment | Building Facilities |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: Discuss - WX115 10/14/25 - Need more detail - GM 10/21/25 - Power was checked & ballast replaced. 2 Accent lights are needing to be replaced- AW | 2026-01-12 12:02:24
2025-03-31 08:55:41 | Abel Smith | 100 | 116 | Vacuum -Second turbine | 2020 | Q3 | N/A | 5000 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Equipment | Vacuum | Customer Experience | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - rusty: Over budgeted - equipment being sourced from 120. Budget reduction from $25,000 to $5,000 | 2026-01-12 12:31:32
2025-03-31 08:55:41 | Abel Smith | 100 | 116 | Tire Brush - Macneil Sonic Brushes or Sonnys Python brushes | 2020 | Q4 | N/A | 18000 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Equipment | Wheel Brush | Wash Quality | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:41 | Abel Smith | 100 | 116 | Wrap 2 Cores DS/PS and cloth replacement | 2020 | Q3 | January | 5500 |  | Committed | 5213.82 | 286.18 |  | Planned maintenance | Equipment | Wrap Brush | Wash Quality | Completed |  | EQ-0116-2025-1140 | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:41 | Abel Smith | 100 | 116 | Tire Shine Replacement | 2020 | Q4 | N/A | 27300 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Equipment | Tire Shine | Wash Quality | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - unknown: Converting to R&M | 2026-01-12 12:31:32
2025-08-28 10:43:14 | David Carreon | 100 | 116 | LED Sign replacement | 2021 |  | N/A | 5900 |  | Uncommitted | 0 | 0 | No | Unplanned | Building/Site | marketing/signage | Customer Experience | Deferred | 2025-09-01 |  | 2025 | Low | No |  | 01/12/2026 - rusty: LED sign removal and installation of fixed design, permit needed, marketing approval of design and installation by 3rd part 04/21/2026 - Jonathan Blair: LED sign removal and installation of fixed design, permit needed, marketing approval of design and installation by 3rd part | 2026-04-21 13:16:59
2025-11-07 10:26:29 | Austin Webb | 100 | 116 | Market Air Compressor |  |  | May | 5700 |  | Committed | 0 | 0 | No | Prevent further damage | Equipment |  |  | Completed |  | EQ-0116-2026-1782 | 2026 | High | Yes |  | 01/12/2026 - unknown: Spare based on historic needs 02/16/2026 - Jonathan Blair: Assigned to 116 02/16/2026 - Jonathan Blair: Went from 7,000 to 5,700. 02/17/2026 - Philip Loper: Price for Compressor, Tax and Freight is $4,104.84 02/23/2026 - Philip Loper: 02/23 - Sent a follow-up email to Green Valley 02/23/2026 - Philip Loper: Sent email in Error to Green Valley. The proposal was sent and overlooked. 04/21/2026 - Andrew Folse: Asset used from Ella construction. Need to determine how asset is transferred with accounting 04/21/2026 - Andrew Folse: Asset used from Ella construction. Need to determine how asset is transferred with accounting 05/07/2026 - Rusty Modesty: Ordered from Green Valley | 2026-05-18 14:41:32
2025-11-07 10:26:29 | Austin Webb | 100 | 116 | Aqua Labs (or Rebuild of Misers) |  |  | August | 22000 | 13000 | Committed | 947.53 | 12052.47 | No | Wash Quality | Equipment |  |  | Completed |  | EQ-0116-2026-1917 | 2026 | High | No | Yes | 01/12/2026 - unknown: WX116- Currently falling apart being held together by vice grips 09/18/25 - Sent an email request to Sonnys asking for a proposal -PL 09/25/25 - Terry returned the proposal and I have placed it in a folder. -PL 9/29 Need proposal from Dubois also. -RM 10/01/25 - Sent an email to Brian Lonsdale and requested a correct proposal. - PL 10/03/25 - Sent a Follow up email to Brian Lonsdale. I will proceed with Sonnys price point without labor or additional parts. - PL 02/17/2026 - Philip Loper: 02/17 - Sent an email to Terry at Sonnys asking for a proposal. 02/17/2026 - Philip Loper: Proposal returend and placed in the CAPEX folder. Total with pumps is $30,886.02 07/23/2026 - Andrew Folse: Aqua lab panes were ordered on 7/22 | 2026-08-10 13:41:51
2025-11-07 10:26:29 | Austin Webb | 100 | 116 | Vac producer needs to be replaced, two cracks in it. |  |  | November | 18514 |  | Committed | 0 | 0 | No | Prevent further damage | Equipment | Vacuum |  | Deferred |  |  | 2026 | Medium | No |  | 01/12/2026 - unknown: 02/17/2026 - Philip Loper: 02/17 - Sent an email to the site to request additional information. 02/18/2026 - Philip Loper: 02/18 - Sent an email to Jody @ MCWW and requested a proposal. 02/19/2026 - Philip Loper: 02/19 - Jody @ MCWW returned the proposal. This has been placed in the capex folder. The cost for the producer is $17,966.43 02/24/2026 - Rusty Modesty: Marked as Committed. July | 2026-08-21 11:32:46
2025-11-07 10:26:29 | Austin Webb | 100 | 116 | Camera system (vast upgrade) |  |  | June | 8000 |  | Committed | 3332.58 | 4667.42 | No | Safety | IT | Camera |  | Completed | 2026-06-14 | EQ-0116-2026-1848 | 2026 | Medium | No |  | 01/12/2026 - unknown: 02/24/2026 - Rusty Modesty: Marked as Committed. May 06/15/2026 - David Carreon: Equipment ordered, will be at the office on 6/22 07/20/2026 - David Carreon: 2 Network switches 6u Rack Licenses | 2026-07-20 14:07:07
2025-11-07 10:26:29 | Austin Webb | 100 | 116 | Sign LED |  |  | September | 12000 |  | Committed | 0 | 0 | No | Customer Experience | IT | Building Facilities |  | Ordered |  | SI-0116-2026-1980 | 2026 | Low | No |  | 01/12/2026 - unknown: https://app.getmaintainx.com/workorders/54787759 02/24/2026 - Rusty Modesty: Marked as Committed. Sept 09/10/2026 - Mason Faltysek: Sign company is working on manufacturing. Expected to install last week of september | 2026-09-10 08:28:47
2025-11-07 10:26:29 | Austin Webb | 100 | 116 | replace tri foam light and blower area light |  |  |  | 2700 |  |  | 0 | 0 | No | Customer Experience | Equipment | Building Facilities |  | 2026 Request |  |  | 2026 | Medium | No |  | 01/12/2026 - unknown: 02/19/2026 - Philip Loper: 02/19 - This would not be copnsiodered two seperate projects. One of teh lights cost is only $1,100.00 per josh Murray | 2026-02-19 15:45:19
2025-03-31 08:55:41 | Abel Smith | 100 | 117 | Tire Seal hub,spindle rebuild | 2023 | Q1 | N/A | 2800 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Equipment | Tire Shine | Wash Quality | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - unknown: Not needed by AD | 2026-01-12 12:31:32
2025-03-31 08:55:41 | Abel Smith | 100 | 117 | Tire Shine | 2023 |  | January | 2510 |  | Committed | 0 | 0 |  | Planned maintenance | Equipment | Tire Shine | Wash Quality | Completed |  | EQ-0117-2024-1089 | 2025 | Low | No |  | 01/12/2026 - unknown: Duplicate of line 26 | 2026-01-12 12:31:32
2025-11-07 10:26:29 | Austin Webb | 100 | 117 | Office roof leak |  |  |  | 2500 |  |  | 0 | 0 | No | Prevent further damage | Building/Site | Facilities Site Work |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: 10/14/25 - Need more detail - GM - is leak over tunnel or office? WX117 10/17/25 - roof leak is in the office pictures are attached - AW 10/17/25 - quote is $2500 work order 34835 - AW 10/20/25 - Does not qualify for cpex based on scope of work - this will be R&M to be handled by regional team | 2026-01-12 12:02:24
2026-07-28 12:56:21 | Andrew Folse | 100 | 119 | 20gpm Grundfoss Pump |  |  | September | 9000 |  | Committed | 0 | 0 | No | Planned maintenance | Equipment | Hydroflex | Prevent further damage | Completed | 2026-09-01 | EQ-0119-2026-1933 |  | High | No | No |  | 2026-09-16 15:16:18
2025-03-31 08:55:41 | Abel Smith | 100 | 120 | Blower gators or AreoGates | 2019 | Q3 | N/A | 8500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Equipment | Blowers | Wash Quality | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - rusty: Only need 4 gates | 2026-01-12 12:31:32
2025-11-07 10:26:29 | Austin Webb | 100 | 120 | Power Packs Replacement and division of 9 flow unit to multiple PP/install hydrapulse |  |  | January | 28000 |  | Committed | 42596.67 | -14596.67 | No | Prevent further damage | Equipment | Hydraulic Power Pack | Prevent further damage | Completed | 2026-01-08 | EQ-0120-2026-1629 | 2026 | Low | No |  |  | 2026-02-20 12:51:10
2025-11-07 10:26:29 | Austin Webb | 100 | 120 | TCS1 Upgrade |  |  |  | 45000 |  |  | 0 | 0 | No | Prevent further damage | IT | Technology |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: | 2026-01-12 12:02:24
2025-11-07 10:26:29 | Austin Webb | 100 | 120 | Site needs two new air compressors, only running on one as of now |  |  | May | 11000 |  | Committed | 9793.2 | 1206.8 | No | Prevent further damage | Equipment |  |  | Completed |  | EQ-0120-2026-1786 | 2026 | High | Yes |  | 01/12/2026 - unknown: 02/17/2026 - Philip Loper: 02/17 - Sent an email to the store asking for additional information. Looking for voltage. 02/23/2026 - Philip Loper: 02/17 - Joe Shankling sent a email stating he would obtain the voltage this evening. 02/23 - Sent a follow up email to Joe, Rusty, and Austin 02/24/2026 - Rusty Modesty: Marked as Committed. May 02/26/2026 - Philip Loper: 02/17 - Sent an email to Joe and the team to ask for the correct voltage at the site. 02/23 - Sent a follow-up email on the voltage. I was informed by Joe they will need to take a meter to the compressor to find out. 02/26 - Austin sent a photo of the compressors, and Joe informed us that we can't use those. We will have to wait for his team to take a voltage measurement. 03/03/2026 - Philip Loper: 03/03 - Green Valley returned the proposal, and it has been placed in the CAPEX folder. Cost for (2) compressors, tax, and freight is $8,362.31 05/07/2026 - Rusty Modesty: Ordered from Green Valley | 2026-05-18 14:43:39
2025-11-07 10:26:29 | Austin Webb | 100 | 123 | 15 tunnel lights out or partially out |  |  | April | 12500 |  | Committed | 5864.34 | 6635.66 | No | Customer Experience | Building/Site | Building Facilities |  | Completed |  | FA-0123-2026-1705 | 2026 | High | Yes |  | 01/12/2026 - unknown: 10/14/25 - Need more detail - how long have they been out? Has anyone been out to diagnose? - GM 10/17/25 - 15 lights are completely out or partially ticket says been out since April, Joe he reached out to Intertek photos attached and requested a quote - AW 02/16/2026 - Jonathan Blair: 10/14/25 - Need more detail - how long have they been out? Has anyone been out to diagnose? - GM 10/17/25 - 15 lights are completely out or partially ticket says been out since April, Joe he reached out to Intertek photos attached and requested a quote - AW 03/04/2026 - Mason Faltysek: Electrician will be onsite to find the issue 3/5 03/12/2026 - Mason Faltysek: 18 Lights have been ordered and paid for by accounting 1 week lead time once payment is processed 03/23/2026 - Mason Faltysek: Lights are shipping out week of 3/23 | 2026-04-23 14:11:47
2025-03-31 08:55:41 | Mason Faltysek | 100 | 125 | Relocate electrical transformer from roof and repair roof | 2015 | Q1 | Feb | 30000 |  | Committed | 25502 | 4498 |  | Planned maintenance | Building/Site | Building Facilities | Safety | Completed |  | FA-0125-2025-1206 | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:41 | Mason Faltysek | 100 | 125 | Water damage remediation | 2015 | Q1 | Feb | 27000 |  | Committed | 0 | 0 |  | Planned maintenance | Building/Site | Building Facilities | Prevent further damage | Completed |  | FA-0125-2025-1207 | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:41 | Rusty Modesty | 100 | 125 | Water Softener | 2015 | Q2 | May | 12000 |  | Committed | 14557.38 | -2557.38 |  | Planned maintenance | Equipment | Water Softener | Wash Quality | Completed |  | EQ-0125-2025-1298 | 2025 | Low | No |  | 01/12/2026 - fruia_1: Equipment is on the ground. Rainbow was given info on install quote 7/15. We expect the install quote 7/16 Rainbow Scheduled for week of 9/15 | 2026-01-12 12:31:32
2025-03-31 08:55:41 | Abel Smith | 100 | 125 | Grandfos - 2 20 GPM Grundfos Pumps - 460V | 2015 | Q2 | N/A | 13000 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Equipment | Hydroflex | Wash Quality | Deferred |  |  | 2025 | Low | No |  | 04/21/2026 - Jonathan Blair: Duplicate per Andrew/ Rusty | 2026-04-21 13:17:46
2025-03-31 08:55:41 | Abel Smith | 100 | 125 | Wrap Rebuilds (Multiple) | 2015 | Q3 | N/A | 3250 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Equipment | Wrap Brush | Wash Quality | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - rusty: Gearbox and motor only | 2026-01-12 12:31:32
2025-08-28 10:33:12 | David Carreon | 100 | 125 |  | 2018 |  | N/A | 5500 |  | Uncommitted | 0 | 0 | No | Planned maintenance | Building/Site | marketing/signage | Customer Experience | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - rusty: We have replaced LED panels, 2 conrollers and a wireless bridge for this sign since acquisition, but the controller has failed a 04/21/2026 - Jonathan Blair: We have replaced LED panels, 2 conrollers and a wireless bridge for this sign since acquisition, but the controller has failed a | 2026-04-21 13:19:47
2025-11-07 10:26:29 | Austin Webb | 100 | 125 | Repaint the vacuum stands and booms |  |  | N/A | 15000 |  | Uncommitted | 0 | 0 | No | Customer Experience | Building/Site |  |  | Deferred |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: 02/24/2026 - Rusty Modesty: Marked as Committed. July 06/01/2026 - Rusty Modesty: Marked as deferred based on 6/1 capex sw call. | 2026-06-01 16:31:36
2025-11-07 10:26:29 | Austin Webb | 100 | 125 | Sign Digital |  |  | N/A | 80000 |  | Committed | 0 | 0 | Yes | Planned maintenance | Equipment | Building Facilities | Safety | Completed |  |  | 2026 | Medium | No |  | 05/18/2026 - David Carreon: Camera system to be upgraded in Q3 05/20/2026 - Henry Shine: Use for 2025 tracking | 2026-05-20 10:51:48
2025-11-07 10:26:29 | Austin Webb | 100 | 125 | vac turbine |  |  | November | 18514 |  | Uncommitted | 0 | 0 | No | Customer Experience | Equipment | Vacuum |  | Deferred |  |  | 2026 | Medium | No |  | 01/12/2026 - unknown: 02/17/2026 - Philip Loper: 02/17 - Sent an email to Jody at MCWW and requested a proposal. 02/18/2026 - Philip Loper: 02/18 - Vac proposal returned and placed in teh CAPEX folder. Price is $16,856.78 02/24/2026 - Rusty Modesty: Marked as Committed. 05/18/2026 - Andrew Folse: Pushed to November deployment | 2026-08-21 11:36:26
2025-11-07 10:26:29 | Austin Webb | 100 | 125 | Grundfos pump |  |  | April | 13000 |  | Committed | 16225.19 | -3225.19 | No | Wash Quality | Equipment |  |  | Completed |  | EQ-0125-2026-1663 | 2026 | High | Yes |  | 02/05/2026 - Philip Loper: Capex ex PO request has been submitted. 02/05/2026 - Philip Loper: Original Budget was 13,000. New budget is $16,259.76 04/21/2026 - Andrew Folse: Will be completed on 4/27 | 2026-09-15 15:58:56
2025-03-31 08:55:41 | Rusty Modesty | 100 | 126 | Water Softner - Water Softener upgrade | 2019 | Q2 | N/A | 12000 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Equipment | Water Softener | Wash Quality | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - rusty: Sonnys slow to act. Gaining quote from Sobrite, also gaining install quote from Short co. (RM Removed from Committed based on le | 2026-01-12 12:31:32
2025-03-31 08:55:41 | Rusty Modesty | 100 | 126 | Tunnel roll up doors | 2019 | Q2 | N/A | 14000 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Building Facilities | Safety | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - rusty: Brandy received estimate rusty approved Denied by BO Quinn | 2026-01-12 12:31:32
2025-03-31 08:55:41 | Abel Smith | 100 | 126 | Lighting - Upgrade tunnel led lights, ceramic, triple foam and blower lights in the tunnel. | 2019 | Q2 | February | 7819.79 |  | Committed | 13484.79 | -5665 |  | Planned maintenance | Equipment | Building Facilities | Safety | Completed | 2024-10-29 | FA-0126-2024-1035 | 2025 | Low | No |  | 01/12/2026 - unknown: Tunnel lights are being replaced in Q4 2024 (and rusted conduit) | 2026-01-12 12:31:32
2025-08-19 14:08:01 | Abel Smith | 100 | 126 | Chain Rollers X458-Log Chain Conversion |  | Q4 | October | 15000 |  | Committed | 8950.94 | 6049.06 | No | Planned maintenance | Equipment | chain/roller | Customer Experience | Completed |  | EQ-0126-2025-1489 | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-11-07 10:26:29 | Austin Webb | 100 | 126 | Water softener |  |  | October | 12500 |  | Committed | 0 | 0 | No | Wash Quality | Equipment |  |  | In-Process |  | EQ-0126-2026-2026 | 2026 | Low | No |  | 01/12/2026 - unknown: 10/08/25 - This price includes water softener, Tax, and frieght. Install was an estimate and added to this price. - PL 02/24/2026 - Rusty Modesty: Marked as Committed October 09/14/2026 - Andrew Folse: Bringing a water softener from LA | 2026-09-15 16:09:37
2025-11-07 10:26:29 | Austin Webb | 100 | 126 | IR Air compressor needs a motor and Head |  |  | May | 5500 |  | Committed | 0 | 0 | No | Wash Quality | Equipment |  |  | Completed |  | EQ-0126-2026-1785 | 2026 | High | No |  | 01/12/2026 - unknown: 02/17/2026 - Philip Loper: 02/17 - Sent an email to the store requesting additional information. 04/07/2026 - Philip Loper: Sent an email to Joe Shanklin asking voltage 04/21/2026 - Andrew Folse: Asset transferred from Ella. Will get with accounting on how to transfer | 2026-05-18 14:24:00
2025-03-31 08:55:41 | Abel Smith | 200 | 201 | Vac producer collecting water (broken undergorund lateral) | 2015 | Q1 | Feb | 25000 |  | Committed | 0 | 0 |  | Planned maintenance | Equipment | Vacuum | Customer Experience | Completed |  |  | 2025 | Low | No |  | 01/12/2026 - rusty: Duplicate line 48/50 EQ-0201-2025-1417 04/21/2026 - Jonathan Blair: Duplicate line 48/50 EQ-0201-2025-1417 | 2026-04-21 12:49:55
2025-03-31 08:55:41 | Abel Smith | 200 | 201 | Tire shine brush replacement | 2014 | Q1 | N/A | 23000 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Equipment | Tire Shine | Wash Quality | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - unknown: Repaired | 2026-01-12 12:31:32
2025-03-31 08:55:41 | Abel Smith | 200 | 201 | Tunnel Poly Replacement | 2014 | Q1 | N/A | 13500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Equipment | Building Facilities | Wash Quality | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:41 | Phil Loper | 200 | 201 | Vacuum Producers | 2014 | Q1 | March | 32000 |  | Committed | 34487.28 | -2487.28 |  | Planned maintenance | Equipment | Vacuum | Customer Experience | Completed |  | EQ-0201-2025-1194 | 2025 | Low | No |  | 01/12/2026 - unknown: WX201 - 2x 40hp vac producers.pdf | 2026-01-12 12:31:32
2025-03-31 08:55:41 | Mason Faltysek | 200 | 201 | Building improvements - Office Refresh (Paint, Drywall Repair, Trim, VCT. | 2014 | Q2 | April | 7500 |  | Committed | 0 | 0 |  | Planned maintenance | Building/Site | Building Facilities | Prevent further damage | Completed |  | FA-0201-2025-1315 | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:41 | David Carreon | 200 | 201 | Camera System Upgrade/Replacement | 2014 | Q1 | March | 9000 |  | Committed | 8878.71 | 121.29 |  | Planned maintenance | IT | Camera | Safety | Completed |  | EQ-0201-2025-1293 | 2025 | Low | No |  | 01/12/2026 - rusty: PROJECT COMPLETED Single PO for 201, 202, 212 ,215 camera upgrade from acquire. changed from $3k to $9k JMCC | 2026-01-12 12:31:32
2025-03-31 08:55:41 | Abel Smith | 200 | 201 | New power pack | 2014 | Q2 | N/A | 8000 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Equipment | Hydraulic Power Pack | Wash Quality | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - unknown: New Prince Valve changed. Will monitor over the next few weeks. May drop project. R&M on unit, No replacement needed. | 2026-01-12 12:31:32
2025-03-31 08:55:41 | David Carreon | 200 | 201 | XPT Replacement/upgrade | 2014 | Q2 | June | 6000 |  | Committed | 8878.71 | -2878.71 |  | Planned maintenance | IT | XPT | Customer Experience | Completed |  | EQ-0201-2025-1293 | 2025 | Low | No |  | 01/12/2026 - rusty: Take XPT from 223 install at 201 lane 2, Install SAL at 223 into lane 1. Changed est cost from $40k to $6k - JMCC | 2026-01-12 12:31:32
2025-03-31 08:55:41 | Mason Faltysek | 200 | 201 | Faded Exterior sign replacement | 2014 | Q2 | March | 4500 |  | Committed | 0 | 0 |  | Planned maintenance | Building/Site | marketing/signage | Customer Experience | Completed |  |  | 2025 | Low | No |  | 01/12/2026 - gregg: Lead time may be high. Could be a Q2 order with Q3 install | 2026-01-12 12:31:32
2025-07-11 11:27:03 | David Carreon | 200 | 201 | XPT Replacement/upgrade | 2014 |  | July | 6000 |  | Committed | 3736.56 | 2263.44 | No | Planned maintenance | IT | Technology | Customer Experience | Completed | 2025-07-01 | EQ-0201-2025-1399 | 2025 | Medium | No |  | 01/12/2026 - rusty: SAL's received | 2026-01-12 12:01:22
2025-11-07 10:26:29 | Ryan Payne | 200 | 201 | TCS1 Upgrade |  |  |  | 45000 |  |  | 0 | 0 | No | Prevent further damage | IT | Technology |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: | 2026-01-12 12:02:24
2025-11-07 10:26:29 | Ryan Payne | 200 | 201 | Grand Entry |  |  | October | 8000 |  | Committed | 0 | 0 | No | Prevent further damage | Equipment | Building Facilities |  | Ordered |  | SI-0201-2026-2004 | 2026 | Low | Yes |  | 01/12/2026 - unknown: 10/01/25 - This value is for the Arch and tax. Freight and any additional labor or parts are not included. - PL 02/17/2026 - Philip Loper: 02/17 - Sent an email to Terry @ Sonnys requesting a proposal. 02/23/2026 - Philip Loper: 02/23 - Received proposal from Terry and placed in the CAPEX folder. The Cost with tax (No freight) is $6,598.52 02/24/2026 - Rusty Modesty: Marked as committed October 08/26/2026 - Andrew Folse: Order placed 8/25 | 2026-08-26 12:45:43
2025-11-07 10:26:29 | Ryan Payne | 200 | 201 | Door Equipment room and frame |  |  | September | 5000 | 5410 | Committed | 0 | 0 | No | Safety | Building/Site | Facilities Site Work |  | Completed |  | FA-0201-2026-1891 | 2026 | Medium | No |  | 01/12/2026 - mason: Bid received from renascent pricing updated to reflect bid 11/26 MF 02/24/2026 - Rusty Modesty: Marked Committed and July 06/12/2026 - Andrew Folse: Quote for new rollup door 5400. Plan to action on July 1st 07/20/2026 - Andrew Folse: Quote was approved on 7/13. Waiting on vendor to install | 2026-09-16 15:08:14
2025-03-31 08:55:41 | Abel Smith | 200 | 202 | Vacuum- Replace underground vac line | 2015 | Q1 | Jan | 15000 |  | Committed | 14079.22 | 920.78 |  | Planned maintenance | Equipment | Facilities Site Work | Customer Experience | Completed | 2025-01-29 | EQ-0202-2025-1167 | 2025 | Low | No |  | 01/12/2026 - unknown: Duplicate line 48/50 | 2026-01-12 12:31:32
2025-03-31 08:55:42 | David Carreon | 200 | 202 | Camera System Upgrade/Replacement | 2015 | Q1 | N/A | 3000 |  | Uncommitted | 0 | 0 |  | Planned maintenance | IT | Camera | Safety | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - unknown: Deferred Combined with 201 PO JMCC | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Abel Smith | 200 | 202 | Tire Shine Machine | 2015 | Q2 | N/A | 20000 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Equipment | Tire Shine | Wash Quality | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - unknown: Repaired | 2026-01-12 12:31:32
2025-03-31 08:55:42 | David Carreon | 200 | 202 | XPT Replacement/upgrade and SAL | 2015 | Q2 | April | 8000 |  | Committed | 8943.16 | -943.16 |  | Planned maintenance | IT | XPT | Customer Experience | Completed |  | EQ-0202-2025-1279 | 2025 | Low | No |  | 01/12/2026 - rusty: Move XPT from 221. order SAL for XPT at 221 and Sal for 202 lane 1. Use fab SALs. SAL's received on site, pending installation | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Mason Faltysek | 200 | 202 | Concrete - Entry Concrete sinking - mud jacking | 2015 | Q3 | N/A | 7500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Building Facilities | Prevent further damage | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Mason Faltysek | 200 | 202 | Vac station repaint | 2015 | Q3 | N/A | 4500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Facilities Site Work | Prevent further damage | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-11-07 10:26:29 | Ryan Payne | 200 | 202 | TCS1 Upgrade |  |  |  | 45000 |  |  | 0 | 0 | No | Prevent further damage | IT | Technology |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: | 2026-01-12 12:02:24
2026-06-03 12:06:23 | Andrew Folse | 200 | 202 | Conveyor |  |  | November | 90000 |  | Committed | 0 | 0 | No | Planned maintenance | Equipment | Conveyor Chain | Prevent further damage | Proposal Solicitation |  |  |  | High | No | No |  | 2026-08-21 07:58:48
2025-03-31 08:55:42 | Rusty Modesty | 200 | 203 | Landscape Refresh | 2017 | Q2 | N/A | 8500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Facilities Site Work | Prevent further damage | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Abel Smith | 200 | 203 | Blowers - Addition of 3 blowers | 2017 | Q3 | N/A | 35000 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Equipment | Blowers | Wash Quality | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - unknown: 2024 Project | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Mason Faltysek | 200 | 203 | Parking lot restripe | 2017 | Q3 | N/A | 6500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Facilities Site Work | Customer Experience | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-11-07 10:26:29 | Ryan Payne | 200 | 203 | Market Spare 40 Vac Producer |  |  | February | 17000 |  | Committed | 36026.35 | -19026.35 | No | Prevent further damage | Equipment | Vacuum | Customer Experience | Completed |  | EQ-0203-2026-1644 | 2026 | High | Yes |  | 01/12/2026 - Rusty Modesty: Spare based on historic needs - RM Converted project to 203 based on need with Jan Deployment 02/25/2026 - Rusty Modesty: Spare based on historic needs - RM Converted project to 203 based on need with Jan Deployment | 2026-02-25 12:32:48
2025-11-07 10:26:29 | Ryan Payne | 200 | 203 | Sinking Concrete |  |  |  | 8500 |  |  | 0 | 0 | No | Customer Experience | Building/Site | Facilities Site Work |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - mason: Bid received from renascent pricing updated to reflect bid 11/26 MF | 2026-01-12 12:02:24
2025-11-07 10:26:29 | Ryan Payne | 200 | 203 | TCS1 Upgrade |  |  |  | 45000 |  |  | 0 | 0 | No | Prevent further damage | IT | Technology |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: | 2026-01-12 12:02:24
2025-11-07 10:26:29 | Ryan Payne | 200 | 203 | Upgrade XPT to XPT5+ from XPT 2012 |  |  |  | 40000 |  |  | 0 | 0 | No | Prevent further damage | IT | XPT |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: | 2026-01-12 12:02:24
2025-11-07 10:26:29 | Ryan Payne | 200 | 203 | Lanscaping Major Refresh |  |  | June | 15000 |  | Committed | 0 | 0 | No | Customer Experience | Building/Site | Facilities Site Work |  | Completed |  | FA-0203-2026-1827 | 2026 | Low | No |  | 01/12/2026 - Mason Faltysek: 10/2/25 This estimate is pulled using data from new Landscaping costs 02/24/2026 - Rusty Modesty: Marked as Committed. 03/12/2026 - Mason Faltysek: Sent out to bid 04/17/2026 - Mason Faltysek: bids sent to Jonathan waiting on ryan to confirm what will be in house so we are under budget. 05/12/2026 - Mason Faltysek: Meeting landscaper 5/12 to discuss in dallas 05/18/2026 - Mason Faltysek: Waiting on revised estimates from yellow stone after our site walk on 5/12 06/03/2026 - Mason Faltysek: Approved and released to the vendor 06/08/2026 - Donald Murry: Work scheduled to be completed by end of month. | 2026-07-01 12:55:57
2025-11-07 10:26:29 | Ryan Payne | 200 | 203 | Lighting LED lights on street side vacuums (dark during winter) |  |  | October | 10500 |  | Committed | 0 | 0 | No | Customer Experience | Equipment | Building Facilities |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - Mason Faltysek: 10/02/25 - Estimate Pulled from similar work this year in DFW- MF https://drive.google.com/drive/folders/1f33DBIJGYV8GRj20quyJpPAZBcTR12bv?usp=drive_link https://mail.google.com/mail/u/0?ui=2&ik=c225bf958e&attid=0.1&permmsgid=msg-f:1845464831398958489&th=199c687c8902d599&view=att&disp=safe&realattid=f_mgiq368y2&zw https://mail.google.com/mail/u/0?ui=2&ik=c225bf958e&attid=0.2&permmsgid=msg-f:1845464831398958489&th=199c687c8902d599&view=att&disp=safe&realattid=f_mgiq392z3&zw https://mail.google.com/mail/u/0?ui=2&ik=c225bf958e&attid=0.3&permmsgid=msg-f:1845464831398958489&th=199c687c8902d599&view=att&disp=safe&realattid=f_mgiq3cny4&zw 07/27/2026 - Andrew Folse: 10/02/25 - Estimate Pulled from similar work this year in DFW- MF https://drive.google.com/drive/folders/1f33DBIJGYV8GRj20quyJpPAZBcTR12bv?usp=drive_link https://mail.google.com/mail/u/0?ui=2&ik=c225bf958e&attid=0.1&permmsgid=msg-f:1845464831398958489&th=199c687c8902d599&view=att&disp=safe&realattid=f_mgiq368y2&zw htt | 2026-07-27 16:22:01
2025-11-07 10:26:29 | Ryan Payne | 200 | 203 | Blowers. Install (2) to match standard |  |  | November | 25000 |  | Committed | 0 | 0 | No | Wash Quality | Equipment |  |  | 2026 Request |  |  | 2026 | Low | Yes |  | 01/12/2026 - Mason Faltysek: 10/01/25 - Sent an email to Terry @ Sonnys and requested a proposal for 2 blowers and 1 arch - PL 02/17/2026 - Philip Loper: 02/17 - Sent an email to Terry at sonnys asking for a proposal. 02/23/2026 - Philip Loper: 02/23 - Terry returned the proposal and it has been placed in the capex folder. The proce for 2 blowers and an arch (powder coated) with tax is $15,855.88 (No Freight) | 2026-02-25 13:09:50
2025-03-31 08:55:42 | Rusty Modesty | 200 | 204 | Lanscape refresh | 2020 | Q2 | N/A | 11500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Facilities Site Work | Prevent further damage | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Mason Faltysek | 200 | 204 | Parking lot restripe | 2020 | Q3 | N/A | 6500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Facilities Site Work | Customer Experience | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Abel Smith | 200 | 204 | Replace poodle brush 1 with python brush | 2020 | Q3 | N/A | 15000 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Wrap Brush | Wash Quality | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Mason Faltysek | 200 | 204 | XPT 2 gate box bollard | 2020 | Q3 | N/A | 2500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | XPT Gate | Prevent further damage | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-11-07 10:26:29 | Ryan Payne | 200 | 204 | 204-CAPEX Chain/Roller Refit |  |  | January | 13606 |  | Committed | 10584.93 | 3021.07 | No | Prevent further damage | Equipment | chain/roller | Customer Experience | Completed | 2026-01-08 | EQ-0204-2026-1627 | 2026 | High | Yes |  |  | 2026-02-23 17:34:07
2025-11-07 10:26:29 | Ryan Payne | 200 | 204 | XPT 1 and 2 gate box bollards |  |  | N/A | 5000 |  | Uncommitted | 0 | 0 | No | Customer Experience | Building/Site | XPT |  | Deferred |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: 02/23/2026 - Rusty Modesty: Adjusted to Building/Site vs IT 02/24/2026 - Rusty Modesty: Marked as Committed. July | 2026-06-01 16:58:14
2025-11-07 10:26:29 | Ryan Payne | 200 | 204 | Landscaping: mulch beds, new plants in drive flower beds, trim trees |  |  | June | 15000 |  | Committed | 0 | 0 | No | Customer Experience | Building/Site | Facilities Site Work |  | Completed |  |  | 2026 | Low | No |  | 01/12/2026 - Mason Faltysek: 10/01/25 Estimat pulled from similar work in DFW - MF https://mail.google.com/mail/u/0?ui=2&ik=c225bf958e&attid=0.1&permmsgid=msg-f:1845467787517264632&th=199c6b2ccf6482f8&view=att&disp=inline&realattid=f_mgirquse0&zw 02/24/2026 - Rusty Modesty: Marked as Committed. April 03/12/2026 - Mason Faltysek: Sent out to bid 04/17/2026 - Mason Faltysek: bids sent to Jonathan waiting on ryan to confirm what will be in house so we are under budget. 05/12/2026 - Mason Faltysek: Meeting landscaper 5/12 to discuss in dallas 05/18/2026 - Mason Faltysek: Waiting on revised estimates from yellow stone after our site walk on 5/12 06/03/2026 - Mason Faltysek: Approved and released to the vendor 06/08/2026 - Donald Murry: Work scheduled to be completed by end of month. | 2026-07-01 12:56:09
2025-11-07 10:26:29 | Ryan Payne | 200 | 204 | Replace grand arch. It is damaged. |  |  | October | 8000 |  | Committed | 0 | 0 | No | Customer Experience | Equipment | Building Facilities |  | Ordered |  | SI-0204-2026-2005 | 2026 | Low | Yes |  | 01/12/2026 - unknown: 10/01/25 - This value is for the Arch and tax. Freight and any additional labor or parts are not included. - PL 02/17/2026 - Philip Loper: 02/17 - Sent an email to Terry requesting a proposal. 02/24/2026 - Rusty Modesty: Marked as committed. October 03/04/2026 - Philip Loper: Correction to the record. The offical proposal request was sent on 03/04 03/06/2026 - Philip Loper: 03/05 - Terry Returned the proposal and it has been placed in the CAPEX folder. Cost without freight is $6,598.54 08/26/2026 - Andrew Folse: Order placed 8/25 | 2026-08-26 12:45:28
2025-11-07 10:26:29 | Ryan Payne | 200 | 204 | Canopy cloth on canopy structure |  |  | April | 13000 |  | Committed | 12773.5 | 226.5 | No | Customer Experience | Building/Site | Facilities Site Work |  | Completed | 2026-03-10 | EQ-0204-2026-1704 | 2026 | Medium | Yes |  | 01/12/2026 - Mason Faltysek: 10/01/25 - I sent an email to Jako @ Gulf Shades and asked for a proposal. - PL 10/09/25 - Gulf Shades returned a quote of $1,000 per stall as a rule of thumb. - PL 10/17/25 - Gulf Shades retured the quote for 412,773.50 Gulf Shades Quote.pdf https://mail.google.com/mail/u/0?ui=2&ik=c225bf958e&attid=0.1&permmsgid=msg-f:1845467269057840261&th=199c6ab418cd8485&view=att&disp=safe&realattid=f_mgirhtm40&zw https://mail.google.com/mail/u/0?ui=2&ik=c225bf958e&attid=0.2&permmsgid=msg-f:1845467269057840261&th=199c6ab418cd8485&view=att&disp=safe&realattid=f_mgiri3tq1&zw https://mail.google.com/mail/u/0?ui=2&ik=c225bf958e&attid=0.3&permmsgid=msg-f:1845467269057840261&th=199c6ab418cd8485&view=att&disp=safe&realattid=f_mgiri6c02&zw 02/16/2026 - Jonathan Blair: 10/01/25 - I sent an email to Jako @ Gulf Shades and asked for a proposal. - PL 10/09/25 - Gulf Shades returned a quote of $1,000 per stall as a rule of thumb. - PL 10/17/25 - Gulf Shades retured the quote for 412,773.50 Gulf Shades | 2026-03-31 16:16:03
2025-03-31 08:55:42 | Rusty Modesty | 200 | 205 | Replace Tunnel Heaters | 2020 | Q1 | Jan | 23500 |  | Committed | 13709.8 | 9790.2 |  | Planned maintenance | Building/Site | Building Facilities | Safety | Completed |  | EQ-0205-2025-1223 | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Abel Smith | 200 | 205 | Plumbing rebuilding for Hydraflex - Restructure of Hydraflex | 2020 | Q2 | N/A | 2500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Equipment | Hydroflex | Wash Quality | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - unknown: R&M | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Rusty Modesty | 200 | 205 | Water Softener | 2020 | Q1 | N/A | 14000 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Equipment | Water Softener | Wash Quality | Deferred |  |  | 2025 | Low | No |  |  | 2026-04-21 12:50:34
2025-03-31 08:55:42 | Phil Loper | 200 | 205 | Conveyor replacement | 2020 | Q2 | May | 85000 |  | Committed | 100668.58 | -15668.58 |  | Planned maintenance | Equipment | Conveyor Chain | Wash Quality | Completed |  | EQ-0205-2025-1297 | 2025 | Low | No |  | 01/12/2026 - unknown: Actual updated budget $105,000 | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Rusty Modesty | 200 | 205 | Landscaping | 2020 | Q2 | N/A | 8000 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Facilities Site Work | Prevent further damage | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Abel Smith | 200 | 205 | Vacuum - Double Drop Vacuum Hoses | 2020 | Q2 | July | 11200 |  | Committed | 10437.41 | 762.59 |  | Planned maintenance | Equipment | Vacuum | Customer Experience | Completed |  | EQ-0205-2025-1374 | 2025 | Low | No |  | 01/12/2026 - rusty: AS 5/31/25- in process of gathering quotes for this project. | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Mason Faltysek | 200 | 205 | Lighting - Extra Lighting on Backside of Property | 2020 | Q2 | N/A | 18500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Facilities Site Work | Safety | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Mason Faltysek | 200 | 205 | Parking lot restripe | 2020 | Q3 | N/A | 6500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Facilities Site Work | Customer Experience | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | David Carreon | 200 | 205 | Upgrade of TCS (years of abuse) | 2020 | Q2 | N/A | 0 |  | Uncommitted | 0 | 0 |  | Planned maintenance | IT | Technology | Wash Quality | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - unknown: Became R&M Project. Not at capex Threshold. | 2026-01-12 12:31:32
2025-03-31 08:55:42 | David Carreon | 200 | 205 | XPT Replacement/upgrade 2 units | 2020 | Q3 | N/A | 8000 |  | Uncommitted | 0 | 0 |  | Planned maintenance | IT | XPT | Customer Experience | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - unknown: R&M | 2026-01-12 12:31:32
2025-11-07 10:26:29 | Ryan Payne | 200 | 205 | Water Softener--wash issues |  |  | N/A | 18500 |  | Uncommitted | 0 | 0 | No | Wash Quality | Equipment |  |  | Deferred |  |  | 2026 | High | Yes |  | 01/12/2026 - Mason Faltysek: Carry over 02/17/2026 - Philip Loper: 02/17 - Sent an email to Brian Lonsdale and requested a proposal for a new soft water system. 02/23/2026 - Philip Loper: 02/23 - Sent a follow-up email to Brian asking for a status. 02/25/2026 - Philip Loper: 02/25 - Received proposal and have placed it in the capex folder. The cost without tax is $9,129.60 | 2026-04-21 13:01:58
2025-11-07 10:26:29 | Ryan Payne | 200 | 205 | Gutter Downpout to prevent lanscaping washout |  |  |  | 3000 |  |  | 0 | 0 | No | Prevent further damage | Building/Site | Facilities Site Work |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: | 2026-01-12 12:02:24
2025-11-07 10:26:29 | Ryan Payne | 200 | 205 | Dry Mat Machine for Lower Lot |  |  | October | 6500 |  | Committed | 5730.21 | 769.79 | No | Customer Experience | Building/Site | Facilities Site Work |  | Ordered |  | EQ-0205-2026-1996 | 2026 | Low | Yes |  | 01/12/2026 - Rusty Modesty: WX205 09/18/25 - Sent an email to JKO asking for a proposal. -PL 09/18/25 - Received the proposal and have placed it in the folder. -PL 09/30/25 - Need to source a handyman for teh concrete and electrical. - PL 02/17/2026 - Philip Loper: "02/16 - Sent an email to JKO for a proposal 02/16 - Proposal has been placed in the 2026 CAPEX folder for the store. " | 2026-08-26 12:46:08
2025-11-07 10:26:29 | Ryan Payne | 200 | 205 | Equipment Adding VPD to Site and license |  |  | N/A | 2000 |  | Uncommitted | 0 | 0 | No | Wash Quality | IT | Technology |  | Deferred |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: 02/23/2026 - Rusty Modesty: Updated Cost to reflect recent proposals. Moved to uncommitted/Deferred. | 2026-02-23 16:48:21
2025-11-07 10:26:29 | Ryan Payne | 200 | 205 | 2 Lanes - Upgrade 1 XPTs to XPT5+ from XPT 2012 - Replace 1 XPT with SAL use XPT for parts |  |  | June | 46000 | 18000 | Committed | 9865.84 | 8134.16 | No | Prevent further damage | IT | XPT | Customer Experience | Completed | 2026-05-18 | EQ-0205-2026-1808 | 2026 | High | No |  | 01/12/2026 - unknown: 02/23/2026 - Rusty Modesty: Adjusted Deployment to June. 06/14/2026 - David Carreon: 217 Scheduled for 6/16 and 205 is scheduled for 6/25 06/17/2026 - David Carreon: 217 Done, 205 scheduled for 6/25 | 2026-07-09 23:40:49
2025-11-07 10:26:29 | Ryan Payne | 200 | 205 | TCS1 Upgrade |  |  |  | 45000 |  |  | 0 | 0 | No | Prevent further damage | IT | Technology |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: | 2026-01-12 12:02:24
2025-11-07 10:26:29 | Ryan Payne | 200 | 205 | Lanscaping, Multch over crushed granite(Spillout) |  |  |  | 10000 |  |  | 0 | 0 | No | Customer Experience | Building/Site | Facilities Site Work |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: | 2026-01-12 12:02:24
2025-11-07 10:26:29 | Ryan Payne | 200 | 205 | Light pole Leaning |  |  |  | 10000 |  | Uncommitted | 0 | 0 | No | Prevent further damage | Equipment | Building Facilities |  | Deferred |  |  | 2026 | High | No |  |  | 2026-04-21 13:20:45
2025-11-07 10:26:29 | Ryan Payne | 200 | 205 | Stucco Repair |  |  | April | 20000 | 12000 | Committed | 0 | 0 | No | Prevent further damage | Building/Site | Facilities Site Work |  | Completed |  | FA-0205-2026-1759 | 2026 | Medium | No |  | 01/12/2026 - Henry Shine: Bid received from renascent pricing updated to reflect bid 11/26 MF 04/02/2026 - Mason Faltysek: Bid received from renascent pricing updated to reflect bid 11/26 MF 04/23/2026 - Mason Faltysek: FA-0205-2026-1759 | 2026-04-23 14:10:29
2025-11-07 10:26:29 | Ryan Payne | 200 | 205 | Office and Lobby Renovation |  |  | April | 18000 | 18000 | Committed | 19485 | -1485 | No | Customer Experience | Building/Site | Facilities Site Work |  | Completed |  | FA-0205-2026-1733 | 2026 | Medium | Yes |  | 01/12/2026 - Mason Faltysek: Bid received from renascent pricing updated to reflect bid 11/26 MF 02/16/2026 - Jonathan Blair: Bid received from renascent pricing updated to reflect bid 11/26 MF 02/23/2026 - Mason Faltysek: Estimate is for 18,000 Budget 18,000 Delta 0 03/12/2026 - Mason Faltysek: Work expected to kick off Monday 3/16 04/22/2026 - Mason Faltysek: FA-0205-2026-1733 04/23/2026 - Mason Faltysek: Project has been completed | 2026-04-23 14:18:38
2025-11-07 10:26:29 | Ryan Payne | 200 | 205 | Door Equipment room changed to a roll up door |  |  | April | 4000 |  | Committed | 7577.5 | -3577.5 | No | Prevent further damage | Building/Site | Facilities Site Work |  | Completed |  | FA-0205-2026-1735 | 2026 | Medium | No |  | 01/12/2026 - Henry Shine: Bid received from renascent pricing updated to reflect bid 11/26 MF 02/24/2026 - Rusty Modesty: Marked Committed. April 03/12/2026 - Mason Faltysek: Door has been ordered no ETA yet 04/23/2026 - Mason Faltysek: Project has been completed | 2026-04-23 14:17:05
2026-05-18 15:34:24 | David Carreon | 100 | 205 | XPT & SAL |  |  | January | 18000 |  | Uncommitted | 0 | 0 | No | Planned maintenance | IT | XPT | Customer Experience | Deferred |  |  |  | High | No |  | 06/15/2026 - David Carreon: 1 XPT will be removed and replaced by a SAL. The other XPT will be removed and replaced by a unit from 217 | 2026-06-15 15:50:20
2026-09-16 11:47:09 | Mason Faltysek | 200 | 205 |  |  |  | June | 10000 |  | Committed | 9341.98 | 658.02 | No | Planned maintenance | Building/Site |  | Customer Experience | In-Process |  | SI-0205-2026-1789 |  | High | No |  |  | 2026-09-16 11:47:09
2025-03-31 08:55:42 | Rusty Modesty | 200 | 206 | Replace Tunnel Heaters | 2013 | Q1 | Jan | 17500 |  | Committed | 20077.33 | -2577.33 |  | Planned maintenance | Building/Site | Building Facilities | Safety | Completed |  | EQ-0206-2025-1136 | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Abel Smith | 200 | 206 | Hydraflex - Restructure of Hydraflex | 2013 | Q1 | N/A | 6500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Hydroflex | Wash Quality | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Phil Loper | 200 | 206 | Replacement of jko dry mat machine | 2013 | Q1 | N/A | 7500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Equipment | rug & mat | Customer Experience | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Rusty Modesty | 200 | 206 | Water Softener | 2013 | Q1 | N/A | 14000 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Equipment | Water Softener | Wash Quality | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - rusty: Gained quote from Sobrite 7/15. Requested install quote from Short Co. 7/16 (RM Removed from Committed based on leadership feedb | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Abel Smith | 200 | 206 | Mitters | 2013 | Q2 | N/A | 30000 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Equipment | Mitter | Wash Quality | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Mason Faltysek | 200 | 206 | Tunnel Liner Wall Panels | 2013 | Q2 | N/A | 15500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Building Facilities | Customer Experience | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Abel Smith | 200 | 206 | Vacuum - Double Drop Vacuum Hoses | 2013 | Q2 | July | 11200 |  | Committed | 9079.19 | 2120.81 |  | Planned maintenance | Equipment | Vacuum | Customer Experience | Completed |  | EQ-0206-2025-1375 | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Rusty Modesty | 200 | 206 | Lighting - Update/Replace exterior lighting | 2013 | Q3 | N/A | 14500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Building Facilities | Safety | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | David Carreon | 200 | 206 | XPT Replacement/upgrade 2 units | 2013 | Q3 | N/A | 16000 |  | Uncommitted | 0 | 0 |  | Planned maintenance | IT | XPT | Customer Experience | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - david: Take XPT from 202 replace with a SAL and install XPT lane 2 at 206. Install SAL lane 1 at 206. Use fab SAL | 2026-01-12 12:31:32
2025-11-07 10:26:29 | Ryan Payne | 200 | 206 | Water Softener |  |  | N/A | 18500 |  | Uncommitted | 0 | 0 | No | Wash Quality | Equipment |  |  | Deferred |  |  | 2026 | High | Yes |  | 01/12/2026 - Mason Faltysek: WX206 02/17/2026 - Philip Loper: 02/17 - Sent an email to Brian Lonsdale and requested a proposal for a new soft water system. 02/25/2026 - Philip Loper: 02/25 - Received proposal and have placed it in the capex folder. The cost without tax is $9,129.60 | 2026-04-21 13:02:26
2025-11-07 10:26:29 | Ryan Payne | 200 | 206 | Office Renovation |  |  | April | 25000 | 22732.5 | Committed | 22732.5 | 0 | No | Customer Experience | Building/Site | Facilities Site Work |  | Completed |  | FA-0206-2026-1761 | 2026 | Low | No |  | 02/24/2026 - Rusty Modesty: Marked Committed. April 04/02/2026 - Rusty Modesty: Will start work on this site 4/7 04/23/2026 - Mason Faltysek: Work will complete 4/25 04/27/2026 - Mason Faltysek: This was completed 4/27 04/27/2026 - Mason Faltysek: Invoice sent to accounting | 2026-04-27 13:38:24
2025-11-07 10:26:29 | Ryan Payne | 200 | 206 | Repair of Dumpster enclosure |  |  |  | 3500 |  |  | 0 | 0 | No | Customer Experience | Building/Site | Facilities Site Work |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: chrome-extension://efaidnbmnnnibpcajpcglclefindmkaj/https://mail.google.com/mail/u/0?ui=2&ik=e6d507a848&attid=0.1&permmsgid=msg-f:1844816312558024840&th=199a1aa979ddf888&view=att&zw&disp=inline&acrobatPromotionSource=gmail_chrome-card | 2026-01-12 12:02:24
2025-11-07 10:26:29 | Ryan Payne | 200 | 206 | Equipment Adding VPD to Site and license |  |  | N/A | 2000 |  | Uncommitted | 0 | 0 | No | Wash Quality | IT | Technology |  | Deferred |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: 02/23/2026 - Rusty Modesty: Updated to deferred. and marked as uncommitted. | 2026-02-23 16:49:07
2025-11-07 10:26:29 | Ryan Payne | 200 | 206 | OTT Tunnel Terminal Control Unit |  |  | March | 4000 |  | Committed | 3792.96 | 207.04 | No | Prevent further damage | IT | Technology | Customer Experience | Completed | 2026-02-20 | EQ-0206-2026-1716 | 2026 | Low | No |  | 02/17/2026 - David Carreon: Plan was made to use existing enclosure and reteminate existing line. Pending PO, will order equipment on 2/19 03/25/2026 - Eric Dunn: note | 2026-06-25 13:16:59
2025-11-07 10:26:29 | Ryan Payne | 200 | 206 | 2 Lanes - Upgrade 1 XPTs to XPT5+ from XPT 2012 - Replace 1 XPT with SAL use XPT for parts |  |  |  | 46000 |  |  | 0 | 0 | No | Prevent further damage | IT | XPT |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: | 2026-01-12 12:02:24
2025-11-07 10:26:29 | Ryan Payne | 200 | 206 | TCS1 Upgrade |  |  |  | 45000 |  |  | 0 | 0 | No | Prevent further damage | IT | Technology |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: | 2026-01-12 12:02:24
2025-11-07 10:26:29 | Ryan Payne | 200 | 206 | Office front door concrete |  |  | February | 6000 |  | Committed | 4470.37 | 1529.63 | No | Prevent further damage | Building/Site | Facilities Site Work | Safety | Completed |  | FA-0206-2026-1684 | 2026 | Medium | Yes |  | 02/05/2026 - Mason Faltysek: received proposal for 5200 sending foam company to bid. expect that number to come back lower 02/09/2026 - Rusty Modesty: Foam Foundation Company to visit 2/6 02/11/2026 - Mason Faltysek: Waiting on estimate as vendor was out for medical surgery on 2/10 02/23/2026 - Mason Faltysek: received both estimates from roof vendor and concrete sub. both approved. Concrete starting 2/25 roofer starting TBD 03/04/2026 - Mason Faltysek: Both gutter and concrete has been repaired | 2026-04-23 14:31:10
2025-11-07 10:26:29 | Ryan Payne | 200 | 206 | Grand Entry Arch |  |  | October | 8000 |  | Committed | 0 | 0 | No | Customer Experience | Equipment | Building Facilities |  | Ordered |  | SI-0206-2026-2006 | 2026 | High | Yes |  | 01/12/2026 - unknown: Taken off of 2025 10/01/25 - This value is for the Arch and tax. Freight and any additional labor or parts are not included. - PL 02/17/2026 - Philip Loper: 02/17 - Sent an email to Terry @ Sonnys and requested a proposal 02/24/2026 - Philip Loper: 02/26- Proposal was returned and placed in the CAPEX folder. The Cost is $6,598.52 with tax. Freight is running $1,500.00 additional | 2026-08-26 12:46:29
2025-03-31 08:55:42 | Mason Faltysek | 200 | 207 | Roof replacement/remediation | 2010 | Q1 | Jan | 25000 |  | Committed | 0 | 0 |  | Planned maintenance | Building/Site | Facilities Site Work | Safety | Completed |  | FA-0207-2025-1208 | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Mason Faltysek | 200 | 207 | Office refresh | 2010 | Q1 | February | 15000 |  | Committed | 0 | 0 |  | Planned maintenance | Building/Site | Building Facilities | Customer Experience | Completed |  | FA-0207-2025-1208 | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Rusty Modesty | 200 | 207 | Replace Tunnel Heaters | 2010 | Q1 | February | 23500 |  | Committed | 24080.4 | -580.4 |  | Planned maintenance | Building/Site | Building Facilities | Safety | Completed |  | EQ-0207-2025-1134 | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Rusty Modesty | 200 | 207 | Water Softener | 2010 | Q1 | N/A | 14000 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Equipment | Water Softener | Wash Quality | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - rusty: Gained a quote from Sobrite 7/15. Requested estimate from Short co for install. 7/16 (RM Removed from Committed based on leaders 02/17/2026 - Philip Loper: 02/17 - Sent an email to Brian Lonsdale and requested a proposal for a new soft water system. | 2026-02-17 15:02:00
2025-03-31 08:55:42 | Abel Smith | 200 | 207 | Replace Entrance Wraps | 2010 | Q3 | August | 30000 |  | Committed | 38832.97 | -8832.97 |  | Planned maintenance | Equipment | Wrap Brush | Wash Quality | Completed |  | EQ-0207-2025-1410 | 2025 | Low | No |  | 01/12/2026 - rusty: Revised estimated cost 43k to 30k based on updated quotes from MCWW. AS- estimated delivery date is 8/18 | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Mason Faltysek | 200 | 207 | Parking lot restripe | 2010 | Q3 | N/A | 6500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Facilities Site Work | Customer Experience | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-11-07 10:26:29 | Ryan Payne | 200 | 207 | Equipment Adding VPD to Site and license |  |  | N/A | 7500 |  | Uncommitted | 0 | 0 | No | Wash Quality | IT | Technology |  | Deferred |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: 02/23/2026 - Rusty Modesty: Removed from committed. Adjusted pricing from $7,500 to $3,500. | 2026-04-21 13:21:25
2025-11-07 10:26:29 | Ryan Payne | 200 | 207 | OTT Tunnel Terminal Control Unit |  |  | March | 4000 |  | Committed | 0 | 0 | No | Safety | IT | Technology | Safety | Completed |  | EQ-0207-2026-1652 | 2026 | Low | No |  |  | 2026-02-09 13:45:25
2025-11-07 10:26:29 | Ryan Payne | 200 | 207 | TCS1 Upgrade |  |  |  | 45000 |  |  | 0 | 0 | No | Prevent further damage | IT | Technology |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: | 2026-01-12 12:02:24
2025-11-07 10:26:29 | Ryan Payne | 200 | 207 | Grand Entry Arch. It is damaged. |  |  | October | 8000 |  | Committed | 0 | 0 | No | Customer Experience | Equipment | Building Facilities |  | Ordered |  | SI-0207-2026-2007 | 2026 | Low | Yes |  | 01/12/2026 - unknown: 10/01/25 - This value is for the Arch and tax. Freight and any additional labor or parts are not included. - PL https://mail.google.com/mail/u/0?ui=2&ik=c225bf958e&attid=0.1&permmsgid=msg-f:1845518091018908886&th=199c98ed01bd34d6&view=fimg&fur=ip&permmsgid=msg-f:1845518091018908886&sz=s0-l75-ft&attbid=ANGjdJ9qtgcJe4lyyZ5yQw0tbnDeB0xyoN5hjhzHTUdQXeo1JVGwwRKADOsgyTLHtlablfbrd4OHigyZFKGLLfIqqYRWKdUhTsg1zQnkmU3dq5OsgwLW_BXAW-PZ5jI&disp=emb&realattid=ii_199c98da0ce83874db41&zw 02/17/2026 - Philip Loper: 02/17 - Sent an email to Terry @ sonnys and requested a proposal. 02/24/2026 - Philip Loper: 02/23 - Terry returned the proposal, and it has been placed in the CAPEX folder. The cost is $6,598.52 with tax. The freight is $1,500 addotional | 2026-08-26 12:47:19
2025-11-07 10:26:29 | Ryan Payne | 200 | 207 | Lighting LED Tunnel Lights |  |  | March | 10500 |  | Committed | 19890.94 | -9390.94 | No | Customer Experience | Building/Site | Building Facilities |  | Completed |  | FA-0207-2026-1683 | 2026 | Medium | Yes |  | 02/11/2026 - Mason Faltysek: Sub stopped by and got a count of all tunnel lights to be replaced with new tube lights on 2/9 02/23/2026 - Mason Faltysek: Project slated to start 3/2 03/13/2026 - Mason Faltysek: project completed | 2026-04-23 14:21:26
2025-12-30 12:06:49 | Rusty Modesty | 200 | 207 | Water Softener |  |  | N/A | 0 |  | Uncommitted | 0 | 0 | Yes |  | Equipment | Water Softener | Wash Quality | Deferred |  |  | 2026 | High | Yes |  | 01/21/2026 - Rusty Modesty: Addition of Missed project. RM 12/20 02/23/2026 - Philip Loper: 02/17 - Sent an email to Brian Lonsdale and requested a proposal for a new soft water system. 02/23 - Sent a follow-up email to Brian asking for a status. 02/25/2026 - Philip Loper: 02/25 - Received proposal and have placed it in the capex folder. The cost without tax is $9,129.60 02/25/2026 - Rusty Modesty: Adjusted Pricing from $0 to $18,500 | 2026-04-21 13:02:48
2025-03-31 08:55:42 | Rusty Modesty | 200 | 208 | Lighting - Update Exterior lighting | 2019 | Q3 | N/A | 14500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Building Facilities | Safety | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-11-07 10:26:29 | Ryan Payne | 200 | 208 | Concrete Repair |  |  |  | 20000 |  |  | 0 | 0 | No | Prevent further damage | Building/Site | Facilities Site Work |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: https://mail.google.com/mail/u/0?ui=2&ik=c225bf958e&attid=0.1&permmsgid=msg-https://mail.google.com/mail/u/0?ui=2&ik=c225bf958e&attid=0.2&permmsgid=msg-f:1845453801122610545&th=199c5e74594ebd71&view=att&disp=safe&realattid=f_mgijsouf2&zwf:1845453801122610545&th=199c5e74594ebd71&view=att&disp=safe&realattid=f_mgijsou61&zw https://mail.google.com/mail/u/0?ui=2&ik=c225bf958e&attid=0.3&permmsgid=msg-f:1845453801122610545&th=199c5e74594ebd71&view=att&disp=safe&realattid=f_mgijsots0&zw https://mail.google.com/mail/u/0?ui=2&ik=c225bf958e&attid=0.4&permmsgid=msg-f:1845453801122610545&th=199c5e74594ebd71&view=att&disp=safe&realattid=f_mgijsoun3&zw | 2026-01-12 12:02:24
2025-11-07 10:26:29 | Ryan Payne | 200 | 208 | Tunnel grand entry arch broken |  |  | July | 8000 | 9483.43 | Committed | 10685.89 | -1202.46 | No | Customer Experience | Equipment | Building Facilities |  | Completed |  | SI-0208-2026-1856 | 2026 | Low | Yes | Yes | 01/12/2026 - unknown: 02/18/2026 - Philip Loper: 02/18 - Sent an email to Terry @ Sonnys and requested a proposal. 02/25/2026 - Rusty Modesty: Adjusted pricing from $10,000 to $8,000 03/02/2026 - Philip Loper: 03/02 - Proposal returned and placed into tthe CAPEX Folder for 2026. Cost on Arch is $6,598.57 before freight and install 07/20/2026 - Andrew Folse: Shipped on 7/16, waiting on tracking info from vendor 07/23/2026 - Andrew Folse: Arch arrived onsite 7/23. Install scheduled 7/24 07/27/2026 - Andrew Folse: Completed on 7/24 | 2026-07-28 15:17:28
2025-11-07 10:26:29 | Ryan Payne | 200 | 208 | PS Tire brush replacement |  |  | N/A | 23000 |  | Uncommitted | 0 | 0 | No | Wash Quality | Equipment |  |  | Deferred |  |  | 2026 | Low | Yes |  | 01/12/2026 - unknown: 02/16/2026 - Jonathan Blair: Went from 15,000 to 23,000. 02/17/2026 - Philip Loper: 02/17 Sent an email to the store and Rusty to ask for additional information. 02/19/2026 - Philip Loper: 02/19 - Rusty emailed Phil and asked him to hold on this project. 02/20/2026 - Rusty Modesty: Project will not be needed. Transitioned to R&M Rebuild. | 2026-04-21 13:22:16
2025-11-07 10:26:29 | Ryan Payne | 200 | 208 | Grundfos (2) 20 gpm |  |  | April | 17000 |  | Committed | 17034.84 | -34.84 | No | Prevent further damage | Equipment |  |  | Completed |  | EQ-0208-2026-1719 | 2026 | High | Yes |  | 01/12/2026 - Mason Faltysek: This location has experienced multiple pump failures due to setup and error. 02/16/2026 - Jonathan Blair: Went from 16k to 17k. 02/17/2026 - Philip Loper: 02/17 - Sent an email to the store and requested photos and additional information. 02/19/2026 - Philip Loper: 02/19 - Sent an email to Terry @ Sonnys and requested a proposal. 02/23/2026 - Philip Loper: 02/23 - Sent an email to Terry @ Sonnys requesting a follow up. 02/24/2026 - Philip Loper: 02/23 - Terry Replied back with proposal. I have placed it in the CAPEX folder. The cost for pumps and control box is $15,406.09. This includes tax (No Freight). 03/24/2026 - Philip Loper: Capex has been submitted for approval. 03/25/2026 - Philip Loper: Capex approved, and the item has been ordered. I have CC'd Rusty and Ryan. cc | 2026-04-15 12:16:31
2025-11-07 10:26:29 | Ryan Payne | 200 | 208 | Conveyor Chain/Rollers |  |  | January | 14573 |  | Committed | 13336.47 | 1236.53 | No | Prevent further damage | Equipment | Conveyor Chain | Prevent further damage | Completed |  | EQ-0208-2026-1626 | 2026 | Low | No |  |  | 2026-02-09 13:44:59
2025-11-07 10:26:29 | Ryan Payne | 200 | 208 | Dry Mat Machine for volume of customer |  |  | September | 6500 |  | Committed | 5716.14 | 783.86 | No | Customer Experience | Building/Site | Facilities Site Work |  | Completed |  | EQ-0208-2026-1930 | 2026 | High | Yes |  | 02/17/2026 - Philip Loper: "02/16 - Sent an email to JKO for a proposal 02/16 - Proposal has been placed in the 2026 CAPEX folder for the store. " 02/24/2026 - Rusty Modesty: Marked Committed. Sept 08/06/2026 - Andrew Folse: Shipped on 8/6 | 2026-08-20 12:39:49
2026-07-27 11:25:16 | Andrew Folse | 200 | 208 | Grundfoss Pump Market Spare |  |  | August | 9000 |  | Committed | 0 | 0 | No | Planned maintenance | Equipment | high pressure pump | Prevent further damage | Committed | 2026-08-01 |  |  | High | No | No | 07/28/2026 - Andrew Folse: We have several sites running on 1 pump with no spare. This will be a market spare Pump | 2026-07-28 12:50:10
2025-03-31 08:55:42 | Mason Faltysek | 200 | 209 | Building improvements - Office Wall Water Damage Repair | 2019 | Q2 | N/A | 18000 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Building Facilities | Prevent further damage | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Abel Smith | 200 | 209 | Vacuum - Double Drop Vacuum Hoses | 2019 | Q2 | N/A | 11200 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Equipment | Vacuum | Customer Experience | Deferred |  |  | 2025 | Low | No |  |  | 2026-04-21 13:23:04
2025-03-31 08:55:42 | Mason Faltysek | 200 | 209 | Concrete - Exit end foundation - Mud jacking | 2019 | Q3 | N/A | 9500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Facilities Site Work | Prevent further damage | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-11-07 10:26:29 | Ryan Payne | 200 | 209 | Power Pack to remove some items from the PECO power pack |  |  |  | 15000 |  | Uncommitted | 0 | 0 | No | Customer Experience | Equipment |  |  | Deferred |  |  | 2026 | High | No |  | 01/12/2026 - unknown: 02/19/2026 - Philip Loper: 02/19 - Sent an email to Rusty, Ryan and Jonathan for additional information. 02/26/2026 - Philip Loper: 02/26 - Sent an email for follow up, have not received information | 2026-04-21 13:03:08
2025-11-07 10:26:29 | Ryan Payne | 200 | 209 | Lobby & Office Renovation--Water Damage |  |  | September | 30000 | 21000 | Committed | 0 | 0 | No | Prevent further damage | Building/Site | Facilities Site Work |  | In-Process |  | FA-0209-2026-2052 | 2026 | Low | No |  | 01/12/2026 - unknown: Taken off of 2025 WX209 02/24/2026 - Rusty Modesty: Marked Committed. Aug 07/15/2026 - Mason Faltysek: Quote will be ready 7/16 08/11/2026 - Mason Faltysek: Sent roofer and painter out to get prices. Roofer found extnesive list of problems with roof from the original install. This has caused us to pivot and we may have to make roof repairs only and not refresh thew office. Pricing expected by 8/12 08/11/2026 - Mason Faltysek: This is still expected to be actioned in august 08/20/2026 - Mason Faltysek: Quote Approved and scheduled week of 8/24 | 2026-09-16 11:45:22
2025-11-07 10:26:29 | Ryan Payne | 200 | 209 | Building Foundation Issue on back of part of building near equipment room door |  |  | N/A | 20000 |  | Uncommitted | 0 | 0 | No | Prevent further damage | Building/Site | Facilities Site Work |  | Deferred |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: Taken off of 2025 02/16/2026 - Jonathan Blair: Went from 16,500 to 20,000 | 2026-04-21 13:23:32
2025-11-07 10:26:29 | Ryan Payne | 200 | 209 | Exterior Painting |  |  |  | 25000 |  |  | 0 | 0 | No | Prevent further damage | Building/Site |  |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: 10/02/25- Value pulled from similar work completed in 25 at Tulsa/Austin Market 02/25/2026 - Rusty Modesty: 10/02/25- Value pulled from similar work completed in 25 at Tulsa/Austin Market | 2026-02-25 13:18:10
2025-11-07 10:26:29 | Ryan Payne | 200 | 209 | Vac 6 New Vac Stalls, Vac Enclosure, Producer |  |  |  | 60000 |  |  | 0 | 0 | No | Customer Experience | Equipment | Vacuum |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: Review WX209 | 2026-01-12 12:02:24
2026-09-16 11:28:28 | Mason Faltysek | 200 | 209 | Roof Repair |  |  | September | 18000 |  | Committed | 0 | 0 | No | Unplanned | Building/Site |  | Customer Experience | Completed |  | FA-0209-2026-1974 |  | High | No |  |  | 2026-09-16 11:29:04
2025-03-31 08:55:42 | David Carreon | 200 | 210 | Module Screens for all gates | 2007 | Q1 | March | 5500 |  | Committed | 2599.5 | 2900.5 |  | Planned maintenance | IT | Technology | Customer Experience | Completed |  | EQ-0210-2025-1250 | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Rusty Modesty | 200 | 210 | Roofing gutter change - Tunnel puddling concrete cutting | 2007 | Q2 | N/A | 4500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Building Facilities | Prevent further damage | Deferred |  |  | 2025 | Low | No |  |  | 2026-04-21 13:26:19
2025-03-31 08:55:42 | Rusty Modesty | 200 | 210 | Water softener installed | 2007 | Q1 | N/A | 14000 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Equipment | Water Softener | Wash Quality | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - rusty: (RM Removed from Committed based on leadership feedback) 02/17/2026 - Philip Loper: 02/17 - Sent an email to Brian Lonsdale and requested a proposal for a new soft water system. | 2026-02-17 15:02:44
2025-03-31 08:55:42 | Rusty Modesty | 200 | 210 | Landscape update | 2007 | Q2 | N/A | 8500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Facilities Site Work | Prevent further damage | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Mason Faltysek | 200 | 210 | Tunnel Liner Wall Panels | 2007 | Q2 | N/A | 15500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Building Facilities | Customer Experience | Deferred |  |  | 2025 | Low | No |  |  | 2026-04-21 13:27:45
2025-03-31 08:55:42 | Mason Faltysek | 200 | 210 | Lot Restriping | 2007 | Q3 | N/A | 6500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Facilities Site Work | Customer Experience | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Mason Faltysek | 200 | 210 | Paint - Repaint (existing paint peeling) | 2007 | Q3 | May | 2800 |  | Committed | 0 | 0 |  | Planned maintenance | Building/Site | Building Facilities | Prevent further damage | Completed |  | FA-0210-2025-1317 | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Mason Faltysek | 200 | 210 | Paint - Vacuum Stall Repaint | 2007 | Q3 | May | 10000 |  | Committed | 0 | 0 |  | Planned maintenance | Building/Site | Facilities Site Work | Customer Experience | Completed |  | FA-0210-2025-1317 | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Abel Smith | 200 | 210 | Tire Brush - Install Tire Brush | 2007 | Q3 | N/A | 30000 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Equipment | Tire Shine | Wash Quality | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | David Carreon | 200 | 210 | XPT Gate | 2007 | - | N/A | 8000 |  | Uncommitted | 0 | 0 |  | Planned maintenance | IT | XPT Gate | Customer Experience | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - unknown: Deferring this one, we are repairing the gates we have | 2026-01-12 12:31:32
2025-11-07 10:26:29 | Ryan Payne | 200 | 210 | Water Softner New Unit |  |  |  | 18500 |  | Uncommitted | 0 | 0 | No | Customer Experience | Equipment |  |  | Deferred |  |  | 2026 | High | Yes |  | 01/12/2026 - unknown: 02/23/2026 - Philip Loper: 02/17 - Sent an email to Brian Lonsdale and requested a proposal for a new soft water system. 02/23 - Sent a follow-up email to Brian asking for a status. 02/25/2026 - Philip Loper: 02/25 - Received proposal and have placed it in the capex folder. The cost without tax is $9,129.60 | 2026-04-21 13:04:18
2025-11-07 10:26:29 | Ryan Payne | 200 | 210 | Office remodel: cupboards/desks/draws |  |  |  | 16500 |  |  | 0 | 0 | No | Customer Experience | Building/Site |  |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: 10/02/25 Cost is for Millwork only. Will be more if entire office needs remodel- MF https://mail.google.com/mail/u/0?ui=2&ik=c225bf958e&attid=0.1&permmsgid=msg-f:1845465809459685280&th=199c696041f927a0&view=att&disp=safe&realattid=199c688f29281c083941&zw https://mail.google.com/mail/u/0?ui=2&ik=c225bf958e&attid=0.3&permmsgid=msg-https://mail.google.com/mail/u/0?ui=2&ik=c225bf958e&attid=0.4&permmsgid=msg-f:1845465809459685280&th=199c696041f927a0&view=att&disp=safe&realattid=199c688f29281dcb2963&zw f:1845465809459685280&th=199c696041f927a0&view=att&disp=safe&realattid=199c688f29281eaca174&zw 02/25/2026 - Rusty Modesty: 10/02/25 Cost is for Millwork only. Will be more if entire office needs remodel- MF https://mail.google.com/mail/u/0?ui=2&ik=c225bf958e&attid=0.1&permmsgid=msg-f:1845465809459685280&th=199c696041f927a0&view=att&disp=safe&realattid=199c688f29281c083941&zw https://mail.google.com/mail/u/0?ui=2&ik=c225bf958e&attid=0.3&permmsgid=msg-https://mail.google.com/mail/u/0?ui=2&ik=c22 | 2026-02-25 13:24:37
2025-11-07 10:26:29 | Ryan Payne | 200 | 210 | Extend gutter tunnel exit asphalt |  |  |  | 5000 |  |  | 0 | 0 | No | Safety | Building/Site | Facilities Site Work |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: | 2026-01-12 12:02:24
2025-11-07 10:26:29 | Ryan Payne | 200 | 210 | Landscaping: mulch beds, new plants in drive flower beds, trim trees |  |  | June | 15000 |  | Committed | 0 | 0 | No | Customer Experience | Building/Site | Facilities Site Work |  | Completed |  | FA-0210-2026-1830 | 2026 | Low | No |  | 01/12/2026 - Mason Faltysek: https://drive.google.com/file/d/1jzc1aa9MxLsh_mf477YlsQmab_ygfiY8/view?usp=drive_web 02/16/2026 - Jonathan Blair: https://drive.google.com/file/d/1jzc1aa9MxLsh_mf477YlsQmab_ygfiY8/view?usp=drive_web 04/17/2026 - Mason Faltysek: bids sent to Jonathan waiting on ryan to confirm what will be in house so we are under budget. 05/12/2026 - Mason Faltysek: Meeting landscaper 5/12 to discuss in dallas 05/18/2026 - Mason Faltysek: Waiting on revised estimates from yellow stone after our site walk on 5/12 06/03/2026 - Mason Faltysek: Approved and released to the vendor 06/08/2026 - Donald Murry: Work scheduled to be completed by end of month. | 2026-07-01 12:56:30
2025-11-07 10:26:29 | Ryan Payne | 200 | 210 | Touch up brown paint peeling in lot on canopies and central vacuum walls |  |  |  | 20500 |  | Uncommitted | 0 | 0 | No | Customer Experience | Building/Site |  |  | Deferred |  |  | 2026 | High | No |  | 01/12/2026 - unknown: 10/02/25 - Pulled cost from 25 for same work at another DFW location- MF 02/25/2026 - Rusty Modesty: 10/02/25 - Pulled cost from 25 for same work at another DFW location- MF | 2026-04-21 13:04:41
2025-11-07 10:26:29 | Ryan Payne | 200 | 210 | Grand Entry arch sign |  |  | October | 8000 |  | Committed | 0 | 0 | No | Customer Experience | Equipment | Building Facilities |  | Ordered |  | SI-0210-2026-2008 | 2026 | Low | Yes |  | 01/12/2026 - unknown: https://mail.google.com/mail/u/0?ui=2&ik=c225bf958e&attid=0.2&permmsgid=msg-f:1845467032245225953&th=199c6a7cf5abc9e1&view=att&disp=safe&realattid=f_mgir8b7q1&zw https://mail.google.com/mail/u/0?ui=2&ik=c225bf958e&attid=0.3&permmsgid=msg-f:1845467032245225953&th=199c6a7cf5abc9e1&view=att&disp=safe&realattid=f_mgir8dpr2&zw 02/19/2026 - Philip Loper: 02/19 - Sent an email to Terry @ Sonnys requesting a proposal. 02/24/2026 - Philip Loper: 02/23 - Terry returned the proposal and I have placed it in the CAPEX folder. The cos it $6,598.57 with Tax. Freight is an additional $1,500.00 | 2026-08-26 12:47:42
2025-11-07 10:26:29 | Ryan Payne | 200 | 210 | Equipment poodle brush |  |  | March | 22257.7 |  | Committed | 23255.8 | -998.1 | No | Wash Quality | Equipment |  |  | Completed |  | EQ-0210-2026-1691 | 2026 | Low | Yes |  | 02/26/2026 - Philip Loper: 02/26 - Capex Approved. 02/26/2026 - Philip Loper: 02/26 - Sent an email to Jody @ MCWW and requested delivery of 03/23/26 03/05/2026 - Philip Loper: The original budget was $15K. The new proposed budget, due to adding a power pack, is $22,257.70 | 2026-03-26 12:35:44
2025-11-07 10:26:29 | Ryan Payne | 200 | 210 | Wrap Replacement |  |  | N/A | 39000 |  | Uncommitted | 0 | 0 | No | Wash Quality | Equipment |  |  | Deferred |  |  | 2026 | High | Yes |  | 02/19/2026 - Philip Loper: 02/19 - Sent an email Jody @ MCWW and requested a proposal. 03/03/2026 - Philip Loper: 03/02 - Proposal has been returned and placed in the CAPEX folder. Total Cost for Equipment is $24,762.19 | 2026-04-21 13:03:51
2026-02-24 12:38:07 | Rusty Modesty | 200 | 210 | Mitter Replacement |  |  | N/A | 15500 |  | Uncommitted | 0 | 0 | No | Planned maintenance | Equipment | Mitter | Wash Quality | Deferred |  |  |  | High | No |  | 02/24/2026 - Rusty Modesty: Project addition 2/26 | 2026-04-21 13:28:45
2025-03-31 08:55:42 | Mason Faltysek | 200 | 211 | Paint - Repaint (existing paint peeling) | 2011 | Q3 | May | 22200 |  | Committed | 0 | 0 |  | Planned maintenance | Building/Site | Building Facilities | Prevent further damage | Completed |  |  | 2025 | Low | No |  | 01/12/2026 - unknown: Getting Pictures to Contractor to add to our list | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Phil Loper | 200 | 211 | Replace wraps | 2011 | Q4 | September | 40000 |  | Committed | 45959.01 | -5959.01 |  | Planned maintenance | Equipment | Wrap Brush | Safety | Completed | 2025-09-16 | EQ-0211-2025-1464 | 2025 | Low | No |  | 01/12/2026 - phil: 10/01/25 - Project has been completed the evening of 09/30/25 - PL 09/16/25 - Equipment has been ordered and ACH sent. Equipment is scheduled to be delivered on 09/29/25 09/11/25 This project PO was approved by Henry. - PL 09/08/25 -The proposal for Equipment and installation has been given to Gregg and Rusty. Waiting on approval from Rusty - PLOPER Request sent 9/11-RM | 2026-01-12 12:31:32
2025-08-20 11:04:32 | Phil Loper | 200 | 211 | Mitter Replacement 2 | 2011 | Q4 | October | 30000 |  | Committed | 41208.36 | -11208.36 | No | Planned maintenance | Equipment | Mitter | Customer Experience | Completed | 2025-09-16 | EQ-0211-2025-1467 | 2025 | Low | No |  | 01/12/2026 - phil: 10/01/25 - Project has been completed the evening of 09/30/25 - PL 09/16/25 - Equipment has been ordered and ACH sent. Equipment is scheduled to be delivered on 09/29/25 09/11/25 - Submitted for PO approval. Waiting on approval. - PLOPER 09/08/25 -The proposal for Equipment and installation has been given to Gregg and Rusty. Waiting on approval from Rusty - PLOPER | 2026-01-12 12:31:32
2025-11-07 10:26:29 | Ryan Payne | 200 | 211 | Office Remodel |  |  |  | 25000 |  |  | 0 | 0 | No | Customer Experience | Building/Site | Facilities Site Work |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: 10/02/25- Value pulled from work completed in DFW market in 25- MF | 2026-01-12 12:02:24
2025-11-07 10:26:29 | Ryan Payne | 200 | 211 | Landscape Islands/Grass Repair |  |  | June | 15000 |  | Committed | 0 | 0 | No | Customer Experience | Building/Site | Facilities Site Work |  | Completed |  | FA-0211-2026-1831 | 2026 | Low | No |  | 01/12/2026 - unknown: https://drive.google.com/open?id=1HhAIjA_4tWESDlphp3LZGUslp0EclpoA 02/16/2026 - Jonathan Blair: https://drive.google.com/open?id=1HhAIjA_4tWESDlphp3LZGUslp0EclpoA 04/17/2026 - Mason Faltysek: bids sent to Jonathan waiting on ryan to confirm what will be in house so we are under budget. 05/12/2026 - Mason Faltysek: Meeting landscaper 5/12 to discuss in dallas 05/18/2026 - Mason Faltysek: Waiting on revised estimates from yellow stone after our site walk on 5/12 06/03/2026 - Mason Faltysek: Approved and released to the vendor 06/08/2026 - Donald Murry: Work scheduled to be completed by end of month. | 2026-07-01 12:56:41
2025-11-07 10:26:29 | Ryan Payne | 200 | 211 | Exterior Painting |  |  |  | 10000 |  |  | 0 | 0 | No | Customer Experience | Building/Site |  |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: | 2026-02-25 13:24:51
2025-11-07 10:26:29 | Ryan Payne | 200 | 211 | Wheel brush addition |  |  | March | 15000 |  | Committed | 31996.6 | -16996.6 | No | Wash Quality | Equipment |  |  | Completed |  | EQ-0211-2026-1692 | 2026 | Medium | Yes |  | 02/26/2026 - Philip Loper: 02/26 - CAPEX approved. EQ-0211-2026-1692 02/26/2026 - Philip Loper: 02/26 - Sent an email to Jody @ MCWW and requested delivery of 03/23/26 | 2026-03-26 12:35:56
2025-11-07 10:26:29 | Ryan Payne | 200 | 211 | Chain-rollers/rebuild |  |  | September | 13500 |  | Committed | 0 | 0 | No | Prevent further damage | Equipment | Conveyor Chain |  | In-Process | 2026-09-01 | EQ-0211-2026-2019 | 2026 | High | Yes | No | 01/12/2026 - Mason Faltysek: Revised to Rebuild project vs replace. 02/19/2026 - Philip Loper: 02/19 - Sent an email to Eric @ Vaughn and requested a proposal 02/23/2026 - Philip Loper: Eric @ Vaughn has returned the proposal. I have placed it in the folder. The Cost is $10,636.16 07/27/2026 - Andrew Folse: End of life - reduce downtime 09/14/2026 - Andrew Folse: Parts onsite | 2026-09-14 14:45:04
2025-03-31 08:55:42 | David Carreon | 200 | 212 | Camera Sytem Upgrade/Replacement | 2014 | Q2 | N/A | 3000 |  | Uncommitted | 0 | 0 |  | Planned maintenance | IT | Camera | Safety | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - unknown: Deferred Combined with 201 PO JMCC | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Rusty Modesty | 200 | 212 | Landscaping | 2014 | Q2 | N/A | 8000 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Facilities Site Work | Prevent further damage | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Phil Loper | 200 | 212 | Tire Brush - Install tire Brush | 2014 | Q4 | October | 16000 |  | Committed | 22074.82 | -6074.82 |  | Planned maintenance | Equipment | Wheel Brush | Wash Quality | Completed |  | EQ-0212-2025-1511 | 2025 | Low | No |  | 01/12/2026 - rusty: 10/16/25 - Approved and email sent to accounting and vendor - PL 10/06/25 - Received the quote from Jody. Cost is $35,726.89 with Labor - PL 09/24/25 - Received both quotes. They have been loaded into a folder for review. -PL "09/22/25 - Sent an email to Jody at TWW for a proposal. - PL 09/22/25 - Sent an email to Terry at Sonnys for a Proposal - PL" 09/08/25 -The proposal for Equipment and installation has been given to Gregg and Rusty. Waiting on approval from Rusty - PLOPER | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Abel Smith | 200 | 212 | Vacuum - Double Drop Vacuum Hoses | 2014 | Q4 | November | 11200 |  | Committed | 10028.38 | 1171.62 |  | Planned maintenance | Equipment | Vacuum | Customer Experience | Completed |  | EQ-0212-2025-1536 | 2025 | Low | No |  | 01/12/2026 - rusty: RFQ Sent 9/11 | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Mason Faltysek | 200 | 212 | Building improvements - Office wall water Damage. | 2014 | Q2 | May | 19000 |  | Committed | 0 | 0 |  | Planned maintenance | Building/Site | Building Facilities | Prevent further damage | Completed |  | FA-0212-2025-1316 | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Abel Smith | 200 | 212 | Relocation of overhead solenoids | 2014 | Q2 | N/A | 0 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Equipment | Building Facilities | Safety | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - unknown: WIll be R&M | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Mason Faltysek | 200 | 212 | Paint - Repaint (existing paint peeling) | 2014 | Q3 | May | 11500 |  | Committed | 0 | 0 |  | Planned maintenance | Building/Site | Building Facilities | Prevent further damage | Completed |  | FA-0212-2025-1316 | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Mason Faltysek | 200 | 212 | Paint - Vacuum Stall Paint | 2014 | Q3 | May | 15000 |  | Committed | 0 | 0 |  | Planned maintenance | Building/Site | Facilities Site Work | Customer Experience | Completed |  | FA-0212-2025-1316 | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Mason Faltysek | 200 | 212 | Parking lot restripe | 2014 | Q3 | N/A | 6500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Facilities Site Work | Customer Experience | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Phil Loper | 200 | 212 | Conveyor Grates | 2018 | Q3 | N/A | 19000 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Equipment | Conveyor Chain | Safety | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - rusty: Corrected site number 8/28 04/21/2026 - Jonathan Blair: Corrected site number 8/28 | 2026-04-21 13:29:32
2025-11-07 10:26:29 | Ryan Payne | 200 | 212 | Equipment Wrap Brush Replacement |  |  | N/A | 39000 |  | Uncommitted | 0 | 0 | No | Wash Quality | Equipment |  |  | Deferred |  |  | 2026 | High | No |  | 02/19/2026 - Philip Loper: 02/19 - Sent an email to jody @ MCWW for a proposal. 03/03/2026 - Philip Loper: MCWW has returned the proposal and it has been placed in the CAPEX folder. Total for Equipment is $27,603.87 | 2026-04-21 13:06:55
2025-11-07 10:26:29 | Ryan Payne | 200 | 212 | Vac Enclosure Door--Change to Roll Up Door |  |  | September | 7500 |  | Committed | 0 | 0 | No | Safety | Building/Site | Facilities Site Work |  | Completed |  | FA-0212-2026-1931 | 2026 | Low | No |  | 01/12/2026 - unknown: WX212 Recommend replacing sheeting on current door. -RM 02/24/2026 - Rusty Modesty: Marked Committed. Aug 07/15/2026 - Mason Faltysek: Estimate ready 7/16 07/20/2026 - Mason Faltysek: Door has been placed on order 08/11/2026 - Mason Faltysek: Pushed this to october due to long lead time on the roll up door | 2026-09-08 14:44:17
2025-11-07 10:26:29 | Ryan Payne | 200 | 212 | Flag Pole Repair |  |  | April | 6000 | 3226.83 | Committed | 0 | 0 | No | Customer Experience | Building/Site | Facilities Site Work |  | Completed |  | FA-0212-2026-1725 | 2026 | Low | Yes |  | 01/12/2026 - unknown: WX212 02/16/2026 - Jonathan Blair: WX212 02/23/2026 - Mason Faltysek: Received quotes ryan had solicited last year 02/23/2026 - Mason Faltysek: Quote $ 3,164.66 Estimated cost 6000 Delta $2835.34 03/12/2026 - Mason Faltysek: Reaching out to vendor to schedule work 03/26/2026 - Rusty Modesty: Project Completed. Per mason 3/26 04/23/2026 - Mason Faltysek: FA-0212-2026-1725 Hoist and rope has been replaced 05/05/2026 - Ryan Payne: This did not hit capex. | 2026-04-23 14:10:57
2025-11-07 10:26:29 | Ryan Payne | 200 | 212 | Blowers |  |  | N/A | 16500 |  |  | 0 | 0 | No | Prevent further damage | Equipment | Blowers |  | 2026 Request |  |  | 2026 | Medium | No |  | 01/12/2026 - Mason Faltysek: 10/03/25 - This is a price for a flash blower, arch and electrical. WW would preform an install for this price. - PL 02/18/2026 - Philip Loper: 02/18 - Sent an email to Jody @ MCWW requesting a proposal for two blowers 02/23/2026 - Philip Loper: 02/23 - Received an email from Ryan Pane that said "Put this on hold right now, I don't think new blowers are needed, just an adjustment on blower positioning. " | 2026-02-18 16:02:51
2025-11-07 10:26:29 | Ryan Payne | 200 | 212 | Power Pack |  |  |  | 15000 |  | Uncommitted | 0 | 0 | No | Customer Experience | Equipment |  |  | Deferred |  |  | 2026 | High | No |  | 01/12/2026 - unknown: | 2026-04-21 13:06:34
2025-11-07 10:26:29 | Ryan Payne | 200 | 212 | Water Leak in tower |  |  | June | 11500 |  | Committed | 11907.5 | -407.5 | No | Prevent further damage | Building/Site | Facilities Site Work |  | Completed |  | FA-0212-2026-1760 | 2026 | High | No |  | 01/12/2026 - mason: Bid received from renascent pricing updated to reflect bid 11/26 MF 02/24/2026 - Rusty Modesty: Marked Committed. Sept 04/23/2026 - Mason Faltysek: Deployment moved up Will take place after 214 05/12/2026 - Mason Faltysek: Expected to start End of week 5/18 05/29/2026 - Mason Faltysek: Lift has arrived on site scheduled to begin work on 5/29 06/03/2026 - Mason Faltysek: This is completed | 2026-06-03 16:11:57
2026-03-11 12:47:40 | Jonathan Blair | 200 | 212 | Grand Entry |  |  | October | 8000 |  | Committed | 0 | 0 | No | Planned maintenance | Building/Site | Building Facilities | Customer Experience | Ordered |  | SI-0212-2026-2016 |  | High | No |  |  | 2026-08-28 08:06:33
2026-03-13 11:02:48 | Rusty Modesty | 200 | 212 | Conveyor Replacement |  |  | N/A | 110000 |  | Uncommitted | 0 | 0 | No | Planned maintenance | Equipment | Conveyor Chain | Prevent further damage | Deferred |  |  |  | High | No |  | 04/21/2026 - Jonathan Blair: Addition of project based on need and visual inspection. Will need to include new fiberglass grating. | 2026-08-16 13:15:11
2026-07-27 11:33:58 | Andrew Folse | 200 | 212 | New Conveyor |  |  | September | 100000 | 110000 | Committed | 75463.41 | 34536.59 | No | Planned maintenance | Equipment | Conveyor Chain | Prevent further damage | Completed | 2026-09-01 | EQ-0212-2026-1935 |  | High | No | No | 07/28/2026 - Andrew Folse: This conveyor is in really bad shape. We have done countless patch jobs, welds, and repairs. It will not make it to 2027 | 2026-09-16 08:21:02
2026-09-16 11:22:52 | Mason Faltysek | 200 | 212 |  |  |  | June | 15500 |  | Uncommitted | 0 | 0 | No | Planned maintenance |  |  |  | Completed |  | FA-0212-2026-1969 |  | High | No |  |  | 2026-09-16 11:22:52
2026-09-16 11:30:03 | Mason Faltysek | 100 | 212 | Office Remodel |  |  | July | 15500 |  | Committed | 0 | 0 | No | Planned maintenance | Building/Site |  | Customer Experience | Completed |  | FA-0212-2026-1969 |  | High | No |  |  | 2026-09-16 11:30:15
2025-03-31 08:55:42 | Mason Faltysek | 200 | 213 | XPT 1 gate box balusters (middle XPT) | 2015 | Q2 | N/A | 2500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | XPT | Prevent further damage | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Phil Loper | 200 | 213 | Install a tire brush | 2015 | Q2 | N/A | 14500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Equipment | Wheel Brush | Wash Quality | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - rusty: Duplicate 04/22/2026 - Rusty Modesty: Duplicate | 2026-04-22 16:08:52
2025-03-31 08:55:42 | Mason Faltysek | 200 | 213 | Paint - Repaint (existing paint peeling) | 2015 | Q3 | May | 37898 |  | Committed | 0 | 0 |  | Planned maintenance | Building/Site | Building Facilities | Prevent further damage | Completed |  | FA-0213-2025-1318 | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Mason Faltysek | 200 | 213 | Parking lot restripe | 2015 | Q3 | N/A | 6500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Facilities Site Work | Customer Experience | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-08-20 11:21:21 | Phil Loper | 200 | 213 | Addition of Wheel Brush |  | Q4 | October | 16000 |  | Committed | 21582.84 | -5582.84 | No | Planned maintenance | Equipment | Wheel Brush | Customer Experience | Completed |  | EQ-0213-2025-1510 | 2025 | Low | No |  | 01/12/2026 - rusty: 10/16/25 - Approved and email sent to Accounting and Vendor - PL 10/06/25 - Received the quote from Jody. Cost is $35,726.89 with Labor - PL 09/24/25 - Received both quotes. They have been loaded into a folder for review. -PL "09/22/25 - Sent an email to Jody at TWW for a proposal. - PL 09/22/25 - Sent an email to Terry at Sonnys for a Proposal - PL" 09/08/25 -The proposal for Equipment and installation has been given to Gregg and Rusty. Waiting on approval from Rusty - PLOPER | 2026-01-12 12:31:32
2025-11-07 10:26:29 | Ryan Payne | 200 | 213 | Repaint awnings. |  |  |  | 15000 |  | Uncommitted | 0 | 0 | No | Customer Experience | Building/Site |  |  | Deferred |  |  | 2026 | High | No |  | 01/12/2026 - unknown: 10/02/25 Value pulled from 25 for same work in DFW 02/25/2026 - Rusty Modesty: 10/02/25 Value pulled from 25 for same work in DFW | 2026-04-21 13:07:40
2025-11-07 10:26:29 | Ryan Payne | 200 | 213 | Market Spare 40 Vac Producer |  |  | May | 18600 |  | Committed | 17397.94 | 1202.06 | No | Prevent further damage | Equipment | Vacuum |  | Completed |  | EQ-0213-2026-1720 | 2026 | High | Yes |  | 01/12/2026 - unknown: Spare based on historic needs 02/16/2026 - Jonathan Blair: Went from 17,000 to 18,600 02/18/2026 - Philip Loper: 02/18 - MCWW returned the proposal and it has been placed in the CAPEX folder. Cost is $16,856.78 before tax./ 03/24/2026 - Philip Loper: Capex Requested. 03/25/2026 - Philip Loper: This has been ordered via email to MCWW on 03-25-26. Rusty and Ryan have been CC'd. 04/23/2026 - Rusty Modesty: Order was delayed by the manufacturer. We expect shipment last week of April. Pushing project completion to May. 05/07/2026 - Rusty Modesty: Unit was used for an emergency repair at WX0202. Reordered. 06/01/2026 - Andrew Folse: Adjusted deployment to June. Originally ordered producer was used for emergency repair at another location. New producer was ordered for this capex. | 2026-06-14 17:50:35
2025-11-07 10:26:29 | Ryan Payne | 200 | 213 | Conveyor Replacement |  |  | N/A | 108000 |  |  | 0 | 0 | No | Prevent further damage | Equipment | Conveyor Chain |  | 2026 Request |  |  | 2026 | High | No |  | 01/12/2026 - Mason Faltysek: WX213 09/24/25 - Sent an email to the store and asked for additional information and photos. - PL 09/25/25 - Dylan Hebb from teh site sent over the photos that were rquested - PL 09/29/25 - Sent an email to Jody @ TWW requesting a quote. - PL 02/17/2026 - Philip Loper: 2/17 - Sent an email to the store asking for additional information and photos. 02/19/2026 - Philip Loper: 02/18 - Sent Eric @ Vaughn a request for proposal. 02/19/2026 - Philip Loper: 02/19 - Sent an email to MCWW and requested a proposal. 02/24/2026 - Philip Loper: 02/23 - Jody @ MCWW returned the proposal. This jas been placed in the capex folder. The total cost for conveyor, chain, and roller is $75,198.97. | 2026-02-17 16:50:31
2025-11-07 10:26:29 | Ryan Payne | 200 | 213 | Wrap Replacement |  |  | N/A | 39000 |  | Uncommitted | 0 | 0 | No | Wash Quality | Equipment |  |  | Deferred |  |  | 2026 | High | Yes |  | 02/19/2026 - Philip Loper: 02/19 - Sent an email to Jody at MCWW for a proposal. 03/03/2026 - Philip Loper: 03/03 - MCWW returned the proposal and it has been placed in the folder. Total Cost $27,158.96 for Equipment, Tax and Freight. | 2026-04-21 13:07:18
2025-11-07 10:26:29 | Ryan Payne | 200 | 213 | Water leak in tower, repaint office |  |  | August | 15500 |  | Uncommitted | 0 | 0 | No | Prevent further damage | Building/Site | Facilities Site Work |  | Deferred |  |  | 2026 | High | No |  | 01/12/2026 - mason: Bid received from renascent pricing updated to reflect bid 11/26 MF 02/24/2026 - Rusty Modesty: Marked Committed. August 07/15/2026 - Mason Faltysek: Walls removed and watching for leaks with current rain | 2026-08-10 15:35:17
2025-11-07 10:26:29 | Ryan Payne | 200 | 213 | Canopy above vacuums needs to be fixed. |  |  | N/A | 10000 |  | Uncommitted | 0 | 0 | No | Safety | Building/Site | Facilities Site Work |  | Deferred |  |  | 2026 | Medium | No |  | 01/12/2026 - mason: Bid received from renascent pricing updated to reflect bid 11/26 MF 02/24/2026 - Rusty Modesty: Marked Committed. Sept | 2026-07-27 08:07:51
2025-03-31 08:55:42 | Abel Smith | 200 | 214 | Conveyor Chain and rebuild. | 2016 | Q2 | June | 14500 |  | Committed | 11889.59 | 2610.41 |  | Planned maintenance | Equipment | chain/roller | Wash Quality | Completed |  | EQ-0214-2025-1409 | 2025 | Low | No |  | 01/12/2026 - abel_s: Previous estimates were not including required parts. New estimates are in progress. | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Mason Faltysek | 200 | 214 | Paint - Repaint (existing paint peeling) | 2016 | Q3 | N/A | 25500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Building Facilities | Prevent further damage | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-11-07 10:26:29 | Ryan Payne | 200 | 214 | Water Leak in tower |  |  | N/A | 10000 |  | Uncommitted | 0 | 0 | No | Prevent further damage | Building/Site | Facilities Site Work |  | Deferred |  |  | 2026 | High | No |  | 01/12/2026 - mason: Bid received from renascent pricing updated to reflect bid 11/26 MF 02/24/2026 - Rusty Modesty: Marked Committed. Aug 08/10/2026 - Mason Faltysek: This was completed during the paint work earlier in the year. | 2026-08-26 13:41:58
2025-11-07 10:26:29 | Ryan Payne | 200 | 214 | Tunnel Colored lighting |  |  |  | 8000 |  |  | 0 | 0 | No | Customer Experience | Equipment | Building Facilities |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: (How many are out?) - GM (This is for tunnel colored led lights, 4 are out) | 2026-01-12 12:02:24
2025-11-07 10:26:29 | Ryan Payne | 200 | 214 | Roof and building painting |  |  | May | 81000 | 70000 | Committed | 71387.27 | -1387.27 | No | Customer Experience | Building/Site | Facilities Site Work |  | Completed |  | FA-0214-2026-1766 | 2026 | Medium | Yes |  | 01/12/2026 - Henry Shine: Bid received from renascent pricing updated to reflect bid 11/26 MF 02/16/2026 - Jonathan Blair: Bid received from renascent pricing updated to reflect bid 11/26 MF 02/23/2026 - Mason Faltysek: Quote 80.646.25 estimated cost 81000 Delta 354.75 03/23/2026 - Mason Faltysek: Waiting on color selection from marketing 04/27/2026 - Mason Faltysek: Currently in process 05/07/2026 - Mason Faltysek: Wind and weather has been a constant battle with completing this site we are actively still working through it and expect to wrap up the roof painting by the end of the week and move to building the following 05/29/2026 - Mason Faltysek: Completed 5/29 | 2026-05-29 13:48:37
2025-11-07 10:26:29 | Ryan Payne | 200 | 214 | Tar clean up off exterior walls |  |  | June | 25000 |  | Committed | 0 | 0 | No | Safety | Building/Site |  |  | Deferred |  |  | 2026 | Low | Yes |  | 01/12/2026 - Mason Faltysek: 10/02/25 Receieved estimate in 25 for this work - MF 02/16/2026 - Jonathan Blair: 10/02/25 Receieved estimate in 25 for this work - MF 02/23/2026 - Mason Faltysek: Quote 25000 Estimated cost 25000 Delta 0 04/02/2026 - Rusty Modesty: we have started power washing the building today but with rain in the forecast, we do not expect to finish this week, but we will keep you posted on progress. 05/18/2026 - Mason Faltysek: This portion of the project has been completed | 2026-09-16 11:33:23
2025-11-07 10:26:29 | Ryan Payne | 200 | 214 | Repaint awnings |  |  | May | 15000 |  | Committed | 16237.5 | -1237.5 | No | Customer Experience | Building/Site |  |  | Completed |  | FA-0214-2026-1765 | 2026 | Medium | Yes |  | 02/23/2026 - Mason Faltysek: Quote 15000 Estimated Cost 15000 Delta 0 05/29/2026 - Mason Faltysek: completed 5/29 | 2026-05-29 13:47:56
2025-11-07 10:26:29 | Ryan Payne | 200 | 214 | Matt Machine Jko Mat Machine |  |  |  | 6000 |  |  | 0 | 0 | No | Customer Experience | Building/Site | Facilities Site Work |  | 2026 Request |  |  | 2026 | Medium | No |  | 01/12/2026 - unknown: https://mail.google.com/mail/u/0?ui=2&ik=c225bf958e&attid=0.1&permmsgid=msg-f:1845454941254880404&th=199c5f7dce7c8c94&view=att&disp=safe&realattid=199c5f7a39023c125d52&zw https://mail.google.com/mail/u/0?ui=2&ik=c225bf958e&attid=0.2&permmsgid=msg-f:1845454941254880404&th=199c5f7dce7c8c94&view=att&disp=safe&realattid=199c5f7a390292625371&zw https://mail.google.com/mail/u/0?ui=2&ik=c225bf958e&attid=0.3&permmsgid=msg-f:1845454941254880404&th=199c5f7dce7c8c94&view=att&disp=safe&realattid=199c5f7a390f7a99b343&zw | 2026-01-12 12:01:41
2025-11-07 10:26:29 | Ryan Payne | 200 | 215 | Power Packs Replacement |  |  |  | 30000 |  | Uncommitted | 0 | 0 | No | Wash Quality | Equipment |  |  | Deferred |  |  | 2026 | High | No |  | 01/12/2026 - unknown: 02/19/2026 - Philip Loper: 02/19 - Sent Rusty and team an email to request additional information on this project. | 2026-04-21 13:07:59
2025-11-07 10:26:29 | Ryan Payne | 200 | 215 | Repair or replace the wet mat cleaning machine |  |  |  | 10000 |  |  | 0 | 0 | No | Customer Experience | Building/Site | Facilities Site Work |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: Machine Repaired R&M 2025 | 2026-01-12 12:02:24
2025-03-31 08:55:42 | Mason Faltysek | 200 | 216 | Windows perm solution for ventalation | 2018 | Q2 | June | 19000 |  | Committed | 27062.5 | -8062.5 |  | Planned maintenance | Building/Site | Building Facilities | Safety | Completed |  | FA-0216-2025-1319 | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Abel Smith | 200 | 216 | Air Compressor | 2018 | Q4 | October | 7000 |  | Committed | 8845.42 | -1845.42 |  | Planned maintenance | Equipment | Compressors Replacement | Wash Quality | Completed |  | EQ-0216-2025-1469 | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Rusty Modesty | 200 | 216 | Building improvements - Office Entry Doors not closing and bent | 2018 | Q2 | N/A | 3000 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Building Facilities | Prevent further damage | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Rusty Modesty | 200 | 216 | Landscaiping: mulch beds, add plants to parking lot bed, trim trees and roses | 2018 | Q2 | May | 7500 |  | Committed | 0 | 0 |  | Planned maintenance | Building/Site | Facilities Site Work | Prevent further damage | Completed |  |  | 2025 | Low | No |  | 01/12/2026 - rusty: Completed. 7/14 Non-Capex item. Cost increase due to irrigation repair, which was noticed during the refresh. | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Phil Loper | 200 | 216 | tire brushes | 2018 | Q2 | N/A | 4500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Equipment | Wheel Brush | Wash Quality | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Mason Faltysek | 200 | 216 | Lighting - Addition of lighting in parking area | 2018 | Q3 | N/A | 15000 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Facilities Site Work | Safety | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Mason Faltysek | 200 | 216 | Paint - Repaint (existing paint peeling) | 2018 | Q3 | June | 9288 |  | Committed | 0 | 0 |  | Planned maintenance | Building/Site | Building Facilities | Prevent further damage | Completed |  |  | 2025 | Low | No |  | 01/12/2026 - unknown: will be assesed during Louver install 03/31/2026 - Eric Dunn: will be assessed during Louver install | 2026-03-31 12:31:47
2025-03-31 08:55:42 | Mason Faltysek | 200 | 216 | Parking lot restripe | 2018 | Q3 | N/A | 6500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Facilities Site Work | Customer Experience | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Abel Smith | 200 | 216 | Top sprayer | 2018 | Q3 | N/A | 3800 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Equipment | high pressure rinse | Wash Quality | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - rusty: Abel- Can move from July to Sept. Will improve wash quality but Ill make a plan for this and schedule accordingly | 2026-01-12 12:31:32
2025-11-07 10:26:29 | Ryan Payne | 200 | 216 | Wall Panneling (DS blower room) |  |  |  | 15500 |  |  | 0 | 0 | No | Customer Experience | Building/Site | Facilities Site Work |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: 05/05/2026 - Ryan Payne: We can pull material from storage, it's only about a 20 foot section of one side of the tunnel | 2026-01-12 12:02:24
2025-11-07 10:26:29 | Ryan Payne | 200 | 216 | Landscaping: mulch beds & add shore up crushed granite beds |  |  | June | 15000 |  | Committed | 0 | 0 | No | Customer Experience | Building/Site | Facilities Site Work |  | Completed |  | FA-0216-2026-1833 | 2026 | Low | No |  | 02/24/2026 - Rusty Modesty: Marked as committed. April 04/17/2026 - Mason Faltysek: bids sent to Jonathan waiting on ryan to confirm what will be in house so we are under budget. signing with Yellowstone so it would make sense to have them perform the work as they will be maintaing it moving forward. 05/12/2026 - Mason Faltysek: Meeting landscaper 5/12 to discuss in dallas 05/18/2026 - Mason Faltysek: Waiting on revised estimates from yellow stone after our site walk on 5/12 06/03/2026 - Mason Faltysek: Approved and released to the vendor 06/08/2026 - Donald Murry: Work scheduled to be completed by end of month. | 2026-07-01 12:57:13
2025-11-07 10:26:29 | Ryan Payne | 200 | 216 | Touch up brown paint peelig in lot on canopies |  |  |  | 12000 |  | Uncommitted | 0 | 0 | No | Customer Experience | Building/Site |  |  | Deferred |  |  | 2026 | High | No |  | 01/12/2026 - unknown: | 2026-04-21 13:08:21
2025-11-07 10:26:29 | Ryan Payne | 200 | 216 | x2 Car Wash Entrance signs - yellowing & need to be replaced |  |  | June | 16000 |  | Committed | 4916.99 | 11083.01 | No | Customer Experience | Building/Site | Building Facilities |  | Completed |  | SI-0216-2026-1795 | 2026 | Low | No |  | 01/12/2026 - unknown: Need further explination on which sign. 02/16/2026 - Jonathan Blair: Need further explination on which sign. 02/24/2026 - Donald Murry: Awaiting sign company site survey 05/18/2026 - Mason Faltysek: Waiting on revised estimates from yellow stone after our site walk on 5/12 | 2026-07-21 10:06:06
2025-11-07 10:26:29 | Ryan Payne | 200 | 216 | Tire Brush Install |  |  | March | 15000 |  | Committed | 32284.09 | -17284.09 | No | Wash Quality | Equipment |  |  | Completed |  | EQ-0216-2026-1693 | 2026 | Medium | Yes |  | 02/26/2026 - Philip Loper: 02/26 - CAPEX is approved. EQ-0216-2026-1693 02/26/2026 - Philip Loper: 02/26 - Sent an email to Jody @ MCWW and requested delivery of 03/23/26 | 2026-03-26 12:36:41
2025-11-07 10:26:29 | Ryan Payne | 200 | 216 | top omni |  |  | N/A | 15000 |  |  | 0 | 0 | No | Wash Quality | Equipment |  |  | 2026 Request |  |  | 2026 | Low | No |  |  | 2026-01-12 12:02:24
2025-11-07 10:26:29 | Ryan Payne | 200 | 216 | Mezzanine ladder guard |  |  | N/A | 6000 |  |  | 0 | 0 | No | Safety | Building/Site | Facilities Site Work |  | 2026 Request |  |  | 2026 | High | No |  | 01/12/2026 - Mason Faltysek: Bid received from renascent pricing updated to reflect bid 11/26 MF | 2026-01-12 12:00:08
2026-04-14 09:43:37 | Andrew Folse | 100 | 216 | Water Softener |  |  | July | 4500 |  | Uncommitted | 0 | 0 | No | Planned maintenance | Equipment |  | Wash Quality | Deferred |  |  |  | Low | No |  | 04/27/2026 - Andrew Folse: 1 Head is leaking and the system has been bypassed. | 2026-04-27 11:51:42
2026-04-14 09:48:24 | Andrew Folse | 200 | 216 | Water Softener |  |  | August | 4500 |  | Committed | 5488.97 | -988.97 | No | Planned maintenance | Equipment | Water Softener | Wash Quality | Completed |  | EQ-0216-2026-1922 |  | Low | No |  | 04/27/2026 - Andrew Folse: 1 Water softener head is leaking and the system is bypassed so they are running on hard water. 07/01/2026 - Andrew Folse: We are installing all new chemical deliver in July. We will revisit the need for softener based on wash quality after the chemical install 07/27/2026 - Andrew Folse: Awaiting vendor schedule for install date | 2026-08-16 13:10:32
2025-03-31 08:55:42 | Rusty Modesty | 200 | 217 | Landscaping: mulch beds, new plants in lot flower beds, plant missing trees | 2023 | Q2 | N/A | 7500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Facilities Site Work | Prevent further damage | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Mason Faltysek | 200 | 217 | Parking lot restripe | 2023 | Q3 | N/A | 6500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Facilities Site Work | Customer Experience | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-11-07 10:26:29 | Ryan Payne | 200 | 217 | Wall Panneling |  |  | October | 16500 | 18943.75 | Committed | 0 | 0 | No | Customer Experience | Building/Site | Facilities Site Work |  | Completed |  | FA-0217-2026-1975 | 2026 | Low | No |  | 01/12/2026 - unknown: 08/11/2026 - Mason Faltysek: Reached out to ryan for clarification on scope of work 08/11/2026 - Mason Faltysek: Pricing slated to be in 8/16 08/20/2026 - Mason Faltysek: Jonathan blair approved estimate panels are on order 4 week lead time | 2026-09-03 16:36:58
2025-11-07 10:26:29 | Ryan Payne | 200 | 217 | Landscaping: mulch beds, new plants in drive flower beds, trim trees |  |  | June | 15000 |  | Committed | 0 | 0 | No | Customer Experience | Building/Site | Facilities Site Work |  | Completed |  | FA-0217-2026-1834 | 2026 | Low | No |  | 01/12/2026 - Mason Faltysek: https://mail.google.com/mail/u/0?ui=2&ik=c225bf958e&attid=0.6&permmsgid=msg-f:1845468247863262979&th=199c6b97fe26ff03&view=att&disp=safe&realattid=f_mgirzp2t5&zw https://mail.google.com/mail/u/0?ui=2&ik=c225bf958e&attid=0.4&permmsgid=msg- f:1845468247863262979&th=199c6b97fe26ff03&view=att&disp=safe&realattid=f_mgirzglh3&zw https://mail.google.com/mail/u/0?ui=2&ik=c225bf958e&attid=0.2&permmsgid=msg-f:1845468247863262979&th=199c6b97fe26ff03&view=att&disp=safe&realattid=f_mgirzaye1&zw 02/16/2026 - Jonathan Blair: https://mail.google.com/mail/u/0?ui=2&ik=c225bf958e&attid=0.6&permmsgid=msg-f:1845468247863262979&th=199c6b97fe26ff03&view=att&disp=safe&realattid=f_mgirzp2t5&zw https://mail.google.com/mail/u/0?ui=2&ik=c225bf958e&attid=0.4&permmsgid=msg- f:1845468247863262979&th=199c6b97fe26ff03&view=att&disp=safe&realattid=f_mgirzglh3&zw https://mail.google.com/mail/u/0?ui=2&ik=c225bf958e&attid=0.2&permmsgid=msg-f:1845468247863262979&th=199c6b97fe26ff03&view=att&disp=safe&realattid=f_mgir | 2026-07-01 12:57:25
2025-03-31 08:55:42 | Mason Faltysek | 200 | 219 | Roof leak repair (Active project?) | 2022 | Q4 | N/A | 16000 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Building Facilities | Prevent further damage | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - mason: Roof needs full replacement. Work has been completed that temporarily solves the leak but will need replacement to solve it long term. 9/9 04/22/2026 - Rusty Modesty: Roof needs full replacement. Work has been completed that temporarily solves the leak but will need replacement to solve it long term. 9/9 | 2026-04-22 16:12:50
2025-03-31 08:55:42 | Rusty Modesty | 200 | 219 | Landscaping | 2022 | Q2 | N/A | 8500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Facilities Site Work | Prevent further damage | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-08-20 11:23:45 | Mason faltysek | 200 | 219 | Exit Pad Concrete |  | Q4 | N/A | 15000 |  | Uncommitted | 0 | 0 | No | Planned maintenance | Building/Site | Facilities Site Work | Customer Experience | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - mason: The existing grade is higher than the slab elevation this cannot be fixed. 9/9 04/21/2026 - Jonathan Blair: The existing grade is higher than the slab elevation this cannot be fixed. 9/9 | 2026-04-22 16:13:02
2025-11-07 10:26:29 | Ryan Payne | 200 | 219 | French Drain XPT2 |  |  |  | 30000 |  |  | 0 | 0 | No | Safety | Building/Site | Facilities Site Work |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: This would be an expensive repair as there is no easy outlet to route the water. We looked at this when the seller was renovating the site and there was not an easy solution. This would likely be 10's of 10,000's of $$ to correct -GM | 2026-01-12 12:02:24
2025-11-07 10:26:29 | Ryan Payne | 200 | 219 | Landscaping refresh |  |  | June | 15000 |  | Committed | 0 | 0 | No | Customer Experience | Building/Site | Facilities Site Work |  | Completed |  | FA-0219-2026-1835 | 2026 | Low | No |  | 01/12/2026 - Mason Faltysek: https://drive.google.com/file/d/1MXNEzsX7MjOwnUsGXptdkfavmdCMc5WX/view?usp=drive_web https://drive.google.com/file/d/1JlwtY3E7mq6ehdOL3i9BXpbDmK0w98TN/view?usp=drive_web https://drive.google.com/file/d/15crdoUqFlu6FocrPOpXt7LUDXS09siPj/view?usp=drive_web https://drive.google.com/file/d/1WV7fFASMYODGrK0Dmmp-N0u4a2RDzww0/view?usp=drive_web 02/24/2026 - Rusty Modesty: Marked as committed. April 05/12/2026 - Mason Faltysek: Meeting landscaper 5/12 to discuss in dallas 05/18/2026 - Mason Faltysek: Waiting on revised estimates from yellow stone after our site walk on 5/12 06/03/2026 - Mason Faltysek: Approved and released to the vendor 06/08/2026 - Donald Murry: Work scheduled to be completed by end of month. | 2026-07-01 12:57:37
2026-05-19 10:09:14 | Rusty Modesty | 200 | 219 | Chain/Roller Rebuild |  | Q2 | June | 14500 |  | Committed | 14237.26 | 262.74 | No | Planned maintenance | Equipment | chain/roller | Customer Experience | Completed |  | EQ-0219-2026-1823 |  | High | No |  | 05/28/2026 - Andrew Folse: Parts order will be placed today 5/28/2026 Will update with expected delivery date. | 2026-07-20 18:41:18
2025-03-31 08:55:42 | Mason Faltysek | 200 | 220 | Cut Concrete channel for drainage in tunnel | 2023 | Q1 | August | 7500 |  | Committed | 0 | 0 |  | Planned maintenance | Building/Site | Facilities Site Work | Prevent further damage | Completed |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | David Carreon | 200 | 220 | Module screen for all gates | 2023 | Q1 | March | 5600 |  | Committed | 3736.83 | 1863.17 |  | Planned maintenance | IT | XPT Gate | Customer Experience | Completed |  | EQ-0220-2025-1249 | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-11-07 10:26:29 | Ryan Payne | 200 | 220 | Landscaping--river rock from mulch |  |  | N/A | 15000 |  |  | 0 | 0 | No | Customer Experience | Building/Site | Facilities Site Work |  | 2026 Request |  |  | 2026 | Low | No |  |  | 2026-01-12 12:02:24
2025-03-31 08:55:42 | Mason faltysek | 200 | 221 | Lighting in Tunnel | 2014 | Q3 | May | 8500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Building Facilities | Safety | Completed |  |  | 2025 | Low | No |  | 01/12/2026 - rusty: Only 5 light out on the site. This will not fall under capex. 04/21/2026 - Jonathan Blair: Only 5 light out on the site. This will not fall under capex. | 2026-04-21 12:53:10
2025-03-31 08:55:42 | Mason Faltysek | 200 | 221 | Exterior lighting | 2007 | Q2 | N/A | 7500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Facilities Site Work | Safety | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Mason Faltysek | 200 | 221 | Signage - New Grand Entry Arch (top and sides) | 2007 | Q2 | N/A | 13500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Equipment | marketing/signage | Customer Experience | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Abel Smith | 200 | 221 | Vac Tool Coversion | 2007 | Q2 | N/A | 11200 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Equipment | Vacuum | Customer Experience | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Mason Faltysek | 200 | 221 | Lighting in tunnel | 2007 | Q2 | September | 8500 |  | Committed | 0 | 0 |  | Planned maintenance | Building/Site | Building Facilities | Safety | Completed |  |  | 2025 | Low | No |  | 01/12/2026 - mason: Lights will be installed night of 9/29 and 9/30 | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Mason Faltysek | 200 | 221 | Parking lot restripe | 2007 | Q3 | N/A | 6500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Facilities Site Work | Customer Experience | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-11-07 10:26:29 | Ryan Payne | 200 | 221 | Building Equipment room exhaust fan |  |  | June | 10500 |  | Committed | 9959 | 541 | No | Safety | Building/Site | Facilities Site Work |  | Completed |  | FA-0221-2026-1837 | 2026 | Low | No |  | 01/12/2026 - unknown: It is extremley hot/retention issue 02/24/2026 - Rusty Modesty: Marked as Committed. June 05/12/2026 - Mason Faltysek: Reached out for clarity on scope of work 06/03/2026 - Mason Faltysek: Approved by Rusty/Andrew. The estimate has been approved waiting on Lead time from the vendor 06/08/2026 - Donald Murry: Contractor should be on site tomorrow to begin install 06/08/2026 - Donald Murry: Install scheduled week of 6/8 pending weather 06/15/2026 - Mason Faltysek: This is expected to be completed i have followed up with contractor to confirm 06/15/2026 - Mason Faltysek: Due to weather this will be completed wednesday | 2026-07-01 12:57:49
2025-11-07 10:26:29 | Ryan Payne | 200 | 221 | Concrete Exit Pad |  |  |  | 10000 |  |  | 0 | 0 | No | Safety | Building/Site | Facilities Site Work |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: 2025 project | 2026-01-12 12:02:24
2025-11-07 10:26:29 | Ryan Payne | 200 | 221 | Grand Entry Arch |  |  | October | 8000 |  | Committed | 0 | 0 | No | Customer Experience | Equipment | Building Facilities |  | Ordered |  | SI-0221-2026-2009 | 2026 | Low | Yes |  | 01/12/2026 - unknown: 02/18/2026 - Philip Loper: 02/18 - Sent an email to Jody @ MCWW and requested a proposal. 03/02/2026 - Philip Loper: 03/02 - Proposal returned and placed in the 2026 CAPEX folder. Cost is $6,598.52 before freight | 2026-08-26 12:49:15
2025-11-07 10:26:29 | Ryan Payne | 200 | 221 | Vac Tool Conversion |  |  |  | 10000 |  |  | 0 | 0 | No |  | Equipment | Vacuum |  | 2026 Request |  |  | 2026 | Medium | No |  | 01/12/2026 - unknown: 05/05/2026 - Ryan Payne: This was completed by Ops, can be removed | 2026-01-12 12:01:41
2025-11-07 10:26:29 | Ryan Payne | 200 | 224 | Relocate Mat Machines |  |  | N/A | 10000 |  |  | 0 | 0 | No |  | Building/Site | Facilities Site Work |  | 2026 Request |  |  | 2026 | Low | No |  | 05/05/2026 - Ryan Payne: This was completed already. | 2026-01-12 12:02:24
2025-11-07 10:26:29 | Ryan Payne | 200 | 224 | XPT Sign replaced |  |  |  | 8000 |  |  | 0 | 0 | No | Customer Experience | Equipment | Building Facilities |  | 2026 Request |  |  | 2026 | High | No |  | 01/12/2026 - unknown: Customer Damage | 2026-01-12 12:00:08
2025-03-31 08:55:42 | Abel Smith | 300 | 301 | Hydra Flex - New Hydra Flex | 2011 | Q4 | September | 6500 |  | Committed | 0 | 0 |  | Planned maintenance | Equipment | Hydroflex | Wash Quality | Completed |  | EQ-0301-2025-1577 | 2025 | Low | No |  | 01/12/2026 - Rusty Modesty: Variance in cost due to additional BAM and MAM fitting to support the new panel. As well, an additional power disconnect and communication panel for swap. | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Abel Smith | 300 | 301 | Prep Guns | 2011 | Q2 | N/A | 11000 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Equipment | Prep Pump | Wash Quality | Deferred |  |  | 2025 | Medium | No |  |  | 2026-01-12 12:01:22
2025-03-31 08:55:42 | Mason Faltysek | 300 | 301 | Drainage in Lot (Entrance) (Talk with Lauren before schedule) | 2011 | Q3 | N/A | 5500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Facilities Site Work | Prevent further damage | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Mason Faltysek | 300 | 301 | Parking lot restripe | 2011 | Q3 | N/A | 6500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Facilities Site Work | Customer Experience | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-08-20 11:25:15 | Abel Smith | 300 | 301 | Exit Conveyor Section |  | Q4 | N/A | 10000 |  | Uncommitted | 0 | 0 | No | Planned maintenance | Equipment | Conveyor Chain | Customer Experience | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - rusty: Post further inspection, this will not be needed. AS 04/22/2026 - Rusty Modesty: Post further inspection, this will not be needed. AS | 2026-04-22 16:13:57
2025-11-07 10:36:13 | Lauren Fine | 300 | 301 | TCS1 Upgrade |  |  |  | 45000 |  |  | 0 | 0 | No | Prevent further damage | IT | Technology |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: | 2026-01-12 12:02:24
2026-02-25 13:26:38 | Jonathan Blair | 100 | 301 | Canopies over vacuum |  |  | August | 0 |  | Committed | 0 | 0 | No | Planned maintenance | Building/Site |  |  | Completed |  | FA-0301-2026-1894 |  | High | No |  | 06/01/2026 - Rusty Modesty: Approval received from Clayton through Brandy 6/1/2026 07/20/2026 - Andrew Folse: Waiting on vendor to confirm install date | 2026-09-16 08:23:02
2025-03-31 08:55:42 | Abel Smith | 300 | 302 | Blower Project | 2017 | Q1 | March | 15000 |  | Committed | 57740.73 | -42740.73 |  | Planned maintenance | Equipment | Blowers | Wash Quality | Completed |  | EQ-0302-2025-1200 | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Abel Smith | 300 | 302 | Conveyor rebuild | 2017 | Q1 | N/A | 7500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Equipment | Conveyor Chain | Wash Quality | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Mason Faltysek | 300 | 302 | Parking lot restripe | 2017 | Q3 | N/A | 6500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Facilities Site Work | Customer Experience | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Abel Smith | 300 | 302 | Wind Door Installation - Entrance | 2016 | Q3 | N/A | 12500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Building Facilities | Safety | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-11-07 10:36:13 | Ryan Payne | 300 | 302 | Tunnel radiant heater |  |  | January | 19300 |  | Committed | 19419.35 | -119.35 | No | Safety | Building/Site | Facilities Site Work | Safety | Completed |  | FA-0302-2026-1642 | 2026 | High | Yes |  |  | 2026-04-23 14:43:49
2025-11-07 10:36:13 | Lauren Fine | 300 | 302 | TCS1 Upgrade |  |  |  | 45000 |  |  | 0 | 0 | No | Prevent further damage | IT | Technology |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: | 2026-01-12 12:02:24
2025-03-31 08:55:42 | Abel Smith | 300 | 303 | Chain and rollers | 2016 | Q4 | August | 12000 |  | Committed | 14010.87 | -2010.87 |  | Planned maintenance | Equipment | chain/roller | Wash Quality | Completed |  | EQ-0303-2025-1516 | 2025 | Low | No |  | 01/12/2026 - rusty: RFQ. Site visit needed. Planned week of 9/15 | 2026-01-12 12:31:32
2025-03-31 08:55:42 | David Carreon | 300 | 303 | Alarm System | 2016 | Q2 | N/A | 3200 |  | Uncommitted | 0 | 0 |  | Planned maintenance | IT | Technology | Safety | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - unknown: Deferring this to do it in house - Dustin project Q2. Project is deferred per Lauren | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Abel Smith | 300 | 303 | Conveyor/tunnel Grates | 2016 | Q3 | September | 9000 |  | Committed | 8700 | 300 |  | Planned maintenance | Equipment | Conveyor Chain | Wash Quality | Completed |  | EQ-0303-2025-1424 | 2025 | Low | No |  | 01/12/2026 - rusty: AS- Approval requested 8/12. ShortCo will do this work $8700.00 | 2026-01-12 12:31:32
2025-03-31 08:55:42 | David Carreon | 300 | 303 | Exit Gate | 2016 | Q3 | May | 7500 |  | Committed | 11660.61 | -4160.61 |  | Planned maintenance | IT | XPT | Safety | Completed |  | EQ-0303-2025-1336 | 2025 | Low | No |  | 01/12/2026 - rusty: New gate installed and functional, awaiting new 15 ft arm/barrier | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Mason faltysek | 300 | 303 | Lighting - Addition of lights in parking area | 2016 | Q3 | June | 15000 |  | Committed | 10282.3 | 4717.7 |  | Planned maintenance | Building/Site | Facilities Site Work | Safety | Completed |  | FA-0303-2025-1348 | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Mason Faltysek | 300 | 303 | Paint - Roof Paint | 2016 | Q3 | June | 33000 |  | Committed | 0 | 0 |  | Planned maintenance | Building/Site | Building Facilities | Prevent further damage | Completed |  | FA-0303-2023-416 | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Abel Smith | 300 | 303 | Parking lot restripe | 2016 | Q3 | N/A | 6500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Facilities Site Work | Customer Experience | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Mason faltysek | 300 | 303 | Repaving Lot | 2016 | Q3 | June | 35000 |  | Committed | 40000 | -5000 |  | Planned maintenance | Building/Site | Facilities Site Work | Prevent further damage | Completed |  | FA-0303-2025-1347 | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Abel Smith | 400 | 401 | Additional Flash Blower | 2019 | Q1 | Feb | 15000 |  | Committed | 0 | 0 |  | Planned maintenance | Equipment | Blowers | Wash Quality | Completed |  |  | 2025 | Low | No |  | 01/12/2026 - unknown: only charge was new arch and electrician work | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Abel Smith | 400 | 401 | Ladder Rack for Tunnel and ER 80ft | 2019 | Q4 | N/A | 3000 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Equipment | Building Facilities | Safety | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - unknown: Abel- This can come off the list. Ladder Rack has been supplies from surrounding markets left over from Greenfield installs acro | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Mason Faltysek | 400 | 401 | Replace pylon sign faces | 2019 | Q3 | March | 5600 |  | Committed | 0 | 0 |  | Planned maintenance | Building/Site | marketing/signage | Customer Experience | Completed |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-11-07 10:26:29 | Ryan Payne | 400 | 401 | rockers to replace van highs |  |  |  | 15500 |  |  | 0 | 0 | No | Prevent further damage | Equipment |  |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: follow up with Todd Thacker. This will be corrected through R&M WX401 09/18/25 - Sent an email to Terry @ Sonnys requesting a quote - PL 09/2425 - Terry returned the quote and I placed it in the folder. -PL | 2026-01-12 12:02:24
2025-11-07 10:26:29 | Ryan Payne | 400 | 401 | 401-CAPEX Chain/Roller Refit |  |  | January | 13500 |  | Committed | 15038.03 | -1538.03 | No | Prevent further damage | Equipment | Conveyor Chain | Prevent further damage | Completed | 2026-01-07 | EQ-0401-2026-1624 | 2026 | Low | No |  | 01/12/2026 - Philip Loper: most current car count on chain 347665 12/18/25 - Cost of Equipment, Tax and Freight is $13,213.90. The proposal is located at https://drive.google.com/file/d/17p90B4WahWcI5tP9BtAF_mLrvwgFn1D9/view?usp=drive_link - PL 01/07/2026 - Chain ordered from Vaughn - PL 01/28/2026 - Philip Loper: most current car count on chain 347665 12/18/25 - Cost of Equipment, Tax and Freight is $13,213.90. The proposal is located at https://drive.google.com/file/d/17p90B4WahWcI5tP9BtAF_mLrvwgFn1D9/view?usp=drive_link - PL 01/07/2026 - Chain ordered from Vaughn - PL | 2026-02-09 13:45:49
2025-11-07 10:26:29 | Ryan Payne | 400 | 401 | Power Pack to seperate Single PP |  |  |  | 15000 |  | Uncommitted | 0 | 0 | No | Customer Experience | Equipment |  |  | Deferred |  |  | 2026 | High | No |  | 01/12/2026 - unknown: 02/19/2026 - Philip Loper: 02/19 - Sent Rusty and team an email to request additional information on this project. | 2026-04-21 13:08:48
2025-11-07 10:26:29 | Ryan Payne | 400 | 401 | Office remodel (Flooring, Paint, Customer Island, Break room in place of extra bathroom? Lobby becomes manager office.) |  |  |  | 25000 |  |  | 0 | 0 | No | Customer Experience | Building/Site | Facilities Site Work |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: Is this really necessary???- MF | 2026-01-12 12:02:24
2025-11-07 10:26:29 | Ryan Payne | 400 | 401 | Tunnel liners (Exit area) Use of extra Material? |  |  | April | 18500 |  | Committed | 26927.7 | -8427.7 | No | Customer Experience | Building/Site | Facilities Site Work |  | Completed |  | FA-0401-2026-1726 | 2026 | Low | Yes |  | 01/12/2026 - unknown: WX401 02/16/2026 - Jonathan Blair: It went from 13,000 to 18,500 02/20/2026 - Rusty Modesty: Additional Request of entire tunnel presented by Todd Thacker. Pricing adjusted to match complete tunnel project. 02/23/2026 - Mason Faltysek: Quoted 18500 Estimated cost 18500 Delta 0 04/02/2026 - Rusty Modesty: Currently in production and expected to ship out next week 04/02/2026 - Rusty Modesty: Ordered 04/23/2026 - Mason Faltysek: Expected arrival pushed to first week of may | 2026-04-23 14:25:55
2025-11-07 10:26:29 | Ryan Payne | 400 | 401 | Second mat cleaner machine (Dry JKo |  |  |  | 6500 |  |  | 0 | 0 | No | Customer Experience | Building/Site | Facilities Site Work |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: WX401 09/22/25 - Sent an email to JKO and requested a proposal. -PL 09/22/25 - Recieved the proposal from JKO and placed it in the folder. -PL | 2026-01-12 12:02:24
2025-11-07 10:26:29 | Ryan Payne | 400 | 401 | Whitewater Arch (Complete Arch) |  |  | October | 8000 |  | Committed | 0 | 0 | No | Customer Experience | Equipment | Building Facilities |  | Ordered |  | SI-0401-2026-2010 | 2026 | Low | Yes |  | 01/12/2026 - unknown: WX401 09/22/25 - Spoke to Ryan and he informed me that Tommy is requesting the entire arch be replaced. I have sent an email to Terry @ Sonnys and requested,. -PL 09/22/25 - Terry sent back the quote and I have placed it in the 401 folder - PL 02/17/2026 - Philip Loper: 2/17 - Sent an email to Terry at Sonnys and requested a proposal. 02/24/2026 - Philip Loper: 02/24 - Terry replicd back tih the proposal. I have placed it in the CAPEX folder. Total cost is $6,598.52 with tax. Freight is an additional $1,500.00 02/25/2026 - Rusty Modesty: Revised price from $8,500 to 8,000.00 | 2026-08-26 12:49:43
2025-11-07 10:26:29 | Ryan Payne | 400 | 401 | Take windows out and put roll up doors/ or add vents in tunnel area |  |  | June | 8200 |  | Committed | 8118.75 | 81.25 | No | Safety | Building/Site | Facilities Site Work |  | Completed |  | FA-0401-2026-1811 | 2026 | Medium | Yes |  | 01/12/2026 - Mason Faltysek: Bid received from renascent pricing updated to reflect bid 11/26 MF 02/16/2026 - Jonathan Blair: Bid received from renascent pricing updated to reflect bid 11/26 MF 02/23/2026 - Mason Faltysek: Quote 8118.75 Estimated Cost 8200 Delta 81.25 04/02/2026 - Rusty Modesty: Louvers are ordered. Current lead time is 3 to 4 weeks. 04/17/2026 - Mason Faltysek: Louvers expected to come in May 1st. Lead time has extended 05/12/2026 - Mason Faltysek: Starting the week of 5/18 05/18/2026 - Mason Faltysek: Louvers have shipped as of 5/16 espected to land week of 5/18 05/29/2026 - Mason Faltysek: Louvers arrived onsite 06/03/2026 - Mason Faltysek: This is completed | 2026-06-03 09:16:47
2026-05-04 09:25:59 | Andrew Folse | 400 | 401 | Smart Water Meter | 2026 |  | August | 4485.62 |  | Committed | 6742.22 | -2256.6 | No | Planned maintenance | Building/Site |  | Safety | Completed |  | EQ-0401-2026-1918 |  | Low | No |  | 06/22/2026 - Andrew Folse: Site has to climb down into a tank to check the water meter. It is dangerous and requires lowering a ladder into the tank and climbing down. This is a safety issue. We plan to install a smart water meter inside the equipment room. 07/24/2026 - Andrew Folse: Part has been ordered to site. Maintenance will install in August. 07/30/2026 - Andrew Folse: Meter is onsite 08/10/2026 - Andrew Folse: Meter is onsite. Waiting for parts to arrive. Will schedule for last week in August 08/20/2026 - Andrew Folse: Install 8/28 | 2026-09-14 14:45:54
2025-03-31 08:55:42 | Phil Loper | 400 | 402 | Aqua Lab new | 2020 | Q1 | Mar | 4500 |  | Committed | 8779.41 | -4279.41 |  | Planned maintenance | Equipment | Hydroflex | Wash Quality | Completed |  | EQ-0402-2025-1212 | 2025 | Low | No |  | 01/12/2026 - unknown: EQ-0402-2025-1212 | 2026-01-12 12:31:32
2025-03-31 08:55:42 | David Carreon | 400 | 402 | XPT Printers | 2020 | Q1 | N/A | 3850 |  | Uncommitted | 0 | 0 |  | Planned maintenance | IT | XPT | Customer Experience | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - david: Duplicate entry | 2026-01-12 12:31:32
2025-03-31 08:55:42 | David Carreon | 400 | 402 | XPT Receipt Printers - 2x | 2020 | Q1 | Non Capex | 2800 |  | Uncommitted | 0 | 0 |  | Planned maintenance | IT | XPT | Customer Experience | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - unknown: Not capex required | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Phil Loper | 400 | 402 | Tire brush - Poodle Brushs | 2020 | Q4 | N/A | 4800 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Equipment | Wheel Brush | Wash Quality | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - unknown: Abel- Can be deleted. This is for material, not CapEx | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Mason Faltysek | 400 | 402 | Parking lot restripe | 2020 | Q3 | N/A | 6500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Facilities Site Work | Customer Experience | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-11-07 10:26:29 | Ryan Payne | 400 | 402 | Dumpster Enclosure |  |  | January | 12000 |  | Committed | 0 | 0 | No | Safety | Building/Site | Facilities Site Work |  | Completed |  | FA-0402-2026-1640 | 2026 | High | Yes |  | 02/05/2026 - Mason Faltysek: completed 2/3 | 2026-02-23 18:00:03
2025-11-07 10:26:29 | Ryan Payne | 400 | 402 | Matt Machine Jko Mat Machine |  |  |  | 6500 |  |  | 0 | 0 | No | Customer Experience | Building/Site | Facilities Site Work |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: WX402 09/22/25 - Sent an email to JKO and requested a proposal. -PL 09/22/25 - Recieved the quote back from JKO and placed it in the folder - PL | 2026-01-12 12:02:24
2025-11-07 10:26:29 | Ryan Payne | 400 | 402 | Conveyor Chain/Rollers |  |  | January | 15507 |  | Committed | 14736.49 | 770.51 | No | Prevent further damage | Equipment | Conveyor Chain | Prevent further damage | Completed | 2026-01-08 | EQ-0402-2026-1625 | 2026 | Low | No |  | 01/12/2026 - Philip Loper: most current car count 563702 WX402 12/19/25 - Sonnys returned the Proposal with $15,507.16 Proposal located at https://drive.google.com/file/d/1hSaQNCBl4raw8phZMAbLb8rQTZJghVSJ/view?usp=drive_link -PL 12/19/25 - Orignal Budget was 13,500 - PL 02/09/2026 - Rusty Modesty: most current car count 563702 WX402 12/19/25 - Sonnys returned the Proposal with $15,507.16 Proposal located at https://drive.google.com/file/d/1hSaQNCBl4raw8phZMAbLb8rQTZJghVSJ/view?usp=drive_link -PL 12/19/25 - Orignal Budget was 13,500 - PL | 2026-02-09 13:46:00
2025-11-07 10:26:29 | Ryan Payne | 400 | 402 | Landscaping Refresh |  |  | June | 15000 |  | Committed | 0 | 0 | No | Customer Experience | Building/Site | Facilities Site Work |  | Deferred |  |  | 2026 | Low | No |  | 02/16/2026 - Jonathan Blair: Went from 15,000 to 18,500 02/18/2026 - Jonathan Blair: Corrected to 15000 | 2026-06-03 16:08:40
2025-11-07 10:26:29 | Ryan Payne | 400 | 402 | Sign Clearance Signs for Drive |  |  |  | 7500 |  |  | 0 | 0 | No | Customer Experience | Equipment | Building Facilities |  | 2026 Request |  |  | 2026 | Medium | No |  | 01/12/2026 - unknown: WX402 10/03/25 - Sent an email to the store asking for additional information and photos - PL | 2026-01-12 12:01:41
2026-06-22 13:02:58 | Andrew Folse | 400 | 402 | Tunnel wall liners |  |  | November | 16000 |  | Committed | 0 | 0 | No | Planned maintenance | Building/Site | Building Facilities | Customer Experience | Proposal Solicitation |  |  |  | Low | No |  | 09/02/2026 - Andrew Folse: Tunnel has bare block walls that are dirty and look bad. This project would strictly be for aesthetics. 09/10/2026 - Mason Faltysek: Panels have been ordered due to time constraints of project being uncommited until 9/2. Working on Estimate with contractor | 2026-09-10 08:27:04
2025-03-31 08:55:42 | David Carreon | 400 | 403 | Gate Control Modules 2x | 2020 | Q1 | N/A | 2800 |  | Uncommitted | 0 | 0 |  | Planned maintenance | IT | XPT | Customer Experience | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Mason Faltysek | 400 | 403 | Tunnel Liner Wall Panels | 2020 | Q4 | October | 15500 |  | Committed | 17181.27 | -1681.27 |  | Planned maintenance | Building/Site | Building Facilities | Customer Experience | Completed |  | FA-0403-2025-1514 | 2025 | Low | No |  | 01/12/2026 - rusty: ordered 9/30 Completed per Todd Thacker 10/23 -RM | 2026-01-12 12:31:32
2026-02-24 12:31:05 | Rusty Modesty | 400 | 403 | City Water Booster Pump |  |  | N/A | 0 |  | Uncommitted | 0 | 0 | No | Planned maintenance | Equipment | high pressure pump | Wash Quality | Awaiting Approval |  |  |  | Medium | No |  | 02/24/2026 - Rusty Modesty: Project addition 2/26. $6768 Pump stand, $500 Tax, $1,000 shipping, $2000 install. | 2026-02-24 12:33:39
2025-03-31 08:55:42 | Abel Smith | 400 | 404 | Chain - New Chain,rollers, drum and sprocket | 2022 | Q4 | N/A | 13000 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Equipment | chain/roller | Wash Quality | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - rusty: Duplicate Project. 04/22/2026 - Rusty Modesty: Duplicate Project. | 2026-04-22 16:14:23
2025-03-31 08:55:42 | Abel Smith | 400 | 404 | Tire brush - New Bison Brush for Second Set | 2022 | Q4 | N/A | 4500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Equipment | Wheel Brush | Wash Quality | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - unknown: Abel- This can be removed. Request for material. Not CapEx | 2026-01-12 12:31:32
2025-11-07 10:26:29 | Ryan Payne | 400 | 404 | Create exit lane from exit of tunnel onto Yager Ln |  |  |  | 100000 |  |  | 0 | 0 | No | Customer Experience | Building/Site | Facilities Site Work |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: WX404 | 2026-01-12 12:02:24
2025-11-07 10:26:29 | Ryan Payne | 400 | 404 | Tunnel Liners Entire Tunnel |  |  | April | 18500 |  | Committed | 15857.76 | 2642.24 | No | Customer Experience | Building/Site | Facilities Site Work |  | Completed |  | FA-0404-2026-1727 | 2026 | Low | Yes |  | 01/12/2026 - unknown: 02/16/2026 - Jonathan Blair: From15500 to 18500 02/23/2026 - Mason Faltysek: Quoted 18500 Estimated cost 18500 Delta 0 04/02/2026 - Rusty Modesty: Currently in production and expected to ship out next week 04/02/2026 - Rusty Modesty: Ordered 04/23/2026 - Mason Faltysek: This has been completed | 2026-04-23 14:27:39
2025-11-07 10:26:29 | Ryan Payne | 400 | 404 | Matt Machine Jko Mat Machine |  |  |  | 5521 |  |  | 0 | 0 | No | Customer Experience | Building/Site | Facilities Site Work |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: WX404 09/22/25 - Sent an email to JKO and requested a proposal. -PL 09/22/25 - Recieved the quote back from JKO and placed it in the folder - PL | 2026-01-12 12:02:24
2025-03-31 08:55:42 | Abel Smith | 400 | 405 | Pump - Higher pressure pump for pressure guns | 2021 | Q3 | September | 5000 |  | Committed | 5345.34 | -345.34 |  | Planned maintenance | Equipment | high pressure pump | Wash Quality | Completed |  | EQ-0405-2025-1439 | 2025 | Low | No |  | 01/12/2026 - rusty: Committed per RP for Sept. | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Abel Smith | 400 | 405 | Wrap Core & Material (DS) | 2021 | Q2 | N/A | 4600 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Equipment | Wrap Brush | Wash Quality | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - unknown: Not a Capex Item. Project is R&M | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Abel Smith | 400 | 405 | Groundfus Pumps | 2021 | Q4 | N/A | 14500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Equipment | Hydroflex | Wash Quality | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - rusty: Abel- moved from July to October for reevaluation. store is fully functioning with "stick pumps". | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Abel Smith | 400 | 405 | Blower - Add Flash Blower | 2021 | Q3 | August | 3500 |  | Committed | 4259.3 | -759.3 |  | Planned maintenance | Equipment | Blowers | Wash Quality | Completed |  | EQ-0405-2025-1440 | 2025 | Low | No |  | 01/12/2026 - rusty: AS 8/12- Todd is currently getting quotes for electrical and an arch. We have the blower. New Total $3500 based on in stock mate | 2026-01-12 12:31:32
2025-11-07 10:26:29 | Ryan Payne | 400 | 405 | Conveyor Chain/Rollers |  |  |  | 13500 |  | Uncommitted | 0 | 0 | No | Prevent further damage | Equipment | Conveyor Chain |  | Deferred |  |  | 2026 | High | No |  | 01/12/2026 - unknown: most recent car count 266604. I think we should focus only on new rollers - WX405 09/24/25 - Sent an email to the site to request more information andf photos. -PL 09/29/25 - Sent a folow up email to the site and Ryan Payne. - PL 09/29/25 - Kyle Smith replied back and submitted photos. - PL 09/29/25 - Sent an email to Eric @ Vaughn and requested a quote - PL 09/30/25 - Recieved quote form Eric @ Vaughn.I have placed it in teh folder. - PL 02/25/2026 - Rusty Modesty: most recent car count 266604. I think we should focus only on new rollers - WX405 09/24/25 - Sent an email to the site to request more information andf photos. -PL 09/29/25 - Sent a folow up email to the site and Ryan Payne. - PL 09/29/25 - Kyle Smith replied back and submitted photos. - PL 09/29/25 - Sent an email to Eric @ Vaughn and requested a quote - PL 09/30/25 - Recieved quote form Eric @ Vaughn.I have placed it in teh folder. - PL | 2026-04-21 13:09:14
2025-11-07 10:26:29 | Ryan Payne | 400 | 405 | 20 GPM Grundfos Hydraflex Pump |  |  | May | 9000 |  | Committed | 273.9 | 8726.1 | No | Wash Quality | Equipment |  |  | Completed | 2026-04-27 | EQ-0405-2026-1798 | 2026 | Medium | Yes | Yes | 01/12/2026 - unknown: New Pump needed to improve chem quality 02/25/2026 - Rusty Modesty: New Pump needed to improve chem quality | 2026-06-01 12:32:08
2025-11-07 10:26:29 | Ryan Payne | 400 | 405 | Upgrade Whitewater Arch (Complete Arch) |  |  | October | 8000 |  | Committed | 0 | 0 | No | Customer Experience | Equipment | Building Facilities |  | Ordered |  | SI-0405-2026-2011 | 2026 | Low | No |  | 01/12/2026 - unknown: WX405 09/24/25 - Sent and email to the store asking for more information and photos. -PL 09/24/25 - Spoke to Marketing and they will not replace this arch until next year. Ryan stated there is nothing wrong with the arch, it just does not look like the rest. This will not be replaced. at this time - PL 02/17/2026 - Philip Loper: 02/17 - Sent an email to Terry @ Sonnys and requested a proposal. 02/24/2026 - Philip Loper: 02/23 - Terry returned the proposal, and it has been placed in the CAPEX folder. The cost is $6,598.53 with tax. Freight is an additional $1,500.00 | 2026-08-26 12:50:10
2025-11-07 10:26:29 | Ryan Payne | 400 | 405 | Vac Double Vacuum stall count with shade East side of current vac lane |  |  |  | 50000 |  |  | 0 | 0 | No | Customer Experience | Equipment | Vacuum |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: Competition coming in, 5k+ Membership counts and only xx amount of stalls; would need parking curbs as well WX405 | 2026-01-12 12:02:24
2025-11-07 10:26:29 | Ryan Payne | 400 | 406 | Tunnel Liners Entire Tunnel |  |  | April | 18500 |  | Committed | 17502.23 | 997.77 | No | Customer Experience | Building/Site | Facilities Site Work |  | Completed |  | FA-0406-2026-1728 | 2026 | Low | No |  | 01/12/2026 - unknown: WX406 02/16/2026 - Jonathan Blair: Went from 15,500 to 18,500 02/23/2026 - Mason Faltysek: Quoted 18500 Estimated cost 18500 Delta 0 04/02/2026 - Rusty Modesty: Currently in production and expected to ship out next week 04/23/2026 - Mason Faltysek: This is completed | 2026-04-23 14:28:23
2025-03-31 08:55:42 | Abel Smith | 400 | 407 | Prep Guns | 2020 | Q2 | April | 11000 |  | Committed | 17355.35 | -6355.35 |  | Planned maintenance | Equipment | Prep Pump | Wash Quality | Completed |  | EQ-0407-2025-1238 | 2025 | Low | No |  | 01/12/2026 - rusty: Completed Last week of July | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Phil Loper | 400 | 407 | Replace grill Brush with 24in Rockers | 2020 | Q4 | November | 13976.66 |  | Committed | 12265.1 | 1711.56 |  | Planned maintenance | Equipment | Wrap Brush | Wash Quality | Completed | 2025-10-31 | EQ-0407-2025-1525 | 2025 | Low | No |  | 01/12/2026 - Philip Loper: 10-31-25 - I havereached out to MCWW and awaiting a shipment date. -PL Abel- Pushed to end of year, if not 2026. Wash quality is good from Maintenance standpoint. Will collaborate with Ops RD in the | 2026-01-12 12:31:32
2025-03-31 08:55:42 | David Carreon | 400 | 407 | Camera - Inspection Camera Arch Install | 2020 | Q3 | July | 3000 |  | Committed | 7264.51 | -4264.51 |  | Planned maintenance | IT | Camera | Safety | Completed |  | EQ-0407-2025-1401 | 2025 | Low | No |  | 01/12/2026 - rusty: needed | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Mason Faltysek | 400 | 407 | Lighting - Tower Lights | 2020 | Q3 | N/A | 9500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Building Facilities | Safety | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-08-20 11:27:57 | Abel Smith | 400 | 407 | Addition of Rocker Brush |  | Q4 | N/A | 13000 |  | Uncommitted | 0 | 0 | No | Planned maintenance | Equipment | Wrap Brush | Customer Experience | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - rusty: Duplicate | 2026-01-12 12:31:32
2025-11-07 10:26:29 | Ryan Payne | 400 | 407 | Belt Replace |  |  | May | 50000 |  | Committed | 49119.65 | 880.35 | No | Customer Experience | Equipment | Conveyor Belt |  | Completed |  | EQ-0407-2026-1750 | 2026 | Medium | Yes |  | 01/12/2026 - unknown: Budget was reduced from $70,000 to $50,000 based on site inspection by Todd Thacker and historic cost RM 10/03/25 - This is for sprockets and drives. - PL 02/19/2026 - Philip Loper: 02/19 - Sent an email to Todd, Rusty and Jonathan to request additional information on this project. 02/19/2026 - Philip Loper: 02/19 - Todd Thacker has replied with a detailed list. This has been placed in the CAPEX folder. The cost is $47,086.99 05/19/2026 - Rusty Modesty: Materials are scheduled to arrive the week of 5/25 with installation in the same week. | 2026-06-01 12:33:06
2025-11-07 10:26:29 | Ryan Payne | 400 | 407 | Replacing Mizer with Aqualab (2) Aqua Lab 3 Panels |  |  |  | 20000 |  | Uncommitted | 0 | 0 | No | Wash Quality | Equipment |  |  | Deferred |  |  | 2026 | High | Yes |  | 01/12/2026 - unknown: WX407 09/24/25 - Sent an email to Terry @ Sonnys for a proposal. -PL 0925/25 - Recieved proposal from Terry. Freight is 1K -PL 10/03/25 - This is just for the panels. The idea is to reuse the current pumps - PL 02/17/2026 - Philip Loper: 2/17 - Sent an email to Terry at Sonnys and requested a proposal. 02/24/2026 - Philip Loper: 02/23 - Terry returned the proposal, and it has been placed in the CAPEX folder. Cost with tax is $30,886.03. Freight is an additional $700.00 | 2026-04-21 13:09:43
2025-11-07 10:26:29 | Ryan Payne | 400 | 407 | Compressor Install 1 additional |  |  | February | 6500 |  | Committed | 5668.38 | 831.62 | No | Wash Quality | Equipment | Compressors Replacement |  | Completed | 2026-02-02 | EQ-0407-2026-1650 | 2026 | Medium | No |  | 02/05/2026 - Philip Loper: This compressor has been ordered on 02/02/26. | 2026-02-20 12:56:04
2025-11-07 10:26:29 | Ryan Payne | 400 | 407 | Recaulk Facility (Foundation) |  |  | May | 3500 |  | Committed | 0 | 0 | No | Prevent further damage | Building/Site | Facilities Site Work |  | Completed |  | FA-0407-2026-1784 | 2026 | Low | No |  | 01/12/2026 - unknown: WX407 02/16/2026 - Jonathan Blair: WX407 02/18/2026 - Rusty Modesty: Updated pricing from $10,000 to $3,500. 03/13/2026 - Mason Faltysek: Renascent will be out next week 3/16 05/05/2026 - Mason Faltysek: received estimate and awaiting approval 05/07/2026 - Mason Faltysek: Expected to be completed 5/7 05/12/2026 - Mason Faltysek: This has been completed | 2026-05-18 15:02:41
2025-11-07 10:26:29 | Ryan Payne | 400 | 407 | Tower Lights at Exit of Tunnel |  |  |  | 10000 |  | Uncommitted | 0 | 0 | No | Customer Experience | Equipment | Building Facilities |  | Deferred |  |  | 2026 | High | No |  | 01/12/2026 - unknown: 2025 WX407 02/25/2026 - Rusty Modesty: 2025 WX407 | 2026-04-21 13:10:17
2026-04-10 18:57:51 | Andrew Folse | 400 | 407 | Grand Entry Arch |  |  | October | 8000 |  | Committed | 0 | 0 | No | Planned maintenance | Equipment | marketing/signage |  | Ordered |  | SI-0407-2026-2012 |  | Low | No |  | 04/27/2026 - Rusty Modesty: Grand entry arch is damaged and needs to be replaced per Jonathan 04/27/2026 - Jonathan Blair: Grand entry arch is damaged and needs to be replaced per Jonathan | 2026-08-26 12:50:35
2025-03-31 08:55:42 | Abel Smith | 400 | 408 | Prep Gun | 2021 | Q1 | May | 11000 |  | Committed | 17191.24 | -6191.24 |  | Planned maintenance | Equipment | Prep Pump | Wash Quality | Completed |  | EQ-0408-2025-1239 | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Mason Faltysek | 400 | 408 | Lighting - Tower Lights | 2021 | Q3 | N/A | 9500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Building Facilities | Safety | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-08-20 11:29:17 | Brandy Fruia | 400 | 408 | Canopy |  | Q4 | September | 18000 |  | Committed | 17990.07 | 9.93 | No | Planned maintenance | Building/Site | Building Facilities | Customer Experience | Completed |  | FA-0408-2025-1456 | 2025 | Low | No |  | 01/12/2026 - fruia_1: approval from Rusty and Ryan. Adjusted price to reflect replacing canopies and support braces. | 2026-01-12 12:31:32
2025-11-07 10:26:29 | Ryan Payne | 400 | 408 | Equipment Mitters & Small Rocker for beginning of tunnel |  |  |  | 35000 |  |  | 0 | 0 | No | Wash Quality | Equipment |  |  | 2026 Request |  |  | 2026 | Medium | No |  | 01/12/2026 - unknown: WX408 09/24/25 - Sent an email to the store to request photos. - PL 09/29/25 -- Sent a follow up email to the site to request information. - PL 09/29/25 - Luke replied back and included photos. I have placed them in the folder. -PL 09/30/25 - Sent an email to Jody @ TWW and requested a proposal. - PL 10/06/25 - The estimate was returned. The price that I have posted is for Equipment, Freight and tax NOT INSTALL - PL 02/17/2026 - Philip Loper: 02/17 - Sent an email to Jody @ MCWW and requesated a proposal. 02/18/2026 - Philip Loper: MCWW returned a proposal for Mitter only as what was spec'd on Rusty's sheet for $13,997.53. This does not include tax | 2026-01-12 12:01:41
2025-11-07 10:26:29 | Ryan Payne | 400 | 408 | Roof Replacement |  |  | April | 28000 |  | Committed | 27062.5 | 937.5 | No | Prevent further damage | Building/Site | Facilities Site Work |  | Completed |  | FA-0408-2026-1732 | 2026 | Medium | Yes |  | 01/12/2026 - mason: Bid received from renascent pricing updated to reflect bid 11/26 MF 02/16/2026 - Jonathan Blair: Bid received from renascent pricing updated to reflect bid 11/26 MF 02/18/2026 - Rusty Modesty: Adjusted Deployment to June 02/23/2026 - Mason Faltysek: Quote 27062.50 Estimated Cost 28000 Delta 937.50 Delta 0 03/13/2026 - Mason Faltysek: Material is on order expected to kickoff beginning of April 03/23/2026 - Mason Faltysek: This has started 3/20 04/23/2026 - Mason Faltysek: This is completed | 2026-04-23 14:29:21
2025-11-07 10:26:29 | Ryan Payne | 400 | 408 | Replacing Mizer with Aqualab (2) Aqua Lab 3 Panels |  |  |  | 20000 |  | Uncommitted | 0 | 0 | No | Wash Quality | Equipment |  |  | Deferred |  |  | 2026 | High | Yes |  | 01/12/2026 - unknown: WX408 09/24/25 - Sent an email to Terry @ Sonnys for a proposal. -PL 0925/25 - Recieved proposal from Terry. Freight is 1K -PL 10/03/25 - This is just for the panels. The idea is to reuse the current pumps - PL 02/17/2026 - Philip Loper: 02/17 - Sent an email to Terry @ Sonnys and requested a proposal. 03/06/2026 - Philip Loper: 03/05 - Received the proposal from Terry . This has been placed in the CAPEX folder. Cost for 2 panels and 2 pumps, no freight, is $30,585.57 | 2026-04-21 13:10:41
2025-11-07 10:26:29 | Ryan Payne | 400 | 408 | Compressor Install 1 additional |  |  | August | 4000 |  | Committed | 0 | 0 | No | Wash Quality | Equipment | Compressors Replacement |  | Completed |  | EQ-0408-2026-1921 | 2026 | Medium | No |  | 01/12/2026 - unknown: WX408 02/17/2026 - Philip Loper: 02/17 - Sent an email to the team asking for additional information. 02/18/2026 - Philip Loper: 2/18 - Sent an email to the vendor for a proposal. 02/18/2026 - Philip Loper: 02/18 - Green Valley returned the proposal and it has been placed inthe capex folder. 02/25/2026 - Rusty Modesty: WX408 07/27/2026 - Andrew Folse: Compressor ordered from Green Valley Compressor 08/10/2026 - Andrew Folse: Parts onsite as of 8/7 08/20/2026 - Andrew Folse: Install week of 8/24 | 2026-09-15 16:07:24
2025-11-07 10:26:29 | Ryan Payne | 400 | 408 | Canopy over Stand Alone Vacs |  |  | May | 33500 |  | Uncommitted | 0 | 0 | No | Customer Experience | Building/Site | Facilities Site Work |  | Deferred |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: 02/18/2026 - Rusty Modesty: Adjusted to May deployment 02/18/2026 - Rusty Modesty: Current sonnys canopy stalls are $6,700 per stall + freight and install. Estimate total $33,500 + Freight and install. | 2026-06-01 12:36:20
2025-11-07 10:26:29 | Ryan Payne | 400 | 408 | Tower Lights at Exit of Tunnel |  |  |  | 10000 |  | Uncommitted | 0 | 0 | No | Customer Experience | Equipment | Building Facilities |  | Deferred |  |  | 2026 | High | No |  | 01/12/2026 - unknown: WX408 02/25/2026 - Rusty Modesty: WX408 | 2026-04-21 13:11:13
2025-03-31 08:55:42 | Abel Smith | 400 | 409 | Prep Gun | 2021 | Q1 | N/A | 11000 |  | Committed | 15085.82 | -4085.82 |  | Planned maintenance | Equipment | Prep Pump | Wash Quality | Completed |  | EQ-0409-2025-1240 | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Phil Loper | 400 | 409 | Signage - Entrance Arch Right Side | 2021 | Q4 | N/A | 3000 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Equipment | marketing/signage | Customer Experience | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - phil: 09/16/25 - This will not be CAPEX. Ryan Payne has asked this to be moved to R&M due to the cost of $1,900. 09/08/25 -The proposal for Equipment and installation has been given to Gregg and Rusty. Waiting on approval from Rusty - PLOPER 04/22/2026 - Rusty Modesty: 09/16/25 - This will not be CAPEX. Ryan Payne has asked this to be moved to R&M due to the cost of $1,900. 09/08/25 -The proposal for Equipment and installation has been given to Gregg and Rusty. Waiting on approval from Rusty - PLOPER | 2026-04-22 16:18:08
2025-03-31 08:55:42 | Abel Smith | 400 | 409 | Wear Plates | 2021 | Q4 | October | 25000 |  | Committed | 38368.37 | -13368.37 |  | Planned maintenance | Equipment | Conveyor Belt | Wash Quality | Completed |  | EQ-0409-2025-1512 | 2025 | Low | No |  | 01/12/2026 - Abel Smith: Rusty- 7/1 Updated estimated cost from 35k to 25k. Abel- committed. Will reassess in October per Todd. Material expected mid november. | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Mason Faltysek | 400 | 409 | Parking lot restripe | 2021 | Q3 | N/A | 6500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Equipment | Facilities Site Work | Customer Experience | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - unknown: not needed | 2026-01-12 12:31:32
2025-08-20 11:30:34 | Mason faltysek | 400 | 409 | Replacement Light Fixtures (Interior) |  | Q4 | N/A | 4000 |  | Uncommitted | 0 | 0 | No | Planned maintenance | Building/Site | Building Facilities | Customer Experience | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - mason: Duplicate 04/22/2026 - Andrew Folse: Duplicate | 2026-04-22 16:18:10
2025-08-20 11:56:55 | Mason faltysek | 400 | 409 | Replacement Light Fixtures (Interior) |  | Q4 | October | 4000 |  | Committed | 0 | 0 | No | Planned maintenance | Building/Site | Technology | Customer Experience | Completed |  |  | 2025 | Low | No |  | 01/12/2026 - gregg: Possibly not hitting CAPEX Threshold. RM 10/20 | 2026-01-12 12:31:32
2025-11-07 10:26:29 | Ryan Payne | 400 | 409 | Equipment Mitters & Small Rocker for beginning of tunnel |  |  |  | 35000 |  |  | 0 | 0 | No | Wash Quality | Equipment |  |  | 2026 Request |  |  | 2026 | Medium | Yes |  | 01/12/2026 - unknown: WX409 10/06/25 - The estimate was returned. The price that I have posted is for Equipment, Freight and tax NOT INSTALL - PL 02/18/2026 - Philip Loper: 02/18 - Sent an email to Jody @ MCW and requested a proposal. 03/03/2026 - Philip Loper: Proposal was returned for a Mitter at the front of the tunnel This has been placed in the CAPEX folder. Cost is $13,997.53 form the mitter alone. 03/03/2026 - Philip Loper: I will send another request for Rockers. | 2026-03-03 14:15:55
2025-11-07 10:26:29 | Ryan Payne | 400 | 409 | Replacing Mizer with Aqualab (2) Aqua Lab 3 Panels |  |  |  | 20000 |  | Uncommitted | 0 | 0 | No | Wash Quality | Equipment |  |  | Deferred |  |  | 2026 | High | Yes |  | 01/12/2026 - unknown: WX409 09/24/25 - Sent an email to Terry @ Sonnys for a proposal. -PL 0925/25 - Recieved proposal from Terry. Freight is 1K -PL 10/03/25 - This is just for the panels. The idea is to reuse the current pumps - PL 02/19/2026 - Philip Loper: 02/19 - Sent an email to Terry @ Sonnys and requested a proposal. 02/25/2026 - Rusty Modesty: WX409 09/24/25 - Sent an email to Terry @ Sonnys for a proposal. -PL 0925/25 - Recieved proposal from Terry. Freight is 1K -PL 10/03/25 - This is just for the panels. The idea is to reuse the current pumps - PL 03/06/2026 - Philip Loper: 03/05 - Proposal returned and placed in the CAPEX folder. Cost before freight is $30,585.56 | 2026-04-21 13:11:33
2025-11-07 10:26:29 | Ryan Payne | 400 | 409 | Swap camera system to VAST |  |  |  | 2500 |  |  | 0 | 0 | No | Safety | IT | Camera |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: WX409 02/24/2026 - Rusty Modesty: Moved from Equipment to IT. | 2026-02-24 12:46:28
2025-03-31 08:55:42 | Abel Smith | 400 | 410 | Prep Guns | 2022 | Q2 | April | 11000 |  | Committed | 14776.76 | -3776.76 |  | Planned maintenance | Equipment | Prep Pump | Wash Quality | Completed |  | EQ-0410-2025-1241 | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Abel Smith | 400 | 410 | Wear Plates | 2022 | Q2 | June | 32000 |  | Committed | 21569.04 | 10430.96 |  | Planned maintenance | Equipment | Conveyor Belt | Wash Quality | Completed |  | EQ-0410-2025-1337 | 2025 | Low | No |  | 01/12/2026 - unknown: Confirmed Needed 5/20 | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Mason Faltysek | 400 | 410 | Parking lot restripe | 2022 | Q3 | N/A | 6500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Facilities Site Work | Customer Experience | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Phil Loper | 400 | 410 | Aqua - LabAdd 2nd Aqua lab | 2022 | Q4 | N/A | 6200 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Equipment | Hydroflex | Wash Quality | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-11-07 10:26:29 | Ryan Payne | 400 | 410 | Aqualab instead of Dosatrons (1) Aqualab 3 Panel |  |  |  | 15000 |  |  | 0 | 0 | No | Wash Quality | Equipment |  |  | 2026 Request |  |  | 2026 | Medium | Yes |  | 01/12/2026 - unknown: 2025 WX410 09/24/25 - Sent an email to Terry @ Sonnys for a proposal. -PL 0925/25 - Recieved proposal from Terry. Freight is 1K -PL (Also need proposal from Dubois-RM) 10/03/25 - Sent 2 emails to Brian Lonsdale to ask for information and no reply. I have made an educated guess on this. - PL 02/19/2026 - Philip Loper: 02/19 - Sent an email to Terry @ Sonnys requesting a proposal 03/06/2026 - Philip Loper: 03/05 - Proposal returned and placed in the CAPEX folder. Cost without freight is $15,130.23 | 2026-03-06 11:36:41
2025-11-07 10:26:29 | Ryan Payne | 400 | 410 | Cameras |  |  | March | 5500 |  | Committed | 0 | 0 | No | Wash Quality | IT | Camera |  | Completed | 2026-01-29 | EQ-0410-2026-1685 | 2026 | Medium | No |  | 01/12/2026 - unknown: WX410 01/28/2026 - Jonathan Blair: WX410 02/17/2026 - David Carreon: Camera equipmanet was ordered as well as camera poles, poles were ready as of 2/12 This is scheduled for 2/25 | 2026-04-07 14:42:22
2025-11-07 10:26:29 | Ryan Payne | 400 | 412 | spare compressor region |  |  | April | 6500 |  | Committed | 6157.28 | 342.72 | No | Prevent further damage | Equipment | Compressors Replacement |  | Completed |  | EQ-0412-2026-1686 | 2026 | High | Yes |  | 01/12/2026 - unknown: 02/18/2026 - Philip Loper: 02/18 - Sent an email to the team asking for additional information. 03/24/2026 - Philip Loper: Sent a follow up email to Rusty on 03/24 and asked: "Following up with this? I asked you if your team could angle this, since it is a repair, not a full replacement?" 03/27/2026 - Philip Loper: Rusty emailed back Phil and stated, "Thanks, Phil. Yes, we will handle this head. " | 2026-05-18 14:29:10
2025-11-07 10:26:29 | Ryan Payne | 400 | 412 | DRB conversion (TCS Conversion) |  |  |  | 46000 |  |  | 0 | 0 | No | Prevent further damage | IT | Technology |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: 2025 WX412 | 2026-01-12 12:02:24
2025-11-07 10:26:29 | Ryan Payne | 400 | 412 | Repaint Red vacuum booms |  |  |  | 15000 |  |  | 0 | 0 | No | Customer Experience | Equipment |  |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: WX412 | 2026-01-12 12:02:24
2026-04-14 09:51:06 | Andrew Folse | 400 | 412 | Water Softener |  |  | August | 4500 |  | Committed | 4313.82 | 186.18 | No | Planned maintenance | Equipment | Water Softener | Wash Quality | Completed |  | EQ-0412-2026-1923 |  | Low | No | No | 04/27/2026 - Jonathan Blair: Water softener head leaking. System is bypassed and site is on hard water. 07/27/2026 - Andrew Folse: Waiting on vendor scheduling for install date 08/10/2026 - Andrew Folse: Trying to schedule with vendor. He is working on another capex for us today. Will update with the install date when available. | 2026-08-20 12:30:31
2026-02-24 12:36:52 | Rusty Modesty | 400 | 414 | Chain/Roller Rebuild |  |  | November | 0 | 13000 | Committed | 0 | 0 | No | Planned maintenance | Equipment | Conveyor Chain | Customer Experience | In-Process |  | EQ-0414-2026-2022 |  | High | No |  | 02/24/2026 - Rusty Modesty: Project addition 2/26 02/24/2026 - Rusty Modesty: Marked Committed. Nov | 2026-09-14 14:48:46
2025-03-31 08:55:42 | Gary Kingsbury | 500 | 501 | Exit gate - for Vacuum Area | 2019 | Q3 | N/A | 6500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Equipment | XPT | Safety | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - unknown: Not Needed. Copy over from 303 | 2026-01-12 12:31:32
2025-11-07 10:36:13 | Lauren Fine | 500 | 501 | Seal and restripe lot |  |  |  | 7500 |  |  | 0 | 0 | No | Customer Experience | Building/Site | Building Facilities |  | Deferred |  |  | 2026 | Low | No |  |  | 2026-01-22 04:02:42
2025-11-07 10:36:13 | Lauren Fine | 500 | 502 | Replacement Compressor Pump |  |  | May | 8500 |  | Committed | 2902.07 | 5597.93 | No | Prevent further damage | Equipment | Compressors Replacement | Prevent further damage | Completed | 2026-04-17 | EQ-0502-2026-1748 | 2026 | Medium | Yes | No | 04/22/2026 - Gary Kingsbury: Parts ordered on 4/17 08/20/2026 - Gary Kingsbury: Builder to take care of free of charge. Will advise if more work needed. 09/14/2026 - Gary Kingsbury: Maintenace repaired in house | 2026-09-14 12:37:51
2025-11-07 10:36:13 | Lauren Fine | 500 | 502 | Drainage at exit |  |  | October | 10000 |  | Committed | 0 | 0 | No | Customer Experience | Building/Site | Facilities Site Work |  | Deferred |  |  | 2026 | Low | No |  | 08/24/2026 - Gary Kingsbury: Builder to take care of free of charge | 2026-08-24 11:05:56
2025-11-07 10:36:13 | Lauren Fine | 500 | 502 | Seal and restripe lot |  |  |  | 7500 |  |  | 0 | 0 | No | Customer Experience | Building/Site | Building Facilities |  | Deferred |  |  | 2026 | Low | No |  |  | 2026-01-22 04:03:11
2025-11-07 10:36:13 | Lauren Fine | 500 | 502 | Replace tunnel heater |  |  | January | 12000 |  |  | 0 | 0 | No | Prevent further damage | Building/Site | Facilities Site Work |  | Deferred |  |  | 2026 | High | No |  | 01/12/2026 - Bradley Osborne: This is for 1 heater. 10/15/25 - Mason needs to validate cost Greg B says defer entirely | 2026-01-12 12:00:08
2025-03-31 08:55:42 | Mason Faltysek | 500 | 503 | Parking lot restripe | 2022 | Q3 | N/A | 6500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Facilities Site Work | Customer Experience | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Gary Kingsbury | 500 | 504 | Chain and rollers | 2021 | Q1 | N/A | 12000 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Equipment | chain/roller | Wash Quality | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - unknown: Completed and paid for in 2024 | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Gary Kingsbury | 500 | 504 | Garage door system | 2021 | Q2 | N/A | 14000 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Building Facilities | Safety | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - unknown: Deferred by Brad | 2026-01-12 12:31:32
2025-11-07 10:36:13 | Lauren Fine | 500 | 504 | SAL lane |  |  | September | 8000 | 9000 | Committed | 0 | 0 | No | Customer Experience | IT | Technology | Customer Experience | In-Process |  | EQ-0504-2026-1965 | 2026 | Low | No | No | 01/12/2026 - Bradley Osborne: 504 is above 3000 members. 04/16/2026 - David Carreon: 504 is above 3000 members. 06/15/2026 - David Carreon: This is pending the results of the fabricators, if we can use a 3rd party for the enclosure we could save up at least $3k. I will submit the request once I have an answer by the end of the month | 2026-08-17 16:58:44
2025-11-07 10:36:13 | Lauren Fine | 500 | 504 | Seal and restripe lot |  |  |  | 7500 |  |  | 0 | 0 | No | Customer Experience | Building/Site | Building Facilities |  | Deferred |  |  | 2026 | Low | No |  |  | 2026-01-22 04:03:28
2026-07-28 10:10:58 | Gary Kingsbury | 500 | 504 | Garage Door |  | Q4 | October | 15000 |  | Committed | 0 | 0 | No | Planned maintenance | Equipment | Building Facilities | Safety | Ordered |  | FA-0504-2026-2013 |  | High | Yes | No | 08/26/2026 - Gary Kingsbury: Quote received with overnight work $13,998 | 2026-08-27 12:56:42
2025-11-07 10:36:13 | Lauren Fine | 500 | 505 | SAL lane |  |  | September | 8000 | 9000 | Committed | 0 | 0 | No | Customer Experience | IT | Technology | Customer Experience | In-Process |  | EQ-0505-2026-1966 | 2026 | Low | Yes | No | 01/12/2026 - Bradley Osborne: 3000 Members is when we add these 05/14/2026 - David Carreon: 3000 Members is when we add these | 2026-08-17 16:59:16
2025-11-07 10:36:13 | Lauren Fine | 500 | 505 | Seal and restripe lot |  |  |  | 7500 |  |  | 0 | 0 | No | Customer Experience | Building/Site | Building Facilities |  | Deferred |  |  | 2026 | Low | No |  |  | 2026-01-22 04:04:50
2025-03-31 08:55:42 | Gary Kingsbury | 500 | 506 | Canopy above XPT | 2014 | Q2 | May | 7500 |  | Committed | 0 | 0 |  | Planned maintenance | Building/Site | XPT | Customer Experience | Completed | 2025-05-14 | EQ-506-2025-1330 | 2025 | Low | No | No |  | 2026-09-16 08:07:30
2025-03-31 08:55:42 | Mason Faltysek | 500 | 506 | Concrete at Tunnel Exit and metal Exit Plate | 2014 | Q3 | October | 9500 |  | Committed | 6520.39 | 2979.61 |  | Planned maintenance | Building/Site | Facilities Site Work | Prevent further damage | Completed |  | FA-0506-2025-1528 | 2025 | Low | No |  | 01/12/2026 - Mason Faltysek: Demo Existing concrete, remove existing drain, set new catch basin, and pour back. | 2026-01-12 12:31:32
2025-11-07 10:36:13 | Lauren Fine | 500 | 506 | Chain and rollers |  |  | June | 15500 |  | Committed | 12401.5 | 3098.5 | No | Prevent further damage | Equipment | Conveyor Chain | Prevent further damage | Completed | 2026-05-28 | EQ-0506-2026-1820 | 2026 | High | Yes | No | 02/18/2026 - Philip Loper: 02/18 - Sent an email to Gary and team requesting additional information. 02/25/2026 - Philip Loper: 02/25 - Sent an email to Eric @ Vaughn and requested a proposal. 02/26/2026 - Philip Loper: 02/26 - Received the proposal from Eric @ Vaughn. It has been placed in the folder. Total tost for Chain, Rollers and Sprockets is $8,606.22 06/18/2026 - Gary Kingsbury: Completed 6/18/26 | 2026-06-18 13:49:10
2025-03-31 08:55:42 | Gary Kingsbury | 500 | 507 | Canopy above SAL lane | 2017 | Q2 | May | 7500 |  | Committed | 8694.57 | -1194.57 |  | Planned maintenance | Building/Site | XPT | Customer Experience | Completed | 2025-05-14 | EQ-0507-2025-1331 | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-11-07 10:36:13 | Lauren Fine | 500 | 507 | Chain and Roller Conveyor Rebuild |  |  | January | 13500 |  | Committed | 13582.51 | -82.51 | No | Prevent further damage | Equipment | Conveyor Chain |  | Completed | 2026-01-06 | EQ-0507-2026-1620 | 2026 | High | No |  |  | 2026-02-20 09:36:14
2025-11-07 10:36:13 | Lauren Fine | 500 | 507 | Building painting |  |  | June | 24500 |  |  | 0 | 0 | No | Customer Experience | Building/Site | Building Facilities |  | Deferred |  |  | 2026 | Medium | No |  | 01/12/2026 - Mason Faltysek: Received Estimate -MF 07/24/2026 - Gary Kingsbury: Received Estimate -MF | 2026-07-24 11:11:26
2025-03-31 08:55:42 | David Carreon | 500 | 508 | Cameras in the tunnel and in the parking lot | 2016 | Q2 | N/A | 6500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | IT | Camera | Safety | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - unknown: budget looks flipped with 704 | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Gary Kingsbury | 500 | 508 | Canopy above SAL lane | 2016 | Q2 | May | 7500 |  | Committed | 9087.53 | -1587.53 |  | Planned maintenance | Building/Site | XPT | Customer Experience | Completed | 2025-05-14 | EQ-0508-2025-1332 | 2025 | Low | No |  | 01/12/2026 - unknown: Project completed 6/26/2025 | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Mason Faltysek | 500 | 508 | HVAC - Ventilation for the tunnel | 2016 | Q2 | June | 16000 |  | Committed | 15005 | 995 |  | Planned maintenance | Building/Site | Building Facilities | Safety | Completed |  | FA-0508-2025-1398 | 2025 | Low | No |  | 01/12/2026 - rusty: RM Updated per Haglage Quote. Expected completion week of 10/6 | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Gary Kingsbury | 500 | 508 | Increase size of vac producer | 2016 | Q2 | N/A | 20000 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Equipment | Vacuum | Customer Experience | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - rusty: Deferred for 2026 | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Mason Faltysek | 500 | 508 | Signage - Entrance signage | 2016 | Q2 | N/A | 14000 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Equipment | marketing/signage | Customer Experience | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Mason Faltysek | 500 | 508 | Signage - Grand Entry Arch | 2016 | Q2 | N/A | 14000 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Equipment | marketing/signage | Customer Experience | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Mason Faltysek | 500 | 508 | Building improvement - Close off area in Exit of Wash Bay | 2016 | Q3 | August | 5500 |  | Committed | 6318 | -818 |  | Planned maintenance | Building/Site | Building Facilities | Prevent further damage | Completed |  | FA-0508-2025-1444 | 2025 | Low | No |  | 01/12/2026 - mason: Brad Wants to move up | 2026-01-12 11:59:20
2025-03-31 08:55:42 | Gary Kingsbury | 500 | 508 | Chain | 2016 | Q4 | December | 12000 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Equipment | chain/roller | Wash Quality | Deferred |  |  | 2025 | Low | No | No | 01/12/2026 - unknown: Chain was replaced 12/1/21 391K Cars Inspected 6/25 07/28/2026 - Gary Kingsbury: Chain was replaced 12/1/21 391K Cars Inspected 6/25 | 2026-08-14 07:27:23
2025-08-20 12:14:08 | Mason faltysek | 500 | 508 | Tunnel Heater / Gas Conversion |  | Q4 | November | 8000 |  | Uncommitted | 0 | 0 | No | Planned maintenance | Building/Site | Building Facilities | Safety | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - rusty: Pushed to 2026 with larger budget | 2026-01-12 12:31:32
2025-11-07 10:36:13 | Lauren Fine | 500 | 508 | Additional Air compressor |  |  | June | 8500 |  | Committed | 9628.61 | -1128.61 | No | Customer Experience | Equipment | Compressors Replacement |  | Completed | 2026-05-28 | EQ-0508-2026-1822 | 2026 | Medium | Yes | No | 02/24/2026 - Philip Loper: 02/24 - Sent an email to Chris @ Aircentric and requested a proposal. 02/25/2026 - Philip Loper: 02/25 - Proposal returned and placed in the CAPEX folder. Cost is $7,744 before tax and installation cost. 05/28/2026 - Gary Kingsbury: Ships on 6/18 | 2026-06-24 16:45:51
2025-11-07 10:36:13 | Lauren Fine | 500 | 508 | Boiler/Heat |  |  | January | 20000 |  | Committed | 34646.35 | -14646.35 | No | Safety | Equipment |  | Safety | Completed |  | EQ-0508-2026-1658 | 2026 | High | No |  | 01/29/2026 - Mason Faltysek: Electrical work has begun. Heaters expected to be installed by end of next week 2/2 02/11/2026 - Mason Faltysek: Heaters expected to arrive 2/12 02/27/2026 - Gary Kingsbury: Heaters have been installed. Project finalization to be finished mid March per contractor. | 2026-03-20 06:59:50
2025-11-07 10:36:13 | Lauren Fine | 500 | 508 | Rhino Mat Cleaner Repair/Replace |  |  | July | 6000 |  | Uncommitted | 0 | 0 | No | Customer Experience | Building/Site | Facilities Site Work |  | Deferred |  |  | 2026 | Low | No |  | 07/22/2026 - Gary Kingsbury: Adding wash tub to replace Rhino Mat. Cost below capex threshold at $1700 | 2026-07-22 08:10:01
2025-11-07 10:36:13 | Lauren Fine | 500 | 508 | Vacuum upgrade |  |  | May | 25000 |  |  | 0 | 0 | No | Customer Experience | Equipment | Vacuum |  | Deferred |  |  | 2026 | Low | No |  |  | 2026-07-24 11:11:49
2025-11-07 10:36:13 | Lauren Fine | 500 | 508 | Chain and Roller Conveyor Rebuild |  |  | December | 15500 | 14000 | Committed | 13965.47 | 34.53 | No | Prevent further damage | Equipment | Conveyor Chain | Customer Experience | Completed | 2026-09-07 | EQ-0508-2026-1990 | 2026 | High | Yes | No | 02/18/2026 - Philip Loper: 02/18 - Sent an email to Gary and team requesting additional information. 02/25/2026 - Philip Loper: 02/25 - Sent an email to Eric @ Vaughn and requested a proposal. 02/26/2026 - Philip Loper: 02/26 - Proposal was returned from Eric @ Vaughn. The cost for the chain and roller is $9,307.75. Freight is not included. 09/15/2026 - Gary Kingsbury: Completed 9/16 | 2026-09-15 20:08:21
2025-11-07 10:36:13 | Lauren Fine | 500 | 509 | Chain and Roller Conveyor Rebuild |  |  | October | 15500 | 13750 | Committed | 2170.91 | 11579.09 | No | Prevent further damage | Equipment | Conveyor Chain | Customer Experience | Completed | 2026-08-17 | EQ-0509-2026-1955 | 2026 | High | Yes | No | 01/12/2026 - Bradley Osborne: 233,700 Cars on current chain 02/16/2026 - Gary Kingsbury: 233,700 Cars on current chain 02/18/2026 - Philip Loper: 02/18 - Sent an email to Gary and team requesting additional information. 02/25/2026 - Philip Loper: 02/25 - Sent an email to Eric @ Vaughn and requested a proposal. 03/02/2026 - Gary Kingsbury: Moved to Q4 05/29/2026 - Gary Kingsbury: Changed from 516 due to wear of chain at 509. 386,000 Cars on current chain 09/15/2026 - Gary Kingsbury: Completed 9/15 | 2026-09-15 20:09:20
2025-03-31 08:55:42 | Gary Kingsbury | 500 | 510 | Water Softener | 2021 | Q1 | April | 14000 |  | Committed | 11552.18 | 2447.82 |  | Planned maintenance | Equipment | Water Softener | Wash Quality | Completed |  | EQ-0510-2025-1264 | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-08-20 12:16:51 | Mason faltysek | 500 | 510 | Entrance Tunnel Heater |  | Q4 | October | 8000 |  | Uncommitted | 9908 | -1908 | No | Planned maintenance | Building/Site | Building Facilities | Safety | Deferred |  | EQ-0510-2025-1581 | 2025 | High | No |  | 09/21/2026 - Gary Kingsbury: Quote from Wellman serrvices cane in at $4,865.00 | 2026-09-21 14:52:33
2025-11-07 10:36:13 | Lauren Fine | 500 | 510 | Chain and Roller Conveyor Rebuild |  |  | May | 15500 | 16750 | Committed | 14749.33 | 2000.67 | No | Prevent further damage | Equipment | Conveyor Chain | Prevent further damage | Completed | 2026-04-14 | EQ-0510-2026-1751 | 2026 | High | Yes | No | 01/12/2026 - Bradley Osborne: 423,000 Cars on current chain 02/16/2026 - Gary Kingsbury: 423,000 Cars on current chain 02/18/2026 - Philip Loper: 02/18 - Sent an email to Gary and team requesting additional information. 02/25/2026 - Philip Loper: 02/25 - Sent an email to Eric @ Vaughn and requested a proposal. 03/04/2026 - Philip Loper: 02/26 - Eric Replied back to the proposal and this has been placed in the CAPEX folder. Total Cost for Chain and Rollers is $6,684.80 03/12/2026 - Gary Kingsbury: This needs a Heco pulse conversion added 04/13/2026 - Gary Kingsbury: Quotes higher than original estimate 05/15/2026 - Gary Kingsbury: Completed 4/14 | 2026-05-15 07:32:51
2025-11-07 10:36:13 | Lauren Fine | 500 | 510 | Replace old Superior Dryers with Sonnys |  |  | July | 65000 |  |  | 0 | 0 | No | Wash Quality | Equipment | Blowers |  | Deferred |  |  | 2026 | Low | No |  |  | 2026-02-16 10:42:24
2026-09-21 14:57:50 | Gary Kingsbury | 500 | 510 | Tunnel Entrance Heater | 2026 |  | October | 4865 |  | Committed | 0 | 0 | No | Planned maintenance | Building/Site | Building Facilities | Safety | Ordered | 2026-09-22 | FA-0510-2026-2062 |  | High | Yes | No |  | 2026-09-22 06:20:36
2025-03-31 08:55:42 | Phil Loper | 500 | 511 | Conveyor replacement | 2017 | Q3 | June | 100000 |  | Committed | 94970.58 | 5029.42 |  | Planned maintenance | Equipment | Conveyor Chain | Wash Quality | Completed |  | EQ-0511-2025-1340 | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-11-07 10:36:13 | Lauren Fine | 500 | 511 | Tunnel exit hard door |  |  | September | 14000 | 10077 | Committed | 0 | 0 | No | Safety | Building/Site | Facilities Site Work | Prevent further damage | Ordered | 2026-09-14 | FA-0511-2026-2042 | 2026 | Medium | Yes | No | 09/09/2026 - Gary Kingsbury: $ 9,477.00 vendor quote. 20 hours of labor from Maintenance for prep and electrical 09/14/2026 - Gary Kingsbury: Vendor up to 4 weeks out for material 09/15/2026 - Gary Kingsbury: updated estimated cost to reflect quote and labor | 2026-09-15 20:23:28
2025-11-07 10:36:13 | Lauren Fine | 500 | 511 | Building painting |  |  | June | 26000 |  |  | 0 | 0 | No | Customer Experience | Building/Site | Building Facilities |  | Deferred |  |  | 2026 | Medium | No |  |  | 2026-07-24 11:13:19
2025-03-31 08:55:42 | Gary Kingsbury | 500 | 512 | Front end conveyor rebuild | 2015 | Q4 | N/A | 25000 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Equipment | Conveyor Chain | Wash Quality | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - unknown: New conveyor needed 2026 | 2026-01-12 12:31:32
2025-11-07 10:36:13 | Lauren Fine | 500 | 512 | Conveyor track and chain (replace entire Conveyor) |  |  | January | 110000 |  | Committed | 77910.02 | 32089.98 | No | Prevent further damage | Equipment | Conveyor Chain |  | Completed | 2026-01-02 | EQ-0512-2026-1643 | 2026 | High | Yes |  | 02/05/2026 - Philip Loper: Total CAPEX Cost $80,939 This project finished on 01/29/26 -PL | 2026-02-05 11:20:32
2025-11-07 10:36:13 | Lauren Fine | 500 | 512 | Tunnel exit hard door |  |  | September | 14000 | 10228 | Committed | 0 | 0 | No | Safety | Building/Site | Facilities Site Work | Safety | Ordered | 2026-09-14 | FA-0512-2026-2043 | 2026 | Medium | Yes | No | 09/09/2026 - Gary Kingsbury: $ 9,928.00 vendor quote. 10 hours of labor from maintenance for prep and electrical. 09/14/2026 - Gary Kingsbury: Vendor up to 4 weeks out for material 09/15/2026 - Gary Kingsbury: Updated estimated cost to reflect quote and labor | 2026-09-15 20:24:45
2025-11-07 10:36:13 | Lauren Fine | 500 | 512 | Building painting |  |  | June | 24500 |  |  | 0 | 0 | No | Customer Experience | Building/Site | Building Facilities |  | Deferred |  |  | 2026 | Medium | No |  |  | 2026-07-24 11:14:28
2025-03-31 08:55:42 | Mason Faltysek | 500 | 513 | Parking lot restripe | 2005 | Q3 | N/A | 6500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Facilities Site Work | Customer Experience | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-11-07 10:36:13 | Benjamin Herr | 500 | 513 | Conveyor Chain, Rollers, Rebuild |  |  | April | 18500 |  | Committed | 22471.54 | -3971.54 | No | Prevent further damage | Equipment | Conveyor Chain | Prevent further damage | Completed | 2026-03-13 | EQ-0513-2026-1707 | 2026 | High | Yes | No | 01/12/2026 - Mason Faltysek: Confirmed with Josh Weaver, Conveyor frame is in good shape, WIll need welds on conveyor supports, and new top deck ears by roller up and roller down. WX513 09/23/25 - Sent an email over to Jody at MCWW and requested a proposal for the conveyor change out. -PL 09/26/25 - Texas Wash Works returned the proposal and I have placed it in the folder. - PL March? 02/09/2026 - Gary Kingsbury: Confirmed with Josh Weaver, Conveyor frame is in good shape, WIll need welds on conveyor supports, and new top deck ears by roller up and roller down. WX513 09/23/25 - Sent an email over to Jody at MCWW and requested a proposal for the conveyor change out. -PL 09/26/25 - Texas Wash Works returned the proposal and I have placed it in the folder. - PL March? 02/18/2026 - Philip Loper: 02/18 - Sent an email to Gary and team requesting additional information. 02/25/2026 - Philip Loper: 02/25 - Sent an email to Eric @ Vaughn and requested a proposal. Received an email from Gary on this date requestin | 2026-04-27 08:06:27
2025-11-07 10:36:13 | Benjamin Herr | 500 | 513 | New Exit Wind Door |  |  | October | 12816 | 13500 | Committed | 0 | 0 | No | Safety | Building/Site | Facilities Site Work | Safety | Ordered | 2026-08-17 | EQ-0513-2026-1961 | 2026 | Medium | Yes | No | 08/14/2026 - Gary Kingsbury: Quotes from Gallop and Hy-Tech received. | 2026-08-18 08:59:25
2025-11-07 10:36:13 | Benjamin Herr | 500 | 513 | new concrete around underground tanks |  |  |  | 20000 |  |  | 0 | 0 | No | Safety | Building/Site | Facilities Site Work |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: Settling issues | 2026-01-12 12:02:24
2025-11-07 10:36:13 | Benjamin Herr | 500 | 513 | Resealing/Striping |  |  |  | 7500 |  |  | 0 | 0 | No | Customer Experience | Building/Site | Building Facilities |  | Deferred |  |  | 2026 | Low | No |  |  | 2026-01-22 04:34:05
2025-11-07 10:36:13 | Benjamin Herr | 500 | 513 | Winter Hut |  |  | January | 4500 |  | Committed | 4660.36 | -160.36 | No | Customer Experience | Building/Site | Facilities Site Work |  | Completed |  | FA-0513-2026-1661 | 2026 | Medium | No |  | 02/05/2026 - Mason Faltysek: Hut has been ordered 2/3 expected to ship 2/6 02/11/2026 - Mason Faltysek: Arrived onsite 2/10 | 2026-04-23 14:29:56
2025-11-07 10:36:13 | Benjamin Herr | 500 | 513 | (6) StarGate Installation |  |  | January | 13000 |  | Committed | 0 | 0 | No | Wash Quality | Equipment | Blowers | Wash Quality | Completed | 2026-01-08 | EQ-0513-2026-1633 | 2026 | High | Yes |  |  | 2026-03-06 09:44:30
2025-03-31 08:55:42 | Mason Faltysek | 500 | 514 | Parking lot restripe | 2005 | Q3 | N/A | 6500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Facilities Site Work | Customer Experience | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-11-07 10:36:13 | Benjamin Herr | 500 | 514 | New Air Compressor |  |  | June | 17000 | 18363 | Committed | 19927.64 | -1564.64 | No | Prevent further damage | Equipment | Compressors Replacement |  | Completed | 2026-05-29 | EQ-0514-2026-1821 | 2026 | Medium | Yes | No | 02/16/2026 - Gary Kingsbury: Both air compressors need to be replaced. -GK 02/24/2026 - Philip Loper: 02/24 - Sent an email to Chris @ Aircentric and requested a proposal. 03/03/2026 - Philip Loper: Aircentric has returned the proposal and the total is $18,363 with tax. This has been placed in the CAPEX folder. 06/15/2026 - Gary Kingsbury: Ships on 6/18 | 2026-06-28 08:48:33
2025-11-07 10:36:13 | Benjamin Herr | 500 | 514 | Chain/Rollers/Gearbox/Conveyor Rebuild |  |  | May | 18500 | 19800 | Committed | 20939.96 | -1139.96 | No | Prevent further damage | Equipment | Conveyor Chain |  | Completed | 2026-04-14 | EQ-0514-2026-1752 | 2026 | High | Yes | No | 02/18/2026 - Philip Loper: 02/18 - Sent an email to Gary and team requesting additional information. 04/13/2026 - Gary Kingsbury: Quotes higher than original estimate 04/17/2026 - Gary Kingsbury: All part arrived on site 05/15/2026 - Gary Kingsbury: Completed | 2026-05-15 07:34:25
2025-11-07 10:36:13 | Benjamin Herr | 500 | 514 | New Exit Garage Door |  |  | October | 13000 |  |  | 0 | 0 | No | Prevent further damage | Building/Site | Facilities Site Work |  | Proposal Solicitation |  |  | 2026 | Low | No |  |  | 2026-08-11 07:16:45
2025-11-07 10:36:13 | Benjamin Herr | 500 | 514 | Tunnel Heater |  |  | January | 12000 |  | Uncommitted | 265.02 | 11734.98 | No | Wash Quality | Building/Site | Facilities Site Work |  | Deferred |  | FA-0514-2026-1641 | 2026 | High | No |  | 01/29/2026 - Mason Faltysek: Heaters scheduled to land end of week 2/2 02/05/2026 - Mason Faltysek: tunnel heaters are ordered L shaped heater on back order expected to arrive in 4 weeks as of 2/3 stright line heater arriving sooner but will be installed all at one time due to gas lines 03/12/2026 - Mason Faltysek: deferred per brad. Site would have to close for two days for install | 2026-04-23 14:44:32
2025-11-07 10:36:13 | Benjamin Herr | 500 | 514 | Tire Brush Install |  |  | April | 23000 |  | Committed | 21868.22 | 1131.78 | No | Wash Quality | Equipment | Wheel Brush | Wash Quality | Completed | 2026-03-19 | EQ-0514-2026-1708 | 2026 | Medium | Yes | No | 02/18/2026 - Philip Loper: 02/18 - Sent an email to Jody @ MCWW requesting a proposal. 03/04/2026 - Philip Loper: 03/04 - MCWW returned the proposal, and it has been placed in the CAPEX folder. Total Cost of Equipment is $18,517.52 04/17/2026 - Gary Kingsbury: Arrived on site 4/14 | 2026-05-01 06:21:08
2025-03-31 08:55:42 | Mason Faltysek | 500 | 515 | Tunnel Liner Wall Panels | 2022 | Q3 | July | 15500 |  | Committed | 0 | 0 |  | Planned maintenance | Building/Site | Building Facilities | Customer Experience | Completed |  |  | 2025 | High | No |  |  | 2026-01-12 12:00:08
2025-03-31 08:55:42 | Mason Faltysek | 500 | 516 | Tunnel Liner Wall Panels | 2022 | Q3 | July | 15500 |  | Committed | 0 | 0 |  | Planned maintenance | Building/Site | Building Facilities | Customer Experience | Completed |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Mason Faltysek | 500 | 517 | Tunnel Liner Wall Panels | 2014 | Q3 | N/A | 15500 |  | Committed | 16715.74 | -1215.74 |  | Planned maintenance | Building/Site | Building Facilities | Customer Experience | Completed |  | FA-0517-2025-1413 | 2025 | Low | No |  | 01/12/2026 - mason: FA-0517-2025-1413 | 2026-01-12 12:31:32
2025-11-07 10:36:13 | Lauren Fine | 500 | 517 | Chain and Roller Conveyor Rebuild |  |  | October | 15500 | 13000 | Committed | 0 | 0 | No | Prevent further damage | Equipment | Conveyor Chain | Customer Experience | 2026 Request | 2026-09-25 | EQ-0517-2026-2065 | 2026 | High | Yes | No | 01/12/2026 - Bradley Osborne: 209,900 Cars on current chain. 02/16/2026 - Gary Kingsbury: 209,900 Cars on current chain. 02/18/2026 - Philip Loper: 02/18 - Sent an email to Gary and team requesting additional information. 02/25/2026 - Philip Loper: 02/25 - Sent an email to Eric @ Vaughn and requested a proposal. 02/26/2026 - Philip Loper: 02/26 - Received the proposal from Vaughn. It has been placed in the CAPEX folder. Cost from Vaughn is $7,553.93 03/02/2026 - Gary Kingsbury: Moved to Q4 | 2026-09-25 06:29:42
2025-11-07 10:36:13 | Lauren Fine | 500 | 517 | Seal and restripe lot |  |  |  | 7500 |  |  | 0 | 0 | No | Customer Experience | Building/Site | Building Facilities |  | Deferred |  |  | 2026 | Low | No |  | 01/12/2026 - Henry Shine: Capex R&M | 2026-01-12 12:02:24
2025-03-31 08:55:42 | Mason Faltysek | 500 | 518 | Tunnel Liner Wall Panels | 2017 | Q3 | N/A | 15500 |  | Committed | 17387.39 | -1887.39 |  | Planned maintenance | Building/Site | Building Facilities | Customer Experience | Completed |  | FA-0518-2025-1412 | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-11-07 10:36:13 | Lauren Fine | 500 | 518 | Seal and restripe lot |  |  |  | 7500 |  |  | 0 | 0 | No | Customer Experience | Building/Site | Building Facilities |  | Deferred |  |  | 2026 | Low | No |  | 01/12/2026 - Henry Shine: Capex R&M | 2026-01-12 12:02:24
2025-11-07 10:36:13 | Benjamin Herr | 500 | 519 | conveyor entrance and exit rebuild |  |  | October | 3000 |  |  | 0 | 0 | No | Prevent further damage | Equipment | Conveyor Chain |  | 2026 Request |  |  | 2026 | High | No |  | 02/25/2026 - Philip Loper: 02/25 - Spoke to Garty and he stated his team will get me the price list for this job. | 2026-01-22 04:37:38
2025-11-07 10:36:13 | Benjamin Herr | 500 | 519 | Landscaping - Bushes/Stone |  |  | N/A | 5000 |  | Uncommitted | 0 | 0 | No | Customer Experience | Building/Site | Facilities Site Work |  | Deferred |  |  | 2026 | High | No |  | 01/12/2026 - Bradley Osborne: Capex R&M (neighbor complaints Rock against fence) 02/17/2026 - Bradley Osborne: Capex R&M (neighbor complaints Rock against fence) 02/25/2026 - Bradley Osborne: Get scope | 2026-03-10 10:03:43
2025-08-20 12:17:54 | Mason faltysek | 500 | 520 | Winter Hut |  | Q4 | October | 4000 |  | Committed | 4188.3 | -188.3 | No | Planned maintenance | Building/Site | Building Facilities | Safety | Completed |  | FA-0520-2025-1501 | 2025 | Low | No |  | 01/12/2026 - mason: Hut has been ordered 9/30 | 2026-01-12 12:31:32
2025-11-07 10:36:13 | Benjamin Herr | 500 | 520 | conveyor entrance and exit rebuild |  |  | August | 3000 |  |  | 0 | 0 | No | Prevent further damage | Equipment | Conveyor Chain |  | 2026 Request |  |  | 2026 | High | No |  | 02/25/2026 - Philip Loper: 02/25 - Spoke to Garty and he stated his team will get me the price list for this job. | 2026-07-24 11:18:23
2025-03-31 08:55:42 | Mason Faltysek | 500 | 521 | Tunnel Liner Wall Panels | 2016 | Q3 | N/A | 15500 |  | Committed | 27954.55 | -12454.55 |  | Planned maintenance | Building/Site | Building Facilities | Customer Experience | Completed |  | FA-0521-2025-1414 | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-11-07 10:36:13 | Lauren Fine | 500 | 521 | Seal and restripe lot |  |  |  | 7500 |  |  | 0 | 0 | No | Customer Experience | Building/Site | Building Facilities |  | Deferred |  |  | 2026 | Low | No |  | 01/12/2026 - Henry Shine: Capex R&M | 2026-01-12 12:02:24
2025-11-07 10:36:13 | Lauren Fine | 500 | 522 | conveyor entrance and exit rebuild |  |  | August | 3000 |  |  | 0 | 0 | No | Prevent further damage | Equipment | Conveyor Chain |  | 2026 Request |  |  | 2026 | High | No |  | 02/25/2026 - Philip Loper: 02/25 - Spoke to Garty and he stated his team will get me the price list for this job. | 2026-01-22 04:38:18
2025-11-07 10:36:13 | Lauren Fine | 500 | 522 | New Walls in wash Bay |  |  | May | 17500 |  |  | 0 | 0 | No | Customer Experience | Building/Site | Facilities Site Work |  | 2026 Request |  |  | 2026 | Low | No |  |  | 2026-01-22 04:38:38
2025-11-07 10:36:13 | Lauren Fine | 500 | 523 | conveyor entrance and exit rebuild |  |  | November | 3000 |  |  | 0 | 0 | No | Prevent further damage | Equipment | Conveyor Chain |  | 2026 Request |  |  | 2026 | High | No |  | 02/25/2026 - Philip Loper: 02/25 - Spoke to Garty and he stated his team will get me the price list for this job. | 2026-02-25 16:20:12
2025-11-07 10:36:13 | Lauren Fine | 500 | 524 | Belt Refresh |  |  | January | 85000 |  | Committed | 0 | 0 | Yes | Prevent further damage | Equipment | Conveyor Belt | Customer Experience | Completed |  | EQ-0524-2025-1571 | 2026 | High | No |  |  | 2026-02-16 10:47:35
2025-11-07 10:36:13 | Lauren Fine | 500 | 524 | Belt Motor and Gear Box |  |  | December | 20000 |  |  | 0 | 0 | No |  | Equipment | Conveyor Belt |  | 2026 Request |  |  | 2026 | Low | No |  |  | 2026-01-22 04:39:31
2025-11-07 10:36:13 | Lauren Fine | 500 | 524 | New tireshine |  |  | April | 28000 |  | Committed | 32648.38 | -4648.38 | No | Wash Quality | Equipment | Tire Shine | Wash Quality | Completed | 2026-03-19 | EQ-0524-2026-1710 | 2026 | High | Yes | No | 02/18/2026 - Philip Loper: 02/18 - Sent an email to Jody @ MCWW and requested a proposal. 02/18/2026 - Philip Loper: 02/18 - MCWW Returned the proposal and it has been placed in the CAPEX Folder. Cost is $26,023.67 before tax. 03/13/2026 - Gary Kingsbury: Changed estimated cost to account for labor and additional installation costs | 2026-04-30 10:05:37
2025-03-31 08:55:42 | Mason Faltysek | 600 | 601 | Paint - Repaint exterior of building | 2018 | Q3 | N/A | 15000 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Building Facilities | Prevent further damage | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-11-07 10:36:13 | Lauren Fine | 600 | 601 | Concrete pour on exit pad |  |  | July | 10000 | 6015 | Committed | 6015 | 0 | No | Customer Experience | Building/Site | Facilities Site Work | Customer Experience | Completed |  | FA-0601-2026-1841 | 2026 | Medium | Yes | No | 06/09/2026 - Gary Kingsbury: Quote from APM Paving at $6,015.00 | 2026-07-06 17:35:44
2025-11-07 10:36:13 | Lauren Fine | 600 | 601 | Sump Pump Failure |  |  |  | 2500 |  |  | 0 | 0 | No |  | Equipment |  |  | Deferred |  |  | 2026 | Low | No |  |  | 2026-01-22 04:40:42
2025-11-07 10:36:13 | Lauren Fine | 600 | 601 | Seal and restripe lot |  |  |  | 7500 |  |  | 0 | 0 | No | Customer Experience | Building/Site | Building Facilities |  | Deferred |  |  | 2026 | Low | No |  |  | 2026-01-22 04:41:12
2025-11-07 10:36:13 | Lauren Fine | 600 | 601 | Replace tunnel heater |  |  | January | 12000 |  |  | 0 | 0 | No | Prevent further damage | Building/Site | Facilities Site Work |  | Deferred |  |  | 2026 | High | No |  | 01/12/2026 - Bradley Osborne: This is for 1 heater. Q3 of 26 to be done for winter | 2026-01-12 12:00:08
2025-11-07 10:36:13 | Lauren Fine | 600 | 602 | Concrete pour on exit pad |  |  | July | 10000 | 8188 | Committed | 8188 | 0 | No | Customer Experience | Building/Site | Facilities Site Work | Customer Experience | Completed |  | FA-0602-2026-1842 | 2026 | Medium | Yes | No | 06/09/2026 - Gary Kingsbury: Quote from APM Paving for $8,188.00 07/20/2026 - Gary Kingsbury: Pushed back due to weather. Scheduled for 7/21 07/21/2026 - Gary Kingsbury: rescheduled for 7/23 07/22/2026 - Gary Kingsbury: Rescheduled to 7/24 due to weather | 2026-07-24 08:07:05
2025-11-07 10:36:13 | Lauren Fine | 600 | 602 | Sump Pump Failure |  |  |  | 2500 |  |  | 0 | 0 | No |  | Equipment |  |  | Deferred |  |  | 2026 | Low | No |  |  | 2026-01-22 04:41:54
2025-11-07 10:36:13 | Lauren Fine | 600 | 602 | Seal and restripe lot |  |  |  | 7500 |  |  | 0 | 0 | No | Customer Experience | Building/Site | Building Facilities |  | Deferred |  |  | 2026 | Low | No |  |  | 2026-01-22 04:42:12
2025-11-07 10:36:13 | Lauren Fine | 600 | 602 | Tunnel Heater |  |  | January | 7500 |  |  | 0 | 0 | No | Safety | Building/Site | Facilities Site Work |  | Deferred |  |  | 2026 | High | No |  | 01/12/2026 - Bradley Osborne: Q3 of 26 to be done for winter | 2026-01-12 12:00:08
2025-11-07 10:36:13 | Benjamin Herr | 700 | 702 | dual motor prep pump |  |  | February | 13000 |  | Committed | 9029.4 | 3970.6 | No | Customer Experience | Equipment | Prep Pump | Wash Quality | Completed | 2026-02-13 | EQ-0702-2026-1677 | 2026 | High | Yes |  | 02/12/2026 - Gary Kingsbury: Moved forward due to higher priority for wash quality 02/13/2026 - Philip Loper: Was ordered on 02/13/26. 03/10/2026 - Gary Kingsbury: Pumps are on site and in process of installing | 2026-04-20 07:13:25
2025-03-31 08:55:42 | Mason faltysek | 700 | 703 | Replace wind doors with Gallop | 2021 | Q4 | October | 12500 |  | Committed | 18304.95 | -5804.95 |  | Planned maintenance | Building/Site | Building Facilities | Safety | Completed |  | EQ-0703-2025-1459 | 2025 | Low | No |  | 01/12/2026 - rusty: Install date scheduled for November 4th and 5th | 2026-01-12 12:31:32
2025-11-07 10:36:13 | Benjamin Herr | 700 | 703 | Air Compressor |  |  | May | 17000 | 18000 | Committed | 19775.5 | -1775.5 | No | Prevent further damage | Equipment | Compressors Replacement | Prevent further damage | Completed | 2026-04-13 | EQ-0703-2026-1749 | 2026 | High | Yes | No | 02/16/2026 - Gary Kingsbury: Need both air compressors replaced 02/24/2026 - Philip Loper: 02/24 - Sent an email to Chris @ Aircentric and requested a proposal. 02/25/2026 - Philip Loper: 02/25 - Chris returned the proposal, and I have placed it in the CAPEX folder. To quote returned at @ $17,120.00 plus labor and installation. 04/13/2026 - Gary Kingsbury: Estimated cost higher due to fork lift rental and labor 04/24/2026 - Gary Kingsbury: Equipment delivered and on site | 2026-05-29 10:19:24
2025-03-31 08:55:42 | David Carreon | 700 | 704 | Cameras through tunnel to help with damage claims and saftey. | 2014 | Q3 | N/A | 3000 |  | Uncommitted | 0 | 0 |  | Planned maintenance | IT | Camera | Safety | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - unknown: budget looks flipped with 508 project. Use 508 budget $6,000 for 704 budget for this project move to Q3 -JMCC | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Mason Faltysek | 700 | 704 | Signage - new sign above entrance to tunnel to cover soapy joes up or re-do EFIS | 2014 | Q2 | May | 8500 |  | Committed | 0 | 0 |  | Planned maintenance | Building/Site | marketing/signage | Customer Experience | Completed |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Mason Faltysek | 700 | 704 | Tunnel Liner Wall Panels | 2014 | Q2 | June | 22500 |  | Committed | 23168.15 | -668.15 |  | Planned maintenance | Building/Site | Building Facilities | Customer Experience | Completed |  | FA-0704-2025-1339 | 2025 | Low | No |  | 01/12/2026 - unknown: Wall panels on site. Waiting for contractor | 2026-01-12 12:31:32
2025-11-07 10:36:13 | Benjamin Herr | 700 | 704 | Camera Upgrade |  |  | May | 7000 | 8500 | Committed | 10756.78 | -2256.78 | No | Prevent further damage | IT | Camera |  | Completed | 2026-05-13 | EQ-0704-2026-1809 | 2026 | Medium | Yes |  |  | 2026-06-16 09:25:40
2025-11-07 10:36:13 | Benjamin Herr | 700 | 704 | Entrance tunnel heaters |  |  | September | 12000 | 13500 | Committed | 0 | 0 | No | Prevent further damage | Building/Site | Facilities Site Work | Safety | Ordered | 2026-08-12 | EQ-0704-2026-1954 | 2026 | High | Yes | No |  | 2026-08-14 10:18:48
2025-03-31 08:55:42 | Mason Faltysek | 700 | 705 | Parking lot restripe | 2005 | Q3 | N/A | 6500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Facilities Site Work | Customer Experience | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - unknown: Not a capex item | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Gary Kingsbury | 700 | 705 | Replace containment trap covers with open grating | 2005 | Q3 | N/A | 14000 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Facilities Site Work | Prevent further damage | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - unknown: Revisit in 2026 | 2026-01-12 12:31:32
2025-11-07 10:36:13 | Benjamin Herr | 700 | 705 | Prep Gun Pump Replacement |  |  | January | 8952 |  | Committed | 8644.53 | 307.47 | No | Prevent further damage | Equipment | Prep Pump | Wash Quality | Completed | 2026-01-07 | EQ-0705-2026-1630 | 2026 | Low | No |  |  | 2026-01-27 08:06:14
2025-11-07 10:36:13 | Benjamin Herr | 700 | 705 | Area behind curb in vac area back side of building (Sidewalk/Lanscaping) |  |  | May | 20000 | 15000 | Committed | 14499.8 | 500.2 | No | Customer Experience | Building/Site | Facilities Site Work | Customer Experience | Completed |  | FA-0705-2026-1755 | 2026 | Low | Yes |  | 04/17/2026 - Mason Faltysek: Scheduled for first week of may due to weather in the michigan market 05/05/2026 - Mason Faltysek: Work has been completed and waiting for contractor to invoice | 2026-05-05 12:11:25
2025-11-07 10:36:13 | Benjamin Herr | 700 | 705 | Finishing XPT Canopy face |  |  | September | 10000 |  | Committed | 0 | 0 | No | Customer Experience | Building/Site | Facilities Site Work |  | Proposal Solicitation |  |  | 2026 | Low | No | No |  | 2026-08-14 11:29:03
2025-11-07 10:36:13 | Benjamin Herr | 700 | 705 | Concrete pad for towel cart on backside of building |  |  | April | 5000 |  | Uncommitted | 0 | 0 | No | Customer Experience | Building/Site | Facilities Site Work |  | Deferred |  |  | 2026 | Low | No | No | 05/01/2026 - Gary Kingsbury: Needs to be cancelled | 2026-07-21 09:37:30
2025-11-07 10:36:13 | Benjamin Herr | 700 | 705 | Canister Vacs replaced |  |  |  | 12000 |  |  | 0 | 0 | No | Customer Experience | Equipment |  |  | Deferred |  |  | 2026 | Low | No |  |  | 2026-01-22 04:45:30
2025-11-07 10:36:13 | Benjamin Herr | 700 | 705 | Concrete at entrance |  |  |  | 10000 |  |  | 0 | 0 | No | Prevent further damage | Building/Site | Facilities Site Work |  | 2026 Request |  |  | 2026 | Medium | No |  | 01/12/2026 - unknown: | 2026-01-12 12:01:41
2025-11-07 10:36:13 | Benjamin Herr | 700 | 705 | Additional Grundfoss pumps |  |  | May | 17000 |  | Committed | 15644.59 | 1355.41 | No | Prevent further damage | Equipment | Hydroflex | Wash Quality | Completed | 2026-03-13 | EQ-0705-2026-1713 | 2026 | Low | Yes | No | 02/16/2026 - Gary Kingsbury: addition of two Grundfoss pumps 02/18/2026 - Philip Loper: 02/18 - Sent an email to the site requesting additional information and photos. | 2026-05-29 10:18:44
2025-11-07 10:36:13 | Benjamin Herr | 700 | 706 | Camera system repairs |  |  | September | 3500 |  |  | 0 | 0 | No | Safety | IT | Camera |  | Proposal Solicitation |  |  | 2026 | Medium | No |  |  | 2026-08-17 16:56:46
2025-11-07 10:36:13 | Benjamin Herr | 700 | 706 | Mitter frame (Whole replacement) |  |  | August | 20000 |  | Committed | 15401.96 | 4598.04 | No | Wash Quality | Equipment | Mitter | Wash Quality | Completed | 2026-06-16 | EQ-0706-2026-1852 | 2026 | Medium | Yes | No | 02/18/2026 - Philip Loper: 02/18 - Sent an email to Jody @ MCWW requesting a proposal. 02/18/2026 - Philip Loper: 02/18 - MCWW has returned a proposal for the mitter and it has been placed in the CAPEX folder. Cost is $13,882.78 before tax. 02/25/2026 - Philip Loper: 02/25 - Sent an email to Jody @ MCWW and requested a proposal. Informed him it needed to be a wide mitter to clear the tire shine and the system is 208V 07/20/2026 - Gary Kingsbury: Ship date 8/4 08/10/2026 - Gary Kingsbury: Mitter has been delivered. 8/12 scheduled install 08/13/2026 - Gary Kingsbury: Completed 8/12 | 2026-08-13 08:36:53
2026-07-28 10:04:01 | Gary Kingsbury | 700 | 706 | Replace HP Rinse pump |  | Q3 | September | 4000 |  | Committed | 3951.38 | 48.62 | No | Planned maintenance | Equipment | high pressure rinse | Wash Quality | In-Process | 2026-08-17 | EQ-0706-2026-1964 |  | High | Yes | No | 09/15/2026 - Gary Kingsbury: Pump on location | 2026-09-15 20:15:58
2025-03-31 08:55:42 | Gary Kingsbury | 700 | 707 | Chain | 2002 | Q4 | N/A | 12000 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Equipment | chain/roller | Wash Quality | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - unknown: Chain was replaced 12/1/22 364K Cars | 2026-01-12 12:31:32
2025-08-20 12:20:07 | Gary Kingsbury | 700 | 707 | Floor Heat |  | Q4 | October | 50000 |  | Committed | 0 | 0 | No | Planned maintenance | Building/Site | Vacuum | Customer Experience | Completed |  |  | 2025 | Low | No |  |  | 2026-04-17 06:20:20
2025-08-20 12:21:19 | Mason faltysek | 700 | 707 | Auto Wash Replacement Shroud |  | Q4 | November | 6000 |  | Committed | 8800 | -2800 | No | Planned maintenance | Building/Site | Building Facilities | Customer Experience | Completed |  | FA-0707-2025-1493 | 2025 | Low | No |  | 01/12/2026 - mason: Complete | 2026-01-12 12:31:32
2025-11-07 10:36:13 | Benjamin Herr | 700 | 707 | Log Chain Conversion |  |  | March | 13500 |  | Committed | 11398.54 | 2101.46 | No | Prevent further damage | Equipment | Conveyor Chain |  | Completed | 2026-01-26 | EQ-0707-2026-1657 | 2026 | Medium | No |  | 02/05/2026 - Philip Loper: This was ordered by Gary 02/12/2026 - Gary Kingsbury: Completed on 2/11 | 2026-02-12 08:28:11
2025-11-07 10:36:13 | Benjamin Herr | 700 | 707 | New boiler and floor heating in SS & autos |  |  | N/A | 20000 |  |  | 0 | 0 | No | Safety | Building/Site | Facilities Site Work |  | Proposal Solicitation |  |  | 2026 | High | No |  | 01/12/2026 - Mason Faltysek: Ongoing 2025 January? 02/09/2026 - Gary Kingsbury: Ongoing 2025 January? | 2026-02-09 14:03:56
2025-11-07 10:36:13 | Benjamin Herr | 700 | 707 | Mitter frame (Whole replacement) |  |  | April | 14500 |  | Committed | 17187.59 | -2687.59 | No | Wash Quality | Equipment | Mitter | Wash Quality | Completed | 2026-03-16 | EQ-0707-2026-1709 | 2026 | Medium | Yes | No | 02/18/2026 - Philip Loper: 02/18 - Sent an email to Jody @ MCWW requesting a proposal. 02/19/2026 - Philip Loper: 02/19 - Jody @ MCWW returned a proposal and it has been placed in the CAPEX folder The cost is $13,882.78. 03/12/2026 - Gary Kingsbury: Increased estimate due to internal labor and additional parts | 2026-04-29 09:23:06
2025-03-31 08:55:42 | Gary Kingsbury | 700 | 709 | Chain | 2005 | Q4 | N/A | 12000 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Equipment | chain/roller | Wash Quality | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - rusty: Chain was replaced 12/1/22 361K Cars | 2026-01-12 12:31:32
2025-11-07 10:36:13 | Benjamin Herr | 700 | 709 | Chain and Roller Conveyor Rebuild |  |  | April | 15500 |  | Committed | 12001.19 | 3498.81 | No | Prevent further damage | Equipment | Conveyor Chain | Prevent further damage | Completed | 2026-03-13 | EQ-0709-2026-1712 | 2026 | Medium | Yes | No | 02/18/2026 - Philip Loper: 02/18 - Sent an email to Gary and team requesting additional information. 02/25/2026 - Philip Loper: 02/25 - Sent an email to Eric @ Vaughn and requested a proposal. 02/26/2026 - Philip Loper: 02/26 - Received the proposal from Eric and placed it in the CAPEX Folder. The Cost from Vaughn is $9,866.22 | 2026-04-23 08:45:12
2025-11-07 10:36:13 | Benjamin Herr | 700 | 709 | Building Painting |  |  | May | 20000 |  |  | 0 | 0 | No | Customer Experience | Building/Site | Building Facilities |  | Deferred |  |  | 2026 | Low | No |  |  | 2026-05-29 10:17:34
2025-11-07 10:36:13 | Benjamin Herr | 700 | 709 | tunnel entrance door and exit wind door |  |  | August | 18000 |  | Committed | 5000 | 13000 | No | Safety | Building/Site | Facilities Site Work | Safety | Ordered |  | EQ-0709-2026-1913 | 2026 | High | Yes | No | 06/15/2026 - Mason Faltysek: Toledo door coming out to quote. Gallop has supplied quote. Hitech is quoting the installation of the door. 06/15/2026 - Gary Kingsbury: Gallop quote is in equipment diagrams folder $10,427.59 07/20/2026 - Gary Kingsbury: Final quote from Toledo received. Installation quote from Hy tech also received 07/28/2026 - Gary Kingsbury: Security door from Toledo requires mason work to install outside building. Separate Capex will be put in for this. Only Gallop wind door will be installed at exit. | 2026-07-22 08:12:53
2025-11-07 10:36:13 | Benjamin Herr | 700 | 709 | Landscaping near XPT |  |  | May | 5000 |  |  | 0 | 0 | No | Safety | Building/Site | Facilities Site Work |  | 2026 Request |  |  | 2026 | Medium | No |  |  | 2026-01-22 04:50:36
2025-11-07 10:36:13 | Benjamin Herr | 700 | 709 | Mitter frame (Whole replacement) |  |  | September | 30000 | 16000 | Committed | 5600 | 10400 | No | Wash Quality | Equipment | Mitter | Wash Quality | Ordered | 2026-07-31 | EQ-0709-2026-1939 | 2026 | Medium | Yes | No | 07/28/2026 - Gary Kingsbury: Asked Phil to quote this out 7/28 07/31/2026 - Gary Kingsbury: PO # assigned and sent to MCWW to process order | 2026-08-20 14:50:22
2025-03-31 08:55:42 | Gary Kingsbury | 700 | 711 | Replace HP water lines to prep with stainless tubing and install double boom. | 2022 | Q1 | August | 15000 |  | Committed | 0 | 0 |  | Planned maintenance | Equipment | prep pump | Wash Quality | Completed | 2025-09-29 | EQ-0711-2025-1470 | 2025 | Low | No |  | 01/12/2026 - rusty: All components ordered | 2026-01-12 12:31:32
2025-11-07 10:36:13 | Benjamin Herr | 700 | 712 | Tunnel Lighting |  |  | September | 10000 | 3000 | Committed | 2652.86 | 347.14 | No | Safety | Building/Site | Facilities Site Work | Customer Experience | Ordered | 2026-08-14 | EQ-0712-2026-1968 | 2026 | Low | Yes | No | 08/14/2026 - Gary Kingsbury: Quote received to replace/add 11 lights with cords at $2652.86 09/15/2026 - Gary Kingsbury: Deferred (the PO was cancelled). Live PO at this store: FA-0712-2026-1962 (Ordered) | 2026-09-16 07:48:47
2026-07-28 10:07:11 | Gary Kingsbury | 700 | 712 | Entrance Wind Door |  | Q3 | October | 12000 |  | Committed | 5000 | 7000 | No | Planned maintenance | Equipment | Building Facilities | Safety | Ordered | 2026-08-20 | EQ-0712-2026-1984 |  | High | Yes | No |  | 2026-08-20 08:07:54
2026-07-28 10:09:26 | Gary Kingsbury | 700 | 712 | Chain & Rollers, Conveyor rebuild |  | Q3 | September | 15000 | 10500 | Committed | 11611.08 | -1111.08 | No | Planned maintenance | Equipment | Conveyor Chain | Wash Quality | Completed | 2026-08-20 | EQ-0712-2026-1983 |  | High | Yes | No | 08/20/2026 - Gary Kingsbury: Vaughan quote at $9789.13 | 2026-09-10 06:12:01
2026-07-28 10:14:09 | Gary Kingsbury | 700 | 712 | Prep Area Tunnel Heat |  |  | October | 20000 |  | Committed | 0 | 0 | No | Planned maintenance | Building/Site | Facilities Site Work | Safety | Proposal Solicitation |  |  |  | High | No | No |  | 2026-08-14 13:45:55
2025-08-20 12:22:15 | Mason faltysek | 700 | 713 | Winter Hut |  | Q4 | October | 4000 |  | Committed | 4125.73 | -125.73 | No | Planned maintenance | Building/Site | Building Facilities | Safety | Completed |  | FA-0713-2025-1502 | 2025 | Low | No |  | 01/12/2026 - mason: Hut has been ordered 9/30 | 2026-01-12 12:31:32
2025-08-20 12:23:07 | Mason faltysek | 700 | 714 | Winter Hut |  | Q4 | October | 4000 |  | Committed | 0 | 0 | No | Planned maintenance | Building/Site | Building Facilities | Safety | Completed |  | FA-0714-2025-1503 | 2025 | Low | No |  | 01/12/2026 - mason: Hut has been ordered 9/30 | 2026-01-12 12:31:32
2025-11-07 10:36:13 | Benjamin Herr | 700 | 715 | 715 - Winter Hut |  |  | January | 4500 |  | Committed | 4616.18 | -116.18 | No | Safety | Building/Site | Facilities Site Work | Safety | Completed | 2026-01-06 | FA-0715-2026-1621 | 2026 | High | No |  | 01/29/2026 - Mason Faltysek: Installed | 2026-02-02 16:17:36
2025-11-07 10:36:13 | Benjamin Herr | 700 | 717 | 717 - Winter Hut |  |  | January | 4500 |  | Committed | 4583.25 | -83.25 | No | Safety | Building/Site | Facilities Site Work | Safety | Completed | 2026-01-06 | FA-0717-2026-1623 | 2026 | High | No |  |  | 2026-02-02 16:17:37
2025-11-07 10:36:13 | Benjamin Herr | 700 | 718 | Weed Barrier for back mulch bed and replace with Rock |  |  | N/A | 5000 |  | Uncommitted | 0 | 0 | No | Customer Experience | Building/Site | Facilities Site Work |  | Deferred |  |  | 2026 | Low | No |  |  | 2026-03-10 10:08:14
2025-03-31 08:55:42 | Phil Loper | 800 | 801 | Tire Shine | 2009 | Q1 | April | 27350 |  | Committed | 18214.01 | 9135.99 |  | Planned maintenance | Equipment | Tire Shine | Wash Quality | Completed |  | EQ-0801-2025-1226 | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | David Carreon | 800 | 801 | LPR Server upgrade from Windows to Linux (No Longer Supported, No update for bug fix available) | 2009 | Q2 | May | 1600 |  | Committed | 11318.41 | -9718.41 |  | Planned maintenance | IT | Technology | Safety | Completed |  | EQ-0801-2025-1294 | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:42 | Mason Faltysek | 800 | 801 | Parking lot restripe | 2009 | Q3 | N/A | 6500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Facilities Site Work | Customer Experience | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-11-07 10:36:13 | Caleb Harris | 800 | 801 | Spare Market Compressor |  |  | January | 6000 |  | Committed | 4026.17 | 1973.83 | No | Prevent further damage | Equipment | Compressors Replacement | Wash Quality | Completed |  | EQ-0801-2026-1638 | 2026 | Low | Yes |  |  | 2026-03-31 16:11:06
2025-03-31 08:55:42 | David Carreon | 800 | 802 | LPR Server upgrade from Windows to Linux (No Longer Supported, No update for bug fix available) | 2011 | Q2 | May | 1600 |  | Committed | 11318.41 | -9718.41 |  | Planned maintenance | IT | Technology | Safety | Completed |  | EQ-0801-2025-1294 | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-11-07 10:36:13 | Caleb Harris | 800 | 802 | Touch IT upgrade from Win7 |  |  | April | 4995 |  | Uncommitted | 0 | 0 | No | Prevent further damage | IT | Technology |  | Deferred |  |  | 2026 | Medium | No |  |  | 2026-06-01 12:33:23
2025-11-07 10:36:13 | Caleb Harris | 800 | 802 | 2 AutoSentry upgrades from Win7 |  |  | July | 3348.46 |  | Uncommitted | 0 | 0 | No | Prevent further damage | IT | Technology |  | Deferred |  |  | 2026 | Medium | No |  | 01/12/2026 - unknown: | 2026-06-01 12:33:48
2025-11-07 10:36:13 | Caleb Harris | 800 | 802 | POS upgrade from Win7 (PC only) |  |  | April | 2450 |  | Uncommitted | 0 | 0 | No | Prevent further damage | IT | Technology |  | Deferred |  |  | 2026 | Medium | No |  |  | 2026-06-01 12:34:04
2026-05-18 16:04:32 | David Carreon | 800 | 802 | Tablet Project |  |  | May | 12000 |  | Committed | 11414.85 | 585.15 | No | Planned maintenance |  | Technology |  | Completed | 2026-05-13 | EQ-0802-2026-1807 |  | High | No |  |  | 2026-09-14 14:53:52
2026-06-01 12:32:52 | David Carreon | 800 | 802 | Tablet Set up |  |  | May | 12000 |  | Committed | 11414.85 | 585.15 | No | Planned maintenance | IT |  | Customer Experience | Completed |  | EQ-0802-2026-1807 |  | High | No |  |  | 2026-06-01 12:32:52
2025-03-31 08:55:42 | David Carreon | 800 | 803 | LPR Server upgrade from Windows to Linux (No Longer Supported, No update for bug fix available) | 2014 | Q2 | May | 1600 |  | Committed | 11318.41 | -9718.41 |  | Planned maintenance | IT | Technology | Safety | Completed |  | EQ-0801-2025-1294 | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-11-07 10:36:13 | Caleb Harris | 800 | 803 | Add doors to dumpster enclosure |  |  | N/A | 10000 |  | Uncommitted | 0 | 0 | No | Customer Experience | Building/Site | Facilities Site Work |  | Deferred |  |  | 2026 | Low | No |  |  | 2026-06-01 16:44:08
2025-11-07 10:36:13 | Caleb Harris | 800 | 803 | Touch IT upgrade from Win7 |  |  | August | 4995 |  | Committed | 0 | 0 | No | Prevent further damage | IT | Technology |  | Deferred |  |  | 2026 | Medium | No |  | 01/12/2026 - unknown: | 2026-08-17 16:40:00
2025-11-07 10:36:13 | Caleb Harris | 800 | 803 | 2 AutoSentry upgrades from Win7 |  |  | October | 3348.46 |  | Committed | 0 | 0 | No | Prevent further damage | IT | Technology |  | 2026 Request |  |  | 2026 | Medium | No |  | 01/12/2026 - unknown: 08/17/2026 - David Carreon: Moving this project to September due to camera project | 2026-09-08 14:43:21
2025-11-07 10:36:13 | Caleb Harris | 800 | 804 | Chain and Roller Conveyor Rebuild |  |  | July | 13500 |  | Committed | 11668.54 | 1831.46 | No | Prevent further damage | Equipment | Conveyor Chain |  | Completed |  | EQ-0804-2026-1890 | 2026 | Medium | Yes |  | 01/12/2026 - unknown: 188,000 cars on current chain but showing excessive wear. 02/18/2026 - Philip Loper: 02/18 - Sent an email to Eric @ Vaughn and requested a proposal for chain and rollers. 02/24/2026 - Philip Loper: 02/19 - Eric @ Vaughn returned the proposal. Chain, rollers, sprocket, and freight is $9,700.79 07/20/2026 - Andrew Folse: Install scheduled for Thursday 7/23 | 2026-07-23 14:17:27
2025-11-07 10:36:13 | Caleb Harris | 800 | 804 | 1 AutoSentry upgrade from Win7 Lane2 |  |  | June | 2038 | 2800 | Committed | 0 | 0 | No | Prevent further damage | IT | Technology |  | Deferred |  |  | 2026 | Medium | No |  |  | 2026-09-21 11:35:12
2025-11-07 10:36:13 | Caleb Harris | 800 | 804 | Vac Motor Star Cabinet (remove VFD and add starters) |  |  |  | 5300 |  |  | 0 | 0 | No | Prevent further damage | Equipment |  |  | 2026 Request |  |  | 2026 | Medium | No |  | 01/12/2026 - unknown: | 2026-01-12 12:01:41
2025-03-31 08:55:42 | David Carreon | 800 | 805 | LPR Server upgrade from Windows to Linux (No Longer Supported, No update for bug fix available) | 2015 | Q2 | June | 1600 |  | Committed | 11318.41 | -9718.41 |  | Planned maintenance | IT | Technology | Safety | Completed |  | EQ-0801-2025-1294 | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-11-07 10:36:13 | Caleb Harris | 800 | 805 | Compressor |  |  | April | 4104.84 |  | Committed | 4236.84 | -132 | No | Prevent further damage | Equipment | Compressors Replacement |  | Completed | 2026-03-16 | EQ-0805-2026-1711 | 2026 | Medium | Yes | No | 02/16/2026 - Jonathan Blair: Went from 6,500 to 5,700. 02/18/2026 - Philip Loper: 02/18 - Sent an email to the site asking for additional information. 02/18/2026 - Philip Loper: 02/18 - Sent an email to Green valley and requested a proposal. 02/18/2026 - Philip Loper: 02/18 - Green valley returned the proposal and I have placed it in the 2026 CAPEX folder. 02/18/2026 - Philip Loper: The price is $4,104.84 with tax and freight. 03/26/2026 - Gary Kingsbury: 4 hours labor | 2026-04-07 10:36:54
2025-11-07 10:36:13 | Caleb Harris | 800 | 805 | Vac Motor Star Cabinet (remove VFD and add starters) |  |  |  | 5300 |  |  | 0 | 0 | No | Prevent further damage | Equipment |  |  | 2026 Request |  |  | 2026 | Medium | No |  | 01/12/2026 - unknown: | 2026-01-12 12:01:41
2025-11-07 10:36:13 | Caleb Harris | 800 | 805 | Chain and Roller Conveyor Rebuild |  |  | April | 10500 |  | Committed | 11559.92 | -1059.92 | No | Prevent further damage | Equipment | Conveyor Chain |  | Completed | 2026-03-17 | EQ-0805-2026-1714 | 2026 | Medium | Yes |  | 01/12/2026 - unknown: 221,000 Cars on current chain but showing excessive wear. 02/16/2026 - Jonathan Blair: It went from 13,500 to 15,500. 02/17/2026 - Philip Loper: 02/17 - Sent an email tp the site to ask for additional informaion. 02/24/2026 - Philip Loper: 02/23- Store sent back requested information. I emailed Eric @ Vaugh requesting a quote. 02/24/2026 - Philip Loper: 02/23 - Eric replied with the proposal. The total is $9,700.79. This has been placed in the CAPEX folder. 07/20/2026 - Andrew Folse: Contractor should finish install night of 7/20 | 2026-07-20 18:51:17
2025-11-07 10:36:13 | Caleb Harris | 800 | 805 | Ceiling panel replacement/repair |  |  | July | 5000 | 15000 | Committed | 47331.36 | -32331.36 | No | Prevent further damage | Building/Site | Facilities Site Work | Safety | Completed |  | EQ-0805-2026-1815 | 2026 | Medium | Yes | No | 01/12/2026 - unknown: WO: 66422 03/05/2026 - Caleb Harris: WO: 66422 03/12/2026 - Brandy Fruia: WO: 66422 03/25/2026 - Bradley Osborne: WO: 66422 03/25/2026 - Bradley Osborne: WO: 66422 05/21/2026 - Gary Kingsbury: Quote from vendor came in at $14,488.07. We are supplying 65 of the wall panels we have in storage 06/15/2026 - Andrew Folse: Panels are onsite, Maintenance is meeting with contractor on 6/15 to plan install 07/20/2026 - Andrew Folse: Contractor should finish install the night of 7/20 07/27/2026 - Andrew Folse: Contractor delayed, should finish install on 7/27. There are only 15 wall panels left to install | 2026-08-10 13:49:36
2025-11-07 10:36:13 | Caleb Harris | 800 | 805 | 1 AutoSentry upgrades from Win7 |  |  | N/A | 2038 |  |  | 0 | 0 | No | Prevent further damage | IT | Technology |  | Deferred |  |  | 2026 | Medium | No |  | 01/12/2026 - unknown: 02/19/2026 - Bradley Osborne: May not need. 06/01/2026 - David Carreon: This was done through R&M they spent about $1700 in May of 2025 | 2026-06-01 13:12:31
2025-03-31 08:55:42 | David Carreon | 800 | 806 | LPR Server upgrade from Windows to Linux (No Longer Supported, No update for bug fix available) | 2017 | Q2 | June | 1600 |  | Committed | 11318.41 | -9718.41 |  | Planned maintenance | IT | Technology | Safety | Completed |  | EQ-0801-2025-1294 | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-11-07 10:36:13 | Caleb Harris | 800 | 806 | Chain and Roller Conveyor Rebuild |  |  | September | 13500 |  | Committed | 0 | 0 | No | Prevent further damage | Equipment | Conveyor Chain |  | Completed |  | EQ-0806-2026-1992 | 2026 | Low | Yes | No | 01/12/2026 - unknown: 207,000 cars on current chain. Not needed per Kain 10/23 02/18/2026 - Philip Loper: 02/18 - Sent an email to Wric @ Vaughn and requested a proposal. 02/24/2026 - Philip Loper: 02/24 - Eric Returned the proposal and it has been placed in the CAPEX folder. The cost is $9,700.79 | 2026-09-16 08:24:37
2025-03-31 08:55:42 | Mason Faltysek | 800 | 807 | Repair concrete Driveway | 2019 | Q2 | N/A | 0 |  | Committed | 0 | 0 |  | Planned maintenance | Building/Site | Facilities Site Work | Prevent further damage | Completed |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:43 | Mason Faltysek | 800 | 807 | Landscaping: mulch beds | 2019 | Q2 | N/A | 2500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Facilities Site Work | Prevent further damage | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-03-31 08:55:43 | David Carreon | 800 | 807 | LPR Server upgrade from Windows to Linux (No Longer Supported, No update for bug fix available) | 2019 | Q2 | June | 1600 |  | Committed | 11318.41 | -9718.41 |  | Planned maintenance | IT | Technology | Safety | Completed |  | EQ-0801-2025-1294 | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-11-07 10:36:13 | Caleb Harris | 800 | 807 | Soft Start VAc cabinets to replace VFDs |  |  |  | 5300 |  |  | 0 | 0 | No | Prevent further damage | Equipment |  |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: | 2026-01-12 12:02:24
2025-11-07 10:36:13 | Caleb Harris | 800 | 807 | Add doors to dumpster enclosure |  |  |  | 10000 |  |  | 0 | 0 | No | Customer Experience | Building/Site | Facilities Site Work |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: https://drive.google.com/file/d/1HS1IFmg-VY6pxrPjCGBhGtbC3ZT0wmMI/view?usp=sharing | 2026-01-12 12:02:24
2025-11-07 10:36:13 | Caleb Harris | 800 | 807 | Touch IT from Win7 |  |  | October | 4995 |  |  | 0 | 0 | No | Prevent further damage | IT | Technology |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: | 2026-01-12 12:02:24
2025-11-07 10:36:13 | Caleb Harris | 800 | 807 | 2 AutoSentry upgrades from Win7 |  |  | October | 4076 |  |  | 0 | 0 | No | Prevent further damage | IT | Technology |  | 2026 Request |  |  | 2026 | Medium | No |  | 01/12/2026 - unknown: | 2026-01-12 12:01:41
2025-03-31 08:55:43 | David Carreon | 800 | 808 | Cameras, back of property cameras | 2011 | Q3 | N/A | 2500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | IT | Camera | Safety | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - rusty: This is possibly not CAPEX - David talk with Caleb - JMCC | 2026-01-12 12:31:32
2025-03-31 08:55:43 | Abel Smith | 800 | 808 | Chain - New chain/rollers/drum/sprocket - convert to log chain | 2011 | Q4 | August | 12000 |  | Committed | 10133.5 | 1866.5 |  | Planned maintenance | Equipment | chain/roller | Wash Quality | Completed |  | EQ-0808-2025-1432 | 2025 | Low | No |  | 01/12/2026 - rusty: Chain was replaced 11/10/2022 299K Cars | 2026-01-12 12:31:32
2025-11-07 10:36:13 | Caleb Harris | 800 | 808 | Additional JKo Mat Machine |  |  | May | 5500 |  | Committed | 5686.8 | -186.8 | No | Customer Experience | Building/Site | Facilities Site Work |  | Completed | 2026-04-06 | EQ-0808-2026-1723 | 2026 | Low | Yes | No | 02/17/2026 - Philip Loper: price for JKO and freight is $5,238.50. No Tak included. 02/17/2026 - Philip Loper: "02/16 - Sent an email to JKO for a proposal 02/16 - Proposal has been placed in the 2026 CAPEX folder for the store. " | 2026-04-15 08:55:43
2025-11-07 10:36:13 | Caleb Harris | 800 | 808 | Mini Seperator Replacement |  |  | January | 15000 |  | Committed | 12857.63 | 2142.37 | No | Prevent further damage | Equipment | Vacuum | Customer Experience | Completed | 2026-01-02 | EQ-0808-2026-1616 | 2026 | Medium | No |  |  | 2026-03-12 10:42:56
2025-03-31 08:55:43 | Mason Faltysek | 800 | 809 | Parking lot restripe | 2019 | Q3 | N/A | 6500 |  | Uncommitted | 0 | 0 |  | Planned maintenance | Building/Site | Facilities Site Work | Customer Experience | Deferred |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-11-07 10:36:13 | caleb Harris | 800 | 809 | Concrete work Tunnel Exit |  |  |  | 12500 |  |  | 0 | 0 | No | Customer Experience | Building/Site | Facilities Site Work |  | 2026 Request |  |  | 2026 | Medium | No |  | 01/12/2026 - mason: Bid received 11/26 | 2026-01-12 12:01:41
2025-11-07 10:36:13 | Caleb Harris | 800 | 809 | Tablet and networking set up |  |  | March | 10000 |  | Committed | 12323.52 | -2323.52 | No | Customer Experience | IT | Technology |  | Completed |  | EQ-0809-2026-1717 | 2026 | Medium | Yes |  | 02/19/2026 - Bradley Osborne: Going to use this for a tablet instead of an enclosure and new terminal saving around $6-$7k. 03/20/2026 - Gary Kingsbury: Quote for tablet, pin pad, and printer at $7371.51 | 2026-04-16 10:49:57
2025-11-07 10:36:13 | Caleb Harris | 800 | 809 | Standalone POS with PAX reader at pay stations. (SAL) |  |  | N/A | 5000 |  | Uncommitted | 0 | 0 | No | Prevent further damage | IT | Technology |  | Deferred |  |  | 2026 | Medium | No |  | 02/19/2026 - Bradley Osborne: Not needed with tablet | 2026-09-14 14:54:21
2025-11-07 10:36:13 | Caleb Harris | 800 | 809 | Touch IT upgrade from Win7 |  |  | March | 4995 |  | Uncommitted | 0 | 0 | No | Prevent further damage | IT | Technology |  | Deferred |  |  | 2026 | Medium | No |  |  | 2026-04-16 10:51:29
2025-11-07 10:36:13 | Caleb Harris | 800 | 809 | 2 AutoSentry upgrade from Win7 |  |  | March | 4076 |  | Uncommitted | 0 | 0 | No | Prevent further damage | IT | Technology |  | Deferred |  |  | 2026 | Medium | No |  |  | 2026-04-16 10:50:31
2025-11-07 10:36:13 | Caleb Harris | 800 | 809 | POS upgrade from Win7 (PC only) |  |  | March | 2450 |  | Uncommitted | 0 | 0 | No | Prevent further damage | IT | Technology |  | Deferred |  |  | 2026 | Medium | No |  |  | 2026-04-16 10:50:19
2025-11-07 10:36:13 | Caleb Harris | 800 | 809 | 40 HP Producer |  |  | N/A | 20000 |  |  | 0 | 0 | No | Prevent further damage | Equipment |  |  | 2026 Request |  |  | 2026 | High | Yes |  | 01/12/2026 - Mason Faltysek: Clam Shell on producer is starting to split March? 02/18/2026 - Philip Loper: 02/18 - Sent an email to Jody @ MCWW and requested a proposal. 02/19/2026 - Philip Loper: 02/19 - Sent an email to Jody @ MCWW requesting a proposal. 02/19/2026 - Philip Loper: 02/19 - Recieved a proposal from Jody @ MCWW. This was placed in the CAPEX folder. The cost is $17,079.77 . | 2026-02-19 14:43:28
2025-03-31 08:55:43 | Abel Smith | 800 | 810 | Vacuum - New 50HP Vacutech Producer | 2021 | Q1 | April | 30000 |  | Committed | 30359.85 | -359.85 |  | Planned maintenance | Equipment | Vacuum | Customer Experience | Completed |  | EQ-0810-2025-1184 | 2025 | Low | No |  | 01/12/2026 - unknown: Planned for single unit, Second unit failed. Will be replacing both units. | 2026-01-12 12:31:32
2025-11-07 10:36:13 | Caleb Harris | 800 | 810 | Add POS enclosure at XPTs |  |  | N/A | 10000 |  | Uncommitted | 0 | 0 | No | Customer Experience | IT | Technology |  | Deferred |  |  | 2026 | Medium | No |  | 01/12/2026 - unknown: 02/19/2026 - Bradley Osborne: Going to use this for a tablet instead of an enclosure and new terminal saving around $1 - $2k. | 2026-06-02 16:48:29
2025-11-07 10:36:13 | Caleb Harris | 800 | 811 | Exit Gate Installation |  |  |  | 10000 |  |  | 0 | 0 | No | Customer Experience | Building/Site | Facilities Site Work |  | 2026 Request |  |  | 2026 | Low | No |  | 01/12/2026 - unknown: WX811 | 2026-01-12 12:02:24
2025-03-31 08:55:43 | David Carreon | 800 | 814 | Damage Claim Camera Arch | 2021 | Q4 | N/A | 3000 |  | Uncommitted | 0 | 0 |  | Planned maintenance | IT | Camera | Safety | Deferred |  |  | 2025 | Low | No |  | 01/12/2026 - rusty: Move to Q3 - JMCC | 2026-01-12 12:31:32
2025-03-31 08:55:43 | David Carreon | 800 | 814 | Laguna Tunnel Controller or Washlink PC upgrade | 2021 | Q1 | Complete February | 6500 |  | Committed | 5555.36 | 944.64 |  | Planned maintenance | IT | Technology | Customer Experience | Completed |  | EQ-0814-2025-1203 | 2025 | Low | No |  | 01/12/2026 - unknown: Intalled/ Replaced | 2026-01-12 12:31:32
2025-03-31 08:55:43 | David Carreon | 800 | 814 | LPR Server upgrade from Windows to Linux (No Longer Supported, No update for bug fix available) | 2021 | Q3 | N/A | 1600 |  | Committed | 0 | 0 |  | Planned maintenance | Building/Site | Technology | Safety | Completed |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-08-20 12:24:05 | Abel Smith | 800 | 814 | Dual Prep Unit |  | Q4 | November | 13500 |  | Committed | 0 | 0 | No | Planned maintenance | Equipment | Prep Pump | Customer Experience | Completed |  |  | 2025 | Low | No |  |  | 2026-01-12 12:31:32
2025-11-07 10:36:13 | Caleb Harris | 800 | 814 | 2 AutoSentry upgrades from Win7 |  |  | September | 4076 |  | Committed | 0 | 0 | No | Prevent further damage | IT | Technology |  | Deferred |  |  | 2026 | Medium | No |  | 01/12/2026 - unknown: 03/19/2026 - Eric Dunn: testing note | 2026-08-17 16:48:45
2026-07-27 12:11:11 | Andrew Folse | 800 | 816 | High Pressure Pump Replacement |  |  | September | 11242.32 |  | Committed | 0 | 0 | No | Planned maintenance |  | high pressure pump |  | In-Process | 2026-09-01 | EQ-0816-2026-1937 |  | High | No | No | 07/27/2026 - Andrew Folse: We have spent more than 4k in 1 year replacing hoses due to the pump being oversized | 2026-08-16 13:09:07
2026-07-27 12:12:48 | Andrew Folse | 800 | 817 | High Pressure Pump Replacement |  |  | September | 11242.32 |  | Committed | 0 | 0 | No | Planned maintenance | Equipment |  | Prevent further damage | In-Process | 2026-09-01 | EQ-0817-2026-1938 |  | High | No | No | 07/28/2026 - Andrew Folse: we have spent more than 4k in 1 year replacing hoses due to the pump being oversized | 2026-07-30 16:37:42
2026-04-22 12:59:57 | Chase Cursey | 100 | 901 | Test Vacuum | 2022 | 2 months | July | 13000 |  | Uncommitted | 0 | 0 | No | Planned maintenance | Equipment | Vacuum | Customer Experience | Deferred | 2026-05-15 |  |  | Medium | No | No | 07/20/2026 - Gary Kingsbury: Vacuum Turbine at the End of Life, needing to put turbine on shelf before replacement is needed. 07/20/2026 - Gary Kingsbury: This has been superseded by EQ-0901-2026-1914 and should be cancelled. | 2026-07-20 18:33:21
2026-07-28 13:13:34 | Chase Cursey | 100 | 901 | Updated Towel Dispensers |  |  | October | 12000 |  | Uncommitted | 0 | 0 | No | Planned maintenance | Equipment | Vacuum | Customer Experience | Awaiting Approval |  |  |  | Low | No |  |  | 2026-07-28 13:18:07
2026-07-28 13:11:03 | Chase Cursey | 100 | 902 | Overhead Vacuum Lines |  | Fall 2026 | September | 13000 |  | Uncommitted | 0 | 0 | No | Planned maintenance | Equipment | Vacuum | Customer Experience | Awaiting Approval |  |  |  | Medium | No |  |  | 2026-07-28 13:11:03
2026-07-28 13:15:38 | Chase Cursey | 100 | 902 | Updated Towel Dispensers |  |  | January | 8000 |  | Uncommitted | 0 | 0 | No | Planned maintenance | Equipment | Vacuum | Customer Experience | Awaiting Approval |  |  |  | Low | No |  |  | 2026-07-28 13:15:38
2026-07-28 13:17:51 | Chase Cursey | 100 | 903 | Updated Towel Dispensers |  |  | October | 9600 |  | Uncommitted | 0 | 0 | No | Planned maintenance |  |  |  | Awaiting Approval |  |  |  | High | No |  |  | 2026-07-28 13:17:51
2026-07-28 13:19:15 | Chase Cursey | 100 | 903 | Overhead Vacuum Lines |  |  | October | 13000 |  | Uncommitted | 0 | 0 | No | Planned maintenance | Equipment | Vacuum | Customer Experience | Awaiting Approval |  |  |  | High | No |  |  | 2026-07-28 13:19:15
2026-07-28 13:25:38 | Chase Cursey | 100 | 903 | Front Wheel Push Conversion |  |  | October | 15000 |  | Uncommitted | 0 | 0 | No | Planned maintenance | Equipment | Conveyor Chain | Customer Experience | Awaiting Approval |  |  |  | Medium | No |  |  | 2026-07-28 13:25:38
2026-07-28 13:21:03 | Chase Cursey | 100 | 904 | Updated Towel Dispensers |  |  | October | 8000 |  | Uncommitted | 0 | 0 | No | Planned maintenance | Equipment | Vacuum | Customer Experience | Awaiting Approval |  |  |  | Low | No |  |  | 2026-07-28 13:21:03
2026-07-28 13:22:25 | Chase Cursey | 100 | 904 | Lobby Renovation |  |  | October | 10000 |  | Uncommitted | 0 | 0 | No | Planned maintenance | Building/Site | Building Facilities | Customer Experience | Awaiting Approval |  |  |  | Low | No |  |  | 2026-07-28 13:22:25
2026-07-28 13:26:28 | Chase Cursey | 100 | 904 | Front Wheel Push Conversion |  |  | October | 15000 |  | Uncommitted | 0 | 0 | No | Planned maintenance | Equipment | Conveyor Chain | Customer Experience | Awaiting Approval |  |  |  | High | No |  |  | 2026-07-28 13:26:28
2026-07-28 13:29:54 | Chase Cursey | 100 | 905 | Updated Towel Dispensers |  |  | October | 8000 |  | Uncommitted | 0 | 0 | No | Unplanned | Equipment | Vacuum | Customer Experience | Awaiting Approval |  |  |  | Low | No |  |  | 2026-07-28 13:29:54
2026-07-28 13:31:35 | Chase Cursey | 100 | 905 | Vacuum Canopy Paint and Vinyl Decals |  |  | October | 12500 |  | Uncommitted | 0 | 0 | No | Unplanned | Building/Site | Building Facilities | Customer Experience | Awaiting Approval |  |  |  | Medium | No |  |  | 2026-07-28 13:31:35
2026-07-28 13:28:47 | Chase Cursey | 100 | 906 | Updated Towel Dispensers |  |  | October | 8000 |  | Uncommitted | 0 | 0 | No | Unplanned | Equipment | Vacuum | Customer Experience | Awaiting Approval |  |  |  | Low | No |  |  | 2026-07-28 13:28:47
2026-07-28 13:33:01 | Chase Cursey | 100 | 907 | Updated Towel Dispensers |  |  | October | 8000 |  | Uncommitted | 0 | 0 | No | Unplanned | Equipment | Vacuum | Customer Experience | Awaiting Approval |  |  |  | Low | No |  |  | 2026-07-28 13:33:01
2026-07-28 13:37:26 | Chase Cursey | 100 | 907 | Front Wheel Push Conversion |  |  | October | 10000 |  | Uncommitted | 0 | 0 | No | Unplanned | Equipment | Conveyor Chain | Customer Experience | Awaiting Approval |  |  |  | Low | No |  |  | 2026-07-28 13:37:26
2026-07-28 13:34:11 | Chase Cursey | 100 | 908 | Vacuum Canopy Paint and Vinyl |  |  | October | 12000 |  | Uncommitted | 0 | 0 | No | Unplanned | Building/Site | Building Facilities | Customer Experience | Awaiting Approval |  |  |  | Low | No |  |  | 2026-07-28 13:34:11
2026-07-28 13:34:46 | Chase Cursey | 100 | 908 | Updated Towel Dispensers |  |  | October | 8000 |  | Uncommitted | 0 | 0 | No | Unplanned | Equipment | Vacuum | Customer Experience | Awaiting Approval |  |  |  | Low | No |  |  | 2026-07-28 13:34:46
2026-07-28 13:38:11 | Chase Cursey | 100 | 908 | Front Wheel Push Conversion |  |  | October | 10000 |  | Uncommitted | 0 | 0 | No | Unplanned | Equipment | Conveyor Chain | Customer Experience | Awaiting Approval |  |  |  | Low | No |  |  | 2026-07-28 13:38:11
2026-07-28 13:36:06 | Chase Cursey | 100 | 909 | Vacuum Canopy Paint and Vinyl |  |  | October | 6800 |  | Uncommitted | 0 | 0 | No | Unplanned | Building/Site | Building Facilities | Customer Experience | Awaiting Approval |  |  |  | Low | No |  |  | 2026-07-28 13:36:06
2026-07-28 13:38:50 | Chase Cursey | 100 | 909 | Front Wheel Push Conversion |  |  | October | 10000 |  | Uncommitted | 0 | 0 | No | Unplanned | Equipment | Conveyor Chain | Customer Experience | Awaiting Approval |  |  |  | Low | No |  |  | 2026-07-28 13:38:50
2026-07-28 13:36:43 | Chase Cursey | 100 | 910 | Vacuum Canopy Paint and Vinyl |  |  | October | 15000 |  | Uncommitted | 0 | 0 | No | Unplanned | Building/Site | Building Facilities | Customer Experience | Awaiting Approval |  |  |  | Low | No |  |  | 2026-07-28 13:36:43